## Change Log
Date | Requested by | Updated by | Updates
2014-01-21 | Adam | DJ | Added four new tabs; CHANGE LOG, CTX as of NOV 28, TO BE INVESTIGATED and REMOTE OFFICES
2014-01-21 | Adam | Adam | Protected workbook and marked certain columns as hidden that we can't share with vendor
2014-02-05 | Adam | Adam | Added sites 3968 and 2428 as well as added NPA_NXX (not all just one of per transit)
2014-03-25 | James | James | Added the following columns: Branch Category, RBVP ID, Field Prime, SIP Availability Date, Cabling Completion Date, Centrex Contract Expiry Date, MPLS Upgrade required, Critical Path date, Earliest Scheduled Cutover Date, Cutover Date, On Site Training Date, Tech Prime, ADA Prime, Station Review Date
2014-03-25 | James | James | Added conditional formatting to Access Type field to identify blanks
2014-03-25 | James | James | Added SIP Availability dates to sites where we know SIP is scheduled to be available.
2014-03-27 | James | Elaine | Uploaded Bell's revised version
2014-03-28 | Elaine | Elaine | Selecting potential phase 2 pilot sites _marked transits in green
2014-03-31 | Adam | Adam | On schedule tab.. Deleted duplicate transit 1187, added device for 90771, removed transit 968, changed device name for 616 and updated bandwidth, updated bandwidth for the following sites, 4475 North Service Rd Burlington, 666,1104,1357,1360,1718,1891,1934,2018,2039,2064,2214,2428,3869,3968,4662,4695,4958,5662,6462,7440,90581, deleted access types, deleted all bandwidth calculation columns, deleted order columns
2014-04-04 | Adam | Adam | Major changes for MPLS upgrade tracking
2014-04-08 | Leslie | Leslie | Updated column 'MPLS Upgrade Date' with comments. Reformatted 'Recabling Completion Date'. 'Branch Category' will be static data once populated (Elaine). Added Legend on Change Log Tab.
2014-04-09 | Elaine | Elaine | Updated line 5 to remove it as a Round 2 Pilot Option & updated CIM cabling dates
2014-04-17 | James | James | Added Column A "Phase", updated all "Field Prime" values, added "Cutover Dates" for Phase 1 Pilot sites.
2014-04-23 | Elaine | Elaine | Adding Hours of OP, Postal Codes, LOBs and identifying co_habs
2014-04-28 | Adam | Adam | Added columns AO and AP for e911 use, removed site ID 801335, weekly bandwidth updates
2014-04-28 | Patricia | Patricia | Added Hours of OP
2014-05-01 | James | James | Added Postal Code to 90538.
2014-05-01 | Patricia | Patricia | Added NPA and NNX in column BM
2014-05-14 | James | James | Added Concurrent Call column (W), Added column "Comments" (BW), added "Deleted Sites" tab, removed transit 3932 (part of transit 3752), added back Transit 90701 as it was missed off original (missing data needs validation), added "removed data" tab, added "vlookupdata" tab, added "branch prime name" and "branch prime number" columns (w and x)
2014-05-15 | james | james | added column AY_BH regarding SIP trunking info
2014-05-15 | james | james | removed 2 Bloor st from Phase 2 Pilots (removed colouring) as per Elaine, added Phase 2 pilot dates for 50 cutovers July week 3 and 4. updated Phase 1 pilot site dates to July. Deleted transits 02186 and 02413 as per Elaine (moved to deleted taab)
2014-05-22 | James | James | Updated Pilot 1,2,3,4, to Pilot Phase 1
2014-05-23 | James | James | Updated Green Colouring for Phase 1 and Phase 2 Pilot sites. Highlighted full rows instead of individual cells. Added "Phase 3" (August migrations), and Rollout (September onwards).
2014-05-25 | james | james | Corrected RBVPID 800655 City to "Airdrie" from "Airdie", Added cutover dates for September thru December 2014, Added "Rate Centre Analysis Tab" (Temporary).
2014-05-27 | James | James | Corrected Pilot Phase 1 and 2 dates for July to match Calendar provided by Leslie. Updated sites in Brandon Manitoba to show no SIP availability due to delay in network build. Imacted sites are RBVPID 800226 and 800228. Updated Phase "3" due dates starting Aug 18th.
2014-05-27 | Elaine | Karim | Updated ReCabling Target Completion Dates re Serena CIMs SS
2014-05-27 | Elaine | Elaine | AddedTR617 Wasaga to Round 2 Pilot to replace Brandon, MB site. Added 2 new columns H&I to reflect non_emerg stand alone phone cabling and # of phone numbers completed. Changed column header BL & BO to reflect Targeted Completion Dates. Started standardizing the LOB codes.
2014-05-29 | Karim | Karim | Added all the missing business hours for CB_INS branches (light blue).
2014-06-03 | RBC | James | Deleted column F (Cabling completion date). Added DS Pilot branch hours as 6pm (18:00) branch close. Updated QOS Switch upgrade date to "RBC QOS Upgrade", column BO (Blue "Due Date") removed.re_arranged "red" columns to front of sheet for visibility when scheduling.
2014-06-03 | Elaine | James | dd change for 800052 from aug 26 to tbd . Moved 8000111 from aug 28 to tbd. (cabling)
2014-06-03 | Elaine | James | 801255 dd changed from "" to Aug 26. 800082 dd changed from "" to aug 28.( cabling), updated Column A "Phase" Terminoligy to "Phase 1 Pilot, Phase 2 Pilot, Rollout", moved 800382 to July 21st from July 22nd as per Elaines email.
2014-06-03 | Elaine | James | 801700 under renovation. DD changed from July 14 to TBD. 801914 _ DD moved from Aug 21st to July 14th as a replacement.
2014-06-03 | Elaine | James | Pilot 800188 (642) DD moved to TBD from July 23rd due to cabling. Replaced with 801494 (5602). DD moved from Aug 20 to July 23rd.
2014-06-03 | James | James | Changed 800226 Phase from Phase 2 Pilot to Rollout (NO SIP)
* need new sites for Aug 21st and Aug 20th
2014-06-06 | Elaine | Elaine | removed TR 03822 _ RBVPID 801118 site is closing data added to the deleted sites tab. Site did not have a scheduled migration date.
2014-06-06 | Elaine | Elaine | Move Transit column, Site detail columns to beginning of spreadsheet
2014-06-06 | Elaine | Elaine | Cleaned up LOB naming format
2014-06-06 | Elaine | Elaine | Added 2 columns for Prime Contact Name & Number _ Specified LOB ie DS Prime Contact Name & Number
2014-06-16 | Team | Elaine | Changed Column F to read Site Treatment
2014-06-16 | Team | Elaine | Updated Contact Info name & Number for Phase 1 & Phase 2
2014-06-16 | Team | Elaine | Changed Phase 3 to read Rollout
2014-06-18 | Team | James | Changed: 180, 775, 5029, 5662, 6112, 6800, 6857,90508 from July 21 to July 17. 1306 from July 21 to July 22, 9974 moved from July 24 to 23rd.
2014-06-23 |  | Serena | Added completion dates to Standalone phone columns.
2014-06-30 |  | Serena | Added completion dates to Standalone phone columns.
2014-07-03 |  | Patricia | Transit 7111, RBVP ID 801700, Pilot 2; was moved to the "deleted sites" tab as this site was migrated as part of the RBD project. (was row 444)
2014-07-03 |  | Patricia | Trasit 0642, RBVP ID 800188, Pilot 2; new cutover date to be established later on in the program as cabling will not be completed for Pilot (row 443)
2014-07-03 |  | Patricia | Transit 90508, RBVP ID 803060, Pilot 2; New cutover date to be established, this site was removed from Pilot, cutover date was July 17_2014 (row 40)
2014-07-04 |  | John | Changes made to an incorrect file source. DO NOT USE
2014-07-07 |  | Serena | Changes made to an incorrect file source. DO NOT USE.
2014-07-10 |  | Leslie | Confirmed disconnect in files used on July 4th and 7th. Cleaned up root directory and archives so that latest correct source file is available for John's changes planned for July 11th. .
2014-07-13 |  | Patricia | Pilot Delayed Sites _ Transit 90706, 1504, 200, 1458, 1439, 1810, 720, 5399, 629, 1260, 8577
2014-07-13 |  | Patricia | Pilot Delayed Site 90806 _ Site contact (Stephen Kamachi) requested to be scheduled further down in rollout (Row 14)
2014-07-13 |  | Patricia | Pilot Delayed Site 90591 _ Already rescheduled migration date of July 28th (Row 20)
2014-07-13 |  | Patricia | Pilot Delayed Site Co_hab 3372&11337 (Row 17)
2014-07-13 |  | Patricia | MPLS upgrade order placed, no installation date received, scheduled migration delayed for Transits 236, 9409, 124, 617, 126, 5029.
2014-07-13 |  | Patricia | No MPLS upgrade order placed for Transits 8842 and 180
2014-07-13 |  | Patricia | Row 76, Transit 5220 _ MPLS upgrade being confirmed with Adam and Jackie
2014-07-13 |  | Patricia | Row 75, Transit 4329 _ Postponed due to construction re:Nadia
2014-07-13 |  | Patricia | Row 86 _ Transit 3749 and Row 109 Transit 3779 postponed due to Project Maple. Also part of Project Maple Row 245 Transit 10773 migration date of October 14th D. Dubuc recommended October 14th migration date.
2014-07-13 |  | Patricia | Row 890 _ Transit 4506 _ Branch closing
2014-07-13 |  | Patricia | Re_labelled column "BO" to be Change Request Number
2014-07-13 |  | Patricia | Re_labelled column "BP" to be Communication T_30 Date
2014-07-13 |  | Patricia | Re_labelled column "BQ" to be Communication T_20 Date
2014-07-13 |  | Patricia | Re_labelled column "BR" to be Communication T_2 Date
2014-07-13 |  | Patricia | Transit 576 _ Added Alternate Contact (Anna Cherian) to column H
2014-07-13 |  | Patricia | Transit 567 _ Added Alternate Contact (Maria Ruiz) to column H
2014-07-14 |  | Serena | Updated dates and number of phones in Standalone column.
2014-07-16 |  | Patricia | Transit 3372 _ Added cutover date of July 28th 2014 (Co_Hab) (Row 17)
2014-07-16 |  | Patricia | Transit 11337 _ Added cutover date of July 28th 2014 (Co_Hab) (now Row 18)
2014-07-16 |  | Patricia | Transit 5220 _ Added cutover date of August 19th 2014 (previously Roll out delay) (now Row 77)
2014-07-16 |  | Patricia | Transit 775 _ Pilot Delay _ changed cutover date to Pilot Delay (Previously scheduled for July 17th) (Row 35)
2014-07-16 |  | Serena | Added new column X _ Standalone phone target date.
2014-07-17 |  | John | Ran script to update column AV, AX, AZ and BA
2014-07-21 |  | Serena | Updated dates and number of phones in Standalone column.
2014-07-22 |  | Brenda | MPLS circuit order updates
2014-07-23 |  | Patricia | Row 42, Transit 1306 _ Added cutover date of July 28th 2014 (Co_Hab)
2014-07-23 |  | Patricia | Row 43, Transit 11271 _ Added cutover date of July 28th 2014 (Co_Hab) (Added this Row)
2014-07-23 |  | Patricia | Row 11, Transit 01810 _ Added cutover date of July 28th 2014 (previously Pilot Delay)
2014-07-23 |  | Patricia | Row 32, Transit 03680 _ Added cutover date TBD Pilot Delay (previously scheduled for July 16)
2014-07-23 |  | Patricia | Row 33, Transit 08399 _ Added cutover date TBD Pilot Delay (previously scheduled for July 16)
2014-07-23 |  | Patricia | Row 29, Transit 01341 _ Added cutover date TBD Pilot Delay (previously scheduled for July 16)
2014-07-23 |  | Patricia | Row 39, Transit 06800 _ Added cutover date TBD Pilot Delay (previously scheduled for July 17)
2014-07-23 |  | Patricia | Row 40, Transit 06857 _ Added cutover date TBD Pilot Delay (previously scheduled for July 17)
2014-07-23 |  | Patricia | Row 48, Transit 08067 _ Added cutover date TBD Pilot Delay (previously scheduled for July 22)
2014-07-23 |  | Patricia | Row 52, Transit 00126 _ Added cutover date Tentative July 28_29 (previously roll out delay_July 23)
2014-07-23 |  | Patricia | Row 61, Transit 00617 _ Added cutover date Tentative July 28_29 (previously roll out delay_July 24)
2014-07-23 |  | Patricia | Row 54, Transit 05207 _ Added cutover date Tentative July 24 (previously scheduled for July 23)
2014-07-23 |  | Patricia | Row 62, Transit 02147 _ Added cutover date TBD Pilot Delay (previously scheduled for July 24)
2014-07-23 |  | Patricia | Row 10, Transit 01439 _ Added cutover date of July 29th 2014 (previously Pilot Delay)
2014-07-23 |  | Patricia | Row 47, Transit 07319 _ Added cutover date of July 31 (previously scheduled for July 22)
2014-07-23 |  | Patricia | Row 58, Transit 09974 _ Added cutover date of July 31 (previously scheduled for July 23)
2014-07-24 |  | Patricia | Row 52, Transit 00126 _ Added cutover date of July 28 (previously tentative July 28_29)
2014-07-24 |  | Patricia | Row 61, Transit 00617 _ Added cutover date of July 28 (previously tentative July 28_29)
2014-07-24 |  | Patricia | Row 54, Transit 05207 _ Added cutover date of July 24 (previously tentative July 24)
2014-07-24 |  | Patricia | Row 10, Transit 01439 _ Added cutover date of July 31 (previously July 29)
2014-07-24 |  | Patricia | Row 43, Transit 11271 _ Added the address 9495 Mississauga Rd, Brampton, On(Co_Hab)
2014-07-24 |  | Patricia | Row 66, Transit 08842 _ Updated site contact to be Danielle Demartin 519_979_2774 instead of Lina Peters
2014-07-24 |  | Patricia | Row 1116, Transit 7191 _ Added in the cutover date **see comments **Comments added Renovations**Please contact Jean L'Heureux PND Regional Mgr for QC, before scheduling conversions (No cutover date previously)
2014-07-24 |  | Patricia | Row 712, Transit 2591 _ Added in the cutover date **see comments **Comments added Renovations**Please contact Jean L'Heureux PND Regional Mgr for QC, before scheduling conversions (No cutover date previously)
2014-07-28 |  | Serena | Updated dates and number of phones in Standalone column.
2014-07-29 |  | Brenda | Updated MPLS upgrade dates
2014-08-01 |  | Serena | Updated dates and number of phones in Standalone column.
2014-08-06 |  | Patricia | Row 3 _ Transit 06262 _ Changed column C (Branch Category) from PC&B_DS to PC&B
2014-08-06 |  | Patricia | Row 1436 _ Transit 90453 added for DS using existing RBVP ID of 801598, 2175 Queen St E, Floor 2 (same address as Transit 6262 _ Queen & Lee)
2014-08-07 |  | Patricia | Row 67 _ Transit 00234 _ changed Branch Category to PC&B_INS**Added Comments: Ins 15317 16504 50 ST NW , EDMONTON , AB
2014-08-07 |  | Patricia | Row 81 _ Transit 00314 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15266 222 MONTEE MASSON_UNIT 7
2014-08-07 |  | Patricia | Row 99 _ Transit 04356 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15289 500 HAZELDEAN RD_UNIT 103 , KANATA
2014-08-07 |  | Patricia | Row 132 _ Transit 00960 **Added Comments: They are located at 315 FRONT ST W_3RD FLR , TORONTO , ON
2014-08-07 |  | Patricia | Row 146 _ Transit 00836 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15345 383 ASPEN GLEN LANDING SW_UNIT 103 , CALGARY , AB
2014-08-07 |  | Patricia | Row 205 _ Transit 00541 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15230 7250 TASCHEREAU BLVD_UNIT 16
2014-08-07 |  | Patricia | Row 232 _ Transit 00477 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15272 5051 HWY 7_UNIT 101A , MARKHAM
2014-08-07 |  | Patricia | Row 311 _ Transit 00316 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15262 670 KINGSTON RD_UNIT 157
2014-08-07 |  | Patricia | Row 318 _ Transit 00409 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15269 365 HIGH TECH RD_BUILDING C_UNIT 2 , TORONTO
2014-08-07 |  | Patricia | Row 345 _ Transit 04409 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15275 82ND AVE & 83RD ST_UNIT 155 , EDMONTON , AB
2014-08-07 |  | Patricia | Row 356 _ Transit 00476 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15305 55B BRYNE DR , BARRIE , ON
2014-08-07 |  | Patricia | Row 360 _ Transit 06892 _ changed Branch Category to PC&B_INS **Added Comments: ins 15316 5222 130TH AVE SE_UNIT 405 , CALGARY , AB,
2014-08-07 |  | Patricia | Row 453 _ Transit 00170 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15267 231 CHAMPLAIN ST_SUITE 101 , DIEPPE , NB
2014-08-07 |  | Patricia | Row 454 _ Transit 00192 _ changed Branch Category to PC&B_DS **Added Comments: DS 90414 3300 HIGHWAY 7_7TH FLR , CONCORD , ON
2014-08-07 |  | Patricia | Row 483 _ Transit 00533 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15273 361 CORNWALL RD_UNIT 107 , OAKVILLE , ON
2014-08-07 |  | Patricia | Row 490 _ Transit 00593 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15302 8940 HIGHWAY 50_UNIT 2 , BRAMPTON , ON
2014-08-07 |  | Patricia | Row 491 _ Transit 00597 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15303 16 FIRST COMMERCE DR_UNIT 16B , AURORA , ON
2014-08-07 |  | Patricia | Row 500 _ Transit 00724 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15327 5322 DUNDAS ST W_UNIT 2 , ETOBICOKE
2014-08-07 |  | Patricia | Row 504 _ Transit 00744 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15309 2880 MAJOR MACKENZIE DR E_UNIT 4 , MARKHAM , ON
2014-08-07 |  | Patricia | Row 506 _ Transit 00754 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15326 3601 MAJOR MACKENZIE DR_UNIT 1A , WOODBRIDGE , ON
2014-08-07 |  | Patricia | Row 535 _ Transit 00909 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15407 2212 BANK ST_UNIT B , OTTAWA , ON
2014-08-07 |  | Patricia | Row 539 _ Transit 00934 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15268 1206 PROSPECT ST , FREDERICTON , NB
2014-08-07 |  | Patricia | Row 560 _ Transit 01124 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15442 300 KING GEORGE RD_UNIT C2 , BRANTFORD , ON
2014-08-07 |  | Patricia | Row 648 _ Transit 02014 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15420 515 WESTMORELAND RD_UNIT C009B , ST JOHN , NB
2014-08-07 |  | Patricia | Row 649 _ Transit 02034 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15271 1803 STONE CHURCH RD E_UNIT 2 , STONEY CREEK , ON
2014-08-07 |  | Patricia | Row 654 _ Transit 02080 _ changed Branch Category to PC&B_DS **Added Comments: DS 90839 101 _ 8411 200th St Langley BC
2014-08-07 |  | Patricia | Row 676 _ Transit 02204 _ changed Branch Category to PC&B_DS **Added Comments: DS 90282 664 Main St Sussex, NB
2014-08-07 |  | Patricia | Row 726 _ Transit 02755 _ changed Branch Category to PC&B_INS **Added Comments: Ins 12994 3535 ST_CHARLES BLVD_SUITE 100 , KIRKLAND , QC
2014-08-07 |  | Patricia | Row 775 _ Transit 03232 _ changed Branch Category to PC&B_INS **Added Comments: Ins 15250 4141 DIXIE RD_UNIT 7 , MISSISSAUGA , ON
2014-08-07 |  | Patricia | Row 810 _ Transit 03630 _ changed Branch Category to PC&B_DS **Added Comments: DS 90282 664 Main St. Sussex NB
2014-08-07 |  | Patricia | Row 829 _ Transit 03722 _ changed Branch Category to PC&B_DS **Added Comments: DS 90512 48 PEMBROKE ST W , PEMBROKE , ON
2014-08-07 |  | Patricia | Row 863 _ Transit 04130 _ changed Branch Category to PC&B_DS **Added Comments: DS 90855 152 South Alberni Hwy, Parksville, BC
2014-08-07 |  | Patricia | Row 872 _ Transit 04238 _ changed Branch Category to PC&B_DS **Added Comments: DS 90763 4716 50TH AVE , LLOYDMINSTER , SK
2014-08-07 |  | Patricia | Row 934 _ Transit 05010 _ changed Branch Category to PC&B_DS **Added Comments: DS 90809 5760 Teredo St _ Unit 212
2014-08-07 |  | Patricia | Row 1023 _ Transit 05942 _ changed Branch Category to PC&B_INS **Added Comments: Ins 12990 1571 SANDHURST CIRCLE , SCARBOROUGH , ON
2014-08-07 |  | Patricia | Row 1078 _ Transit 06603 _ changed Branch Category to PC&B_DS **Added Comments: DS 90270 one employee 404 Charlotte St Sydney BC
2014-08-07 |  | Patricia | Row 1103 _ Transit 06832_ changed Branch Category to PC&B_INS **Added Comments: Ins 11338 2900 WARDEN AVENUE_UNIT 209 , SCARBOROUGH , ON
2014-08-07 |  | Patricia | Row 1245 _ Transit 08400 _ changed Branch Category to PC&B_DS **Added Comments: DS 90865 1705 Marine Dr West Vancouver, BC
2014-08-07 |  | Patricia | Row 1282 _ Transit 09077_ changed Branch Category to PC&B_INS **Added Comments: Ins 15304 550 LAVAL DR_UNIT # 200 , OSHAWA , ON
2014-08-07 |  | Patricia | Row 1423 _ Transit 90832 _ changed Branch Category to DS **Added Comments: Removed PH&N from LOB not necessary
2014-08-07 |  | Patricia | Row 1427 _ Transit 90851 _ changed Branch Category to DS **Added Comments: Removed PH&N from LOB not necessary
2014-08-07 |  | Patricia | Row 226 _ Transit 00458_ changed Branch Category to PC&B_INS **Added Comments: INS 15308 1520 Major Mackenzie Drive, Suite 200
2014-08-07 |  | Patricia | Row 228 _ Transit 00651 _ changed Branch Category to P&CB**Added Comments: Changed from Co_Hab to one LOB which is P&CB
2014-08-07 |  | Patricia | Row 378 _ Transit 00522 _ changed Branch Category to P&CB_DS **Added Comments: DS 90565 22 Colborne St _ 2nd Flr Second Floor
2014-08-07 |  | Patricia | Row 396 _ Transit 06389 _ changed Branch Category to P&CB**Added Comments: Changed from Co_Hab to one LOB which is P&CB
2014-08-07 |  | Patricia | Row 532 _ Transit 00892 _ changed Branch Category to P&CB_DS **Added Comments: DS 90531 8 Queen St N _ Bolton North Branch _ No DS employees show on Emp. Dir.
2014-08-07 |  | Patricia | Row 686 _ Transit 02301_ changed Branch Category to P&CB_INS **Added Comments: INS 11181 3100 Boul Le Carrefour _ Suite 115
2014-08-07 |  | Patricia | Row 1290 _ Transit 09181 _ changed Branch Category to P&CB**Added Comments: Changed from Co_Hab to one LOB which is P&CB
1900-01-06 |  | Patricia | Updated PC&B to P&CB in the Branch Category
2014-08-08 |  | John | Ran script to update column AV, AX, AZ and BA
2014-08-08 |  | James | Updated migration schedule dates starting September 8th, 2014. All existing dates DELETED. All dates are new dates. Highlighted Insurance sites Blue for visibility. Highlighted DS sites red for visibility
2014-08-12 |  | Patricia | Row 2 _ Transit 7323 _ (P&CB) 95 King St S _ The transit number was changed from 5702 to 7323 because 5702 was a mailing transit. Cutover date was changed to September 10th from September 08th. Training date was removed. Postal Code changed to N2J 5A2.
2014-08-12 |  | Patricia | Row 3 _ Transit 90561 _ Row added (DS) 95 King St S _ The transit number was added for the DS location. Training date of September 11th.
2014-08-12 |  | Patricia | Row 19 _ Transit 12991 _ (INS) 2 Bloor St E _ Cutover date has changed to September 15th from September 22nd.
2014-08-12 |  | Patricia | Row 10 _ Transit 6702 _ (P&CB) 2 Bloor St E _ Training date was removed.
2014-08-12 |  | Patricia | Row 11 _ Transit 90428 _ Row added (DS) 2 Bloor St E, Fl 23 _ The transit number was added for the DS location. Training date of September 16th.
2014-08-12 |  | Patricia | Row 39 _ Transit 2692 (PH&N_Co_hab) 383 Richmond St, London _ Cutover date changed to September 29th instead of September 25th as INS Transit 13158 is also at this location
2014-08-12 |  | Patricia | Row 554 _ Transit 2722 (P&CB) 383 Richmond St, London _ Added cutover date of September 29 from no Cutover Date
2014-08-13 |  | Patricia | Transit 892 _ The Branch category updated to show P&CB instead of P&CB_DS. No DS staff is at this location.
2014-08-13 |  | Patricia | Transit 593 _ P&CB (Co_Hab) 8940 Highway 50. Branch category updated to show P&CB instead of P&CB_INS
2014-08-13 |  | Patricia | Transit 15302 (INS) (Co_Hab) added _ 8940 Highway 50. Branch category updated to show INS
2014-08-13 |  | Patricia | Transit 754 _ P&CB (Co_Hab) 3601 Major Mackenzie. Branch category updated to show P&CB instead of P&CB_INS
2014-08-13 |  | Patricia | Transit 15326 (INS) (Co_Hab) added _ 3601 Major Mackenzie. Branch category updated to show INS
2014-08-13 |  | Patricia | Transit 13158 (INS) Co_Hab _ 383 Richmond St, London _ cutover date removed as Transit 2722 at this location requires switch upgrades
2014-08-13 |  | Patricia | Transit 2692 (PH&N) Co_Hab _ 383 Richmond St, London _ cutover date removed as Transit 2722 at this location requires switch upgrades
2014-08-13 |  | Patricia | Transit 2722 (P&CB) Co_Hab _ 383 Richmond St, London _ cutover date removed, switch upgrade required
2014-08-13 |  | Patricia | Transit 2034 _ P&CB (Co_Hab) 1803 Stone Church Rd E. Branch category updated to show P&CB instead of P&CB_INS
2014-08-13 |  | Patricia | Transit 12918 (INS) (Co_Hab) added _ 1803 Stone Church Rd E. Branch category updated to show INS
2014-08-13 |  | Patricia | Transit 234 _ P&CB (Co_Hab) 16508 50 St NW. Branch category updated to show P&CB instead of P&CB_INS
2014-08-13 |  | Patricia | Transit 15317 (INS) (Co_Hab) added _ 16504 50 St NW. Branch category updated to show INS
2014-08-13 |  | Patricia | Transit 2320 _ P&CB (Co_Hab) 186 Victoria St. Branch category updated to show P&CB instead of P&CB_DS
2014-08-13 |  | Patricia | Transit 90823 (DS) (Co_Hab) added _ 186 Victoria St. Branch category updated to show DS
2014-08-18 |  | Serena | Sites that are IPT ready as per column AR, I added a N_A in the standalone columns as no CIM visit is required.
2014-08-18 |  | Serena | Updated dates and number of phones in Standalone column.
2014-08-19 |  | Brenda | MPLS circuit order updates
2014-08-20 |  | James | Due Date changes: DD Changes: 801645 _ Transit 6702 – 2 Bloor St E. Toronto– DD Sept 15th. New DD TBD 802444 _ Transit 12991 – 2 Bloor St E. Toronto – DD Sept 22nd – New DD TBD 800180 _ Transit 616 – 6 Fort York, Toronto – DD Sept 16th – New DD TBD 800809 _ Transit 02692 (PH&N_Co_Hab) – 383 Richmond st, London – DD Sept 25th – New DD Sept 29th (now migrating multiple “transits” at the same address on the same date) 800816 _ Transit 02722 (P&CB), _ 383 Richmond St. London – DD was TBD – New DD Sept 29th. New additions to schedule (previously had no dates assigned) 800368 _ Transit 1265 – 480 Dundas St. E. Toronto.– DD Sept 15th 800581 _ Transit 1710 – 2 Gladstone, Toronto – DD Sept 22nd 801649 _ transit 6742 – 468 Yonge St. Toronto_ DD Sept 16th 800600 _ transit 1772 _ 117 SILVERCREEK PKWY N Guelph – DD Sept 25th
2014-08-20 |  | James | 803082 Transit 90561 ON RBCDS INC_KITCHENER 95 KING ST S_3RD FLR WATERLOO Ontario Is now also scheduled for Sept 10th DD was Null Deleted Duplicate row entry for 90561 (one without an RBVPID)
2014-08-20 |  | James | Data removed from Critical Path Date column and Earliest Scheduled cutover date column as no longer required.
2014-08-20 |  |  | Changed font from 20pt to 10pt. Changed zoom from 50% to 75% _ PLEASE DO NOT ADJUST FONT SIZE. IF YOU NEED THE TEXT BIGGER USE THE ZOOM FUNCTION.
2014-08-20 |  | James | Transit 1616 Cancelled and moved to Deleted sites tab as branch is closing
2014-08-25 |  | james | added row to identify Insurance component for 800118. now split into 800118a and 800118b. Added transit 15270 and 13214. Changed due date to Sept 15th as it needs to be on a Monday.
2014-08-25 |  | james | 95 king st st waterloo _ 801505 and 803082 DD's moved from Sept 10th to TBD as LOB advised we cannot migrate first week of sept.
2014-08-25 |  | james | Transit 90428 _ RBVPID was deleted. Re_added 803051.
2014-08-25 |  | james | 801649 _ 6742 _ DD changed from Sept 16th to TBD as branch is relocating in December
2014-08-25 |  | james | Added new dates: 800311 _ 1117 _ Sept 18th 800271 _ 942 _ Sept 17th 800466 _ 1517 _ Sept 16th
2014-08-25 |  | james | updated formula to show T_40 for Bell West sites Branch Audit date and added Holiday Calendar to account for holidays (Rate Centre Tab)
2014-08-25 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-09-01 |  | DJ | 800343 changed to 809001 and changed migration date to Nov 19
2014-09-01 |  | DJ | re moved cutover dates for 801565 as per email with Robert (aug 29, 1:26 pm)
2014-09-01 |  | DJ | re moved cust over dates for 801005 as per email from Serena (aug18, 11:20am)
2014-09-02 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-09-02 |  | James | 802470 _ 13147 _ DD moved from Sep 22 to Sep 30th, to match other LOB's.
|  | James | 800311 _ 1117 _ DD POSTPONED FROM SEPT 18TH. Branch not communicated to and no station review.
|  | James | 801493 _ 5600 _ DD moved from Nov 23rd (Sunday) to Jan 6th, 2015
|  | James | 800594 _ 1760 _ Moved from October 28th to Jan 13th, 2015 as per RBC request
| patricia | James | 800086 _ updated address to 336 University Dr. W.
| patricia | James | RBVP ID 800809, Transit 02692 PH&N _ 383 Richmond St, London. changed the floor number from Floor 7 to Floor 8.
| patricia | James | 800681, Transit 02115 _ P&CB _Address updated to 4056 Confederation Parkway, Mississauga, Ontario L5B 0G4 from _ C_O 33 CITY CENTRE DR L5B 2N5 as this was an old mailing address
2014-09-03 |  | Patricia | Transit 3497, RBVP ID 801015, changed the Branch Category from INS to PH&N (50 O'Connor)
2014-09-03 |  | Patricia | Inserted row for Transit 10767, RBVP ID 801015, Branch Category P&CB (50 O'Connor)
2014-09-03 |  | Patricia | Changed column AM to read On Site Training instead of 05_Mar_00
2014-09-05 |  | Patricia | Audit Mtg Sept 05, Transit 06402, RBVP ID 801612, Collision with RBD project, the migration date is to be rescheduled from September 18th to a new date TBD. Communications were sent out previously to this location. Audit and Cutover date removed.
2014-09-05 |  | Patricia | Audit Mtg Sept 05 . Transit 15317, RBVP ID 809006 was added, RBVP ID was blank previously
2014-09-08 |  | Patricia | Audit Mtg _ Sept. 08th = Transit 03497, New RBVP ID assigned to PH&N _ 809003 instead of 801015
2014-09-09 |  | Patricia | Transit 3497, RBVP ID 809003, PH&N 50 O'Connor, added on site training date of September 09th
2014-09-09 |  | Patricia | Transit 13158, RBVP ID 802473 (INS) Co_Hab _ 383 Richmond St _ added cutover date of Sept. 29 as it was blank before
2014-09-09 |  | Brenda | MPLS Updates.
2014-09-10 |  | Patricia | Audit Mtg _ Sept 10th _ Transit 1718 RBVP ID 800584. Added IPT = Yes to this location, identified by Bell. Colum was blank previously.
2014-09-10 |  | Patricia | Sept 10. Transit 90428, RBVP ID 803051. The cutover date was changed to TBD instead of Sept. 15th. There are multiple LOB's at this address, no audit completed as per Sal Gabal. Previously reviewed by Donna and James
2014-09-10 |  | Patricia | Sept. 10. Transit 9057, RBVP ID 802066. Cutover date changed to TBD from Sept. 17. This was reviewed previously by Donna and James
2014-09-11 |  | DJ | Removed audit and migration date 801322 from Transit 4529 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800856 from Transit 2880 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800758 from Transit 2440 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800749 from Transit 2419 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800374 from Transit 1280 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800013 from Transit 80 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800110 from Transit 373 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | Removed audit and migration date 800456 from Transit 1486 as per email (and live discussion) with James sept 3rd (3:16 pm)
2014-09-11 |  | DJ | 800095 transit 320
2014-09-11 |  | DJ | 801103 transit 3779
2014-09-11 |  | DJ | 800635 transit 1934
2014-09-11 |  | DJ | 800204 transit 716
2014-09-11 |  | DJ | 800745 transit 2400
2014-09-11 |  | DJ | 803116 transit 90731
2014-09-11 |  | DJ | 800049 transit 177
2014-09-11 |  | DJ | 801730 transit 7360
2014-09-11 |  | DJ | 800275 transit 960
2014-09-11 |  | DJ | 800196 transit 683
2014-09-11 |  | DJ | 801849 transit 7920
2014-09-11 |  | DJ | 801472 transit 5489
2014-09-11 |  | DJ | 801660 transit 6800
2014-09-11 |  | DJ | 800094 transit 319
2014-09-11 |  | DJ | 801473 transit 5500
2014-09-11 |  | DJ | 800286 transit 1040
2014-09-11 |  | DJ | 800494 transit 1549
2014-09-11 |  | DJ | 802010 transit 87 19
2014-09-11 |  | DJ | 801457 transit 5399 _ all entried above had the audit and migration dates removed by DJ as discusssed with James sept 3 (email from 3:16pm
2014-09-11 |  | Patricia | Audit Mtg _ Sept 11th _ Transit 9057 RBVP ID 802066. Changed cutover date to Sept. 17 from TBD. The audit, T30 are completed.
2014-09-11 |  | Patricia | Audit Mtg _ Sept 11th _ Transit 1117 RBVP ID 800311. Changed cutover date to Sept. 18 from TBD. The audit, T30 are completed.
2014-09-11 |  | Patricia | Transit 13147, RBVP ID 802470, 111 Grangeway, Changed the cutover date to Oct. 30 (Thursday) from Sept. 30. INS migration is during the day.
2014-09-11 |  | Patricia | Transit 90417, RBVP ID 803050, 111 Grangeway, Changed the cutover date to Oct. 30 from Sept. 30.
2014-09-12 |  | JM | Ran script to update column AV | AX | AZ and BA
2014-09-14 | Elaine | Patricia | Transit 2931, RBVP ID 800867 P&CB . Changed the cutover date to TBD from October 08. To be scheduled for January 2015
2014-09-14 | Elaine | Patricia | Transit 6781, RBVP ID 801659 P&CB . Changed the cutover date to TBD from October 27. To be scheduled for January 2015
2014-09-14 | Elaine | Patricia | Transit 90331, RBVP ID 803038 DS, Multi_site, 2828 Laurier Blvd QC . Added cutover date for October 09 from no scheduled date.
2014-09-15 |  | Serena | TR 7862 _ Site added to re_cabling list as it was identified as Type 1 cabling
2014-09-15 |  | Serena | TR 1252 _ Site added to re_cabling list as it was identified as Type 1 cabling
2014-09-15 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-09-16 |  | Brenda | 150 updates to MPLS circuits and POE switches
2014-09-17 |  | Brenda | Updated MPLS Required Column to Yes, as required
2014-09-17 | Audit Mtg | Patricia | Audit Mtg: Sept 15th, Transit 496, RBVP ID 800144. Removed 1 from Colum AR. Bell identified that this is a Centrex location.
2014-09-17 | Elaine | Patricia | Transit 2204, RBVP ID 800708, 664 Main Street, NB. Cutover date changed to TBD from January 08. No SIP available. Replacement site needed
2014-09-17 | Elaine | Patricia | Transit 7310, RBVP ID 801726, 195 Fort St, Winnipeg MB. Cutover date changed to TBD from Nov. 05 due to Centrex sites not starting until W3. Replacement site needed
2014-09-17 | Elaine | Patricia | Transit 8067, RBVP ID 801912, 2855 Pembia, Winnipeg MB. Changed cutover date to TBD from Nov 11. due to Centrex sites not starting until W3. Replacement site needed.
2014-09-17 | Elaine | Patricia | Transit 1753 RBVP ID 800593. 50 Sage Creek Blvd Winnipeg, MB. cutover date to TBD from November 03. No communications sent. Replacement site needed.
2014-09-17 | Elaine | Patricia | Transit 90805, RBVP ID 803132, 2052 West 41st, Vancouver. Added Audit date of Sept. 25 and Cutover date of Nov 25 as these fields were not populated previously
2014-09-17 | Elaine | Patricia | Updated Colum BQ to reflect Communication Target Date T_65_35 (Purple)
2014-09-17 | Elaine | Patricia | Updated Colum BR to reflect Communication Actual Date T_65_35 (Purple)
2014-09-17 | Elaine | Patricia | Updated Colum BS to reflect Communication Target Date T_3 (Purple)
2014-09-17 | Elaine | Patricia | Updated Colum BT to reflect Communication Actual Date T_3 (Purple)
2014-09-17 | Elaine | Patricia | Transit 14326, RBVP ID 809012, 3250 Bloor St W. Cutover date Oct. 06. Added row to match the other LOB at this location as this was identified as a multi site.
2014-09-18 | RBC | James | Copied completed sites back over to schedule tab and deleted completed sites tab. Removed data on VLOOKUP tab as it was old data from out of date master. Deleted Rate Centre Analysis data _ No longer relevant. Updated holiday schedule to properly show Thanksgiving as Oct 13th (not Oct 14th).
2014-09-18 | RBC | James | Removed conditional formatting from Branch hours columns. Cleared blue highlighting from same columns. Minimized Saturday_Sunday branch hours.
2014-09-18 | RBC | James | Updated Bell columns BU to CG to add not in use where applicable. Changed column BV "Service Extension Y or N" to "Trunk Group Name"
2014-09-18 | RBC | James | Imported all available trunk group data.
2014-09-18 | RBC | James | UPDATED BP from Change Record to "RBC Activity Record".
2014-09-18 | RBC | James | Minimized BQ_BR_BS
2014-09-18 | RBC | James | Updated Legend
2014-09-18 | RBC | James | 800330 _ 1202 _ Moved from TBD to Oct 27th (QC branch)
2014-09-18 | RBC | James | 801790 _ 7671 _ Moved from TBD to Oct 27th (QC branch)
2014-09-19 | RBC | Leslie | Added legend for RBC columns shaded light and dark purple. Updated available AR details for cutovers.
2014-09-21 |  | Patricia | Transit 90439 (803052) 3250 Bloor: Cutover date changed to TBD from Oct. 06, No communication or Audit completed. Site replacement required.
2014-09-21 |  | Patricia | Transit 14326 (809012) 3250 Bloor: Cutover date changed to TBD from Oct. 06, No communication or Audit completed. Site replacement required.
2014-09-21 |  | Patricia | Transit 3502 (801016) 279 Lakeshore Rd, Updated branch category from PH&N to P&CB
2014-09-21 |  | Patricia | Transit 15476 (809016) 279 Lakeshore Rd. PH&N Insreted a row. Cutover date of October 09th with traning of Oct. 10
2014-09-21 |  | Patricia | Transit 8030 (801902) 707 Fort St, Victoria BC, Updated branch category from PH&N to P&CB
2014-09-21 |  | Patricia | Transit 3587 (809015) 707 Fort St, Victoria BC, PH&N. Inserted a row. Cutover date November 20 with training of November 21
2014-09-21 |  | Patricia | Transit change to 7473 (801658) from transit 6676. 260 Spadina
2014-09-21 |  | Patricia | Transit 9311 (802151) 4849 Sherbrooke QC cutover date changed to TBD from Nov. 06 due to client request. Site replacement required.
2014-09-21 |  | Patricia | Transit 6221 (801593) 2835 Ave Van Horne QC cutover date changed to TBD from Nov. 11 due to client request. Site replacement required.
2014-09-21 |  | Patricia | Transit change to 8523 (800851) from transit 2857, employees at this location are associated with T8523
2014-09-21 |  | Patricia | Transit 7269 (801724) 614 4th Ave S, Lethbridge AB. Cutover date changed to TBD from Nov. 19. Site replacement required
2014-09-21 |  | Patricia | Transit 3749 (801096) 10107 Jasper Ave, Edmonton AB. Cutover date changed to TBD from Nov. 27. Site replacement required
2014-09-21 |  | Patricia | Transit 3561 (801027) 7151 Jean Talon St, Anjou QC. Cutover date changed to Oct 23 from Oct 08. Site rescheduled as per client's request
2014-09-22 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-09-23 |  | Brenda | Various update to MPLS circuit completions
2014-09-24 |  | Patricia | Transit 15112 (802774) The cutover date was changed to TBD from November 17. This location has ACD application and will be rescheduled in the new year. No Communication or Audit were done. Site replacement needed.
2014-09-24 |  | Leslie | AR Record details added up to Oct 3rd
2014-09-28 |  | Patricia | Transit 741 (800210) Address updated to 3701 Frechette Blvd, Ste 102; from 15 PLACE CHAMBLY (known as 1233 Périgny) UD and ED did not have the 15 Place Chambly address.
2014-09-28 |  | Patricia | Transit 12918 added new RBVP ID 809017 to INS at 1803 Stone Church, Stoney Creek. Previously no RBVP ID.
2014-09-28 |  | Patricia | Transit 6419 (801614), branch category update to P&CB Sales only unit from Sales only unit
2014-09-28 |  | Patricia | Transit 7473 (801658) 260 Spadina. The cutover date was changed to TBD from October 16. No communication or Audit completed. Site replacement required for early November. Coordination of due date with 500 Dundas, Transit 6752 (801650).
2014-09-28 |  | Patricia | Transit 6752 (801650) The cutover is TBD from a blank entry. Please coordinate the cutover date with 260 Spadina, Transit 7473 (801658).
2014-09-28 |  | Patricia | Transit 7319 (801728) The cutover date changed to TBD from July 31. Location is 1240 2A Ave, Lethbridge AB which was rescheduled from Pilot, the cutover date remained as July 31. New scheduled date required.
2014-09-28 |  | Patricia | Transit 192 (800054) P&CB, 3300 Hwy 7, Concord. Cutover date has been changed to TBD from January 06, James to use this location as a site replacement location for November. The business has approved the shortened communications timelines. The cutover date is to be coordinated with Transit 13152 (809018) for INS at the same location.
2014-09-28 |  | Patricia | Transit 13152 (809018) New RBVP ID and row inserted for INS at 3300 Hwy 7, Ste 320, Concord. Cutover date is TBD, James to use this location as a site replacement location for November. The business has approved the shortened communications timelines. The cutover date is to be coordinated with Transit 192 (800054) for P7CB at the same location.
2014-09-29 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-09-30 |  | Brenda | Updates MPLS Completion dates for TR#2762, 7582, 7712.
2014-10-01 |  | Patricia | Transit 6012 (801562) 65 Queen St. Removed from the Scheduled Tab and was placed in the Deleted site tab. Note: The location at 65 Queen St, is not a branch, it only has 1 telephone line and it is located in the Thompson Building. If the location will support IPT, then it should be part of the 20 King St. IPT services. This was confirmed by the RMO. Cutover was scheduled for November 12. No communications sent. Site replacement needed for November in Ontario.
2014-10-01 |  | Patricia | Transit 59 (800010) 207 Queen's Quay West. Removed from the Scheduled Tab and was placed in the Deleted site tab. Note: The Queen's Quay location was removed from migration as the new location will be a GU site. This was confirmed by the RMO. Cutover was scheduled for December 09. No communications sent. Site replacement needed for December in Ontario.
2014-10-01 |  | Patricia | Transit 15326 RBVP ID added (809013) for INS at 3601 Major Mackenzie from blank.
2014-10-01 |  | Patricia | Transit 5462 (801466) 831 College St. Cutover date of November 06 was removed from Scheduled Tab and placed in the Deleted site tab. This transit was a duplicated row on the schedule. The location has CLOSED, this was confirmed by the client. No site replacement needed as 5462 (801467) at 833 College St. is still on the scheduled tab. Cutover date needed.
2014-10-01 |  | Patricia | Transit 1211 (800332) 3610 St. Jean Blvd. updated Colum AR to reflect IPT
2014-10-01 |  | Patricia | Transit 2201 (800706) 1100 Wellington St updated Colum AR to reflect IPT
2014-10-06 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-10-06 |  | Patricia | Transit 1259 (800364) 2500 University, AB. This row was removed from the Scheduled Tab and placed in the Deleted sit tab. There is no staff at this location, there is only 1 telephone line associated with student banking at the University of Calgary.
2014-10-06 |  | Patricia | Transit 836 (800235) 383 Aspen Glen. Changed Branch Category from P&CB_INS to P&CB
2014-10-06 |  | Patricia | Transit 15345 (809019) 383 Aspen Glen. Inserted a row for INS with the same cutover date of December 08 as the other LOB.
2014-10-06 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-08 |  | Patricia | Transit 90865(803165) 1789 Lonsdale Ave, Vancouver BC. Cutover date added for December 08_2014 from a blank entry. This is a multi_site location. The date confirmation was provided by James, pre_audit and communications sent.
2014-10-08 |  | Patricia | Transit 16110 (802896) 3960 Quadra St. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. This location was closed and was never re_opened. The cutover date was December 08th. Email was sent previously to James for site replacement for December.
2014-10-08 |  | Patricia | Transit 10773 (802372) P&CB 10117 Jasper Ave. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. The cutover date was scheduled for December 10. The staff has moved to the GU_Campus network and are no longer part of the branch network. Email was sent previously to James for site replacement for December.
2014-10-08 |  | Patricia | Transit 3779 (801103) P&CB _PH&N. 10117 Jasper Ave. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. The cutover date was a blank entry. The staff has moved to the GU_Campus network and are no longer part of the branch network. Email was sent previously to James for site replacement for December.
2014-10-08 |  | Patricia | Transit 6389 (801610) added Audit delegate information
2014-10-08 |  | Patricia | Transit 1098 (800301) added Audit delegate information
2014-10-08 |  | Patricia | Transit 9047 (802065) B 3089 Wonderland Rd, London. Changed Branch Category from P&CB_INS to P&CB
2014-10-08 |  | Patricia | Transit 15288 (809020) 3089 Wonderland Rd, Unit A, London. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. Site replacement needed for January.
2014-10-08 |  | Patricia | Transit 477 (800131) 5051 Hwy7, Markham. Changed Branch Category from P&CB_INS to P&CB
2014-10-08 |  | Patricia | Transit 15272 (809021) 5051 Hwy7 Unit 101, Markham. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. Site replacement needed for January.
2014-10-08 |  | Patricia | Transit 316 (800093) 670 Kingston Rd, Unit 109, Pickering. Changed Branch Category from P&CB_INS to P&CB
2014-10-08 |  | Patricia | Transit 15257 (809022) 670 Kingston Rd, Unit 108 Pickering. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. Site replacement needed for November.
2014-10-08 |  | Patricia | Transit 2502 (800785) 1020 Ottawa St N, Kitchener. Changed Branch Category from P&CB_INS to P&CB
2014-10-08 |  | Patricia | Transit 15306 (809023) 1020 Ottawa St N, Unit B, Kitchener. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. Site replacement needed for December.
2014-10-08 |  | Patricia | Transit 1942 (800637) 1145 Barton St, E, Unit 1, Hamilton. Changed Branch Category from P&CB_INS to P&CB
2014-10-08 |  | Patricia | Transit 12992 (809024) 1145 Barton St, E, Unit 1, Hamilton. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. Site replacement needed for December.
2014-10-09 |  | June | Transits 3661, 523, 6532, 522 Changed Audit Date from Nov 11th to Nov 10th.
2014-10-09 |  | June | Transit 1297. changed audit date from Nov 11th to Nov 12th
2014-10-09 |  | June | T_65_35 and T_3 Communcation updates _
2014-10-10 |  | John | Ran script to update column AV, AX, AZ and BA
2014-10-14 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-10-15 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-15 |  | June W | T_65_35 and T_3 Communcation updates
2014-10-15 |  | Linda Hickey | New Dates Added to replace transits 3089,5051,670,1020,1145,15112,7473,6752,6012,59 Nov 10th:Transits 2064,3562, 6781 Nov 11th: Transits 361, 5062 Nov 12th: 2591, 1712, 90515, 17322 Nov 13th: Transist 236, 5101 Dec 1st: Transits 9409, 7212, 90326 Dec 3rd: Transit 41 Dec 4th: Transit 2242 Dec 9th: Transits 15286, 124 Dec 10th: Transit 4442 Jan 5th: Transits 2772, 744 Res Transit 7319 fr TBDto Feb 2, 2015 Res Transit 192 fr TBD to Nov 6th Res Transit 13152 fr TBD to Nov 6th Did not schedule dates for Transits 10756,13722,5101 as per Oct 16th call NON SIP sites DD changed to Dec 31, 2015
2014-10-16 |  | Patricia | Transit 15102 (809027) 365 High Tech Rd. Row inserted to add the INS portion with RBVP ID 809027.
2014-10-16 |  | Patricia | Transit 192 (800054) 3300 Hwy 7. Changed the Branch Category to show P&CB instead of P&CB_DS.
2014-10-16 |  | Patricia | Transit 519 (800152) 975 Paisley. Changed Branch category to P&CB instead of P&CB_INS
2014-10-16 |  | Patricia | Transit 15287 (809025) 975 Paisley. Row inserted to add the INS portion with RBVP ID 809025 with a cutover date of November 03
2014-10-16 |  | Patricia | Transit 742 (800211) Updated the postal code to L7N 3W2 from L7L 1S8
2014-10-16 |  | Linda | Added dates for Jan , Feb, March
2014-10-17 |  | Violeta | Fixed the formulas for column BR, BS
2014-10-17 |  | Patricia | Transit 15102 (809027) 365 High Tech Rd. INS**Reno Collision** With Ernie's approval this was removed from migration. The cutover date has been changed to TBD from Nov. 03. Site replacement needed.
2014-10-17 |  | Patricia | Transit 12991 (802444) 2 Bloor St. E. INS**Reno Collision**Cutover date was change to TDB from February 09, site replacement needed.
2014-10-17 |  | Patricia | Transit 15286 (809002) 2485 Appleby Line. INS**Reno Collision** Cutover date was change to TDB from December 09, site replacement needed.
2014-10-17 |  | Patricia | Transit 15405 (802815) 25 Peel Ctr INS**Reno Collision** Cutover date was change to TDB from a blank entry
2014-10-18 |  | David Lu | Fixed formulas for column AK (audit date). Fixed column AK to correctly follow T_10 plan for ON_QC sites, and T_40 for Western sites. Formulas now correctly accounts for Holidays
2014-10-20 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-20 |  | June White | Update T65_35 Actual Communcation Dates
2014-10-20 |  | Patricia | Transit 2291 (800720) 1500 Monette. Added comments to indicate that this location is a sub_branch associated with a retirement home.
2014-10-20 |  | Patricia | Transit 1124 (800315) 300 King George. Changed Branch Category to P&CB instead of P&CB_INS. NOTE: Cutover date was changed to November 19 instead of March 09. Communications were sent advising of migration on November 19, Audit date November 05.
2014-10-20 |  | Patricia | Transit 15442 (809033) 300 King George, U2 . Inserted a row for INS with the cutover date as TBD.
2014-10-21 |  | Linda | TR 1252 Cutover chg fr Nov 27 to TBD pending Site readiness TR 3620 Cutover chg fr Dec 1st to TBD pending Site readiness TR 1120 & 3757 Cutover chg fr Jan 5, 2015 to TBD Site readiness TR 3620 Cutover chg fr Jan 6, 2015 to TBD Site readiness TR 102 Cutover chg fr Jan 12, 2015 to TBD Site readiness TR 5000 Cutover chg fr Jan 12, 2015 to TBD Site readiness TR 7950 Cutover fr Mar 16 to TBD pending Site readiness TR 7497Cutover fr Mar 25 to TBD pending Site readiness TR 342 Cutover fr Jun 18 to TBD pending Site readiness TR 3520:Cutover fr Jan 22 to TBD pending Site readiness TR 482 Cutover fr Jan 28 to TBD pending Site readiness TR 2391: Cutover fr Jan 14 to TBD pending Site readiness TR 1827 : Cutover fr Jan 13 to TBD pending Site readiness TR 8380: Cutover chg fr Feb 9 to TBD pending site readiness TR 84: Cutover res from Jan 15 to Mar 16 pending site readiness
2014-10-21 |  | Linda | TR 1092: Updated master to reflect Cutover date Nov 4th
2014-10-21 |  | Linda | TR 982: Updated master to reflect Cutover date Nov 6th
2014-10-21 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-10-20 |  | Patricia | Transit 15442 (809033) 300 King George, U2 . INS. Updated cutover date to November 19 instead of TBD. Approval received from the Business, Bell has already received notification of this information.
2014-10-20 |  | Patricia | Transit 5855 (801529) P&CB 4370 Wellington St, Verdun. BCP Site: This location will not migrate. The entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. The cutover date was scheduled for November 05. Site replacement needed.
2014-10-20 |  | Patricia | Transit 522 (800154) 22 Colborne. Updated Branch Category to P&CB instead of P&CB_DS.
2014-10-20 |  | Patricia | Transit 90565 (809026) 22 Colborne. Row inserted to add DS with the cutover date of November 25, Training November 26. Communications sent.
2014-10-20 |  | Patricia | Transit 2080 (800667) 11855 224TH ST. Updated Branch Category to P&CB instead of P&CB_DS. NOTE: The SIP Availability date is March 01 2015, however the cutover date is January 13. Communications sent.
2014-10-20 |  | Patricia | Transit 90839 (809029) 11855 224TH ST. Row inserted to add DS with the cutover date of January 13, Training January 14. I have added the same SIP Availability date of March 01 2015. Bell to confirm.
2014-10-22 |  | Brenda | Update MPLS Migration Completed. TR#5633, 5072, 8842, 9409, 7842, 9857, 901, 1851, 1831, 2091. Add POE and MPLS Required NO, as opposed to blank.
2014-10-22 |  | June W. | Update T65_35 and T_3 Actual Communcation Dates
2014-10-23 |  | Linda | Changed Dec 31, 2015 to SIP N_A
2014-10-23 |  | Linda | Transit 2391, 4359, 322, 8040, 732 Replaced with 941, 1766, 1831, 873, 1106
2014-10-23 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-23 |  | Patricia H | Added AR number C00097122 for October 15 to October 29
2014-10-24 |  | John M. | Ran script to update column AV, AX, AZ and BA
2014-10-24 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-24 |  | Violeta | Updated Branch Category column for RBVPID 800809,801204,802366 from PH&N_Co_hab or PH&N_ to PH&N
2014-10-24 |  | Violeta | Updated Branch Category column for RBVPID 801512 from P&CB_DS to P&CB
2014-10-24 |  | June W. | Updated T_65_35 & T__3 Actual Communications
2014-10-27 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-10-28 |  | Brenda | Updated MPLS Completion Dates _ TR#1711, 2621, 543, 863, 7817, 8221
2014-10-28 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates. TR #9311.7841.1292.4627.402.7817.8567.2217.7472.2755.3631.8921.90313.10756.543.2442.2782.1711.13147.313.8099.392.6012.5802.2762.1827.3647.3757.4167.4427.4687.5137.5467.6147.6767.7497.
2014-10-29 |  | Linda | Moved the following sites from Jan to TBD MPLS upgrade req'd _ 800288_1042, 801397_5029, 800610_1819, 800018_85, 800115_400, 801248_4329, 800279_991, 800044_157, 800854_2869, 800356_1240, 803029_90301
2014-10-29 |  | Linda | Replacement sites for Jan 800580_1704,800406_1380, 800571_1672, 800255_888,800377_1291,800261_901, 800314_1123, 800254_886, 800385_1312, 800486_1532
2014-10-29 |  | Linda | Added additional sites to meet Jan quota of 60 branches _ 61 cutovers 800318_1144, 800672_2091,
2014-10-29 |  | Linda | To balance workload ; recommend moving 800212_744 from Jan 26th to Jan 20th
2014-10-29 |  | Linda | Update SIP Availability to : Nanaimo, Hanley, Atikokan
2014-10-29 |  | Linda | Moved the following sites from Feb to TBD MPLS upgrade req'd 801615_6422, 800179_610, 8000029_11y6, 802095_9242, 800359_1248, 801465_5452, 801087_3742, 800080_258, 800082_266, 800105_354, 801051_3532, 801652_6762
2014-10-29 |  | Linda | Per Donn'as request moved DS site 803040_90357 fr Feb 11 to Feb 12
2014-10-29 |  | Linda | 803088_90583 from Feb 18 to Feb 19
2014-10-29 |  | Linda | 803064_90514 from Feb 10 to Feb 12
2014-10-29 |  | Linda | Scheduled Jan _ Mar dates
2014-10-29 |  | Linda | Transit 6781 res from Nov 10 to Jan 12
2014-10-30 |  | Linda | Updated Training dates for DS sites 803106_90706, 800275_906&90808, 801598_900453, 801082_3722&90512
2014-10-31 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-03 |  | Linda | 802444_12991 res to Feb 9th to align with 803051_90428 & 800383_1307
2014-11-03 |  | Linda | Updated Rollout column
2014-11-03 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-11-04 |  | Patricia H | Transit 3749 (801096) 10107 Jasper Ave. The site no longer qualifies for RBVP as it is now a CAMPUS_GU location. Donna had requested a site replacement. The cutover date populated was February 04 2015. I have moved this entry from the Schedule tab to the Deleted Sites tab.
2014-11-04 |  | Patricia H | Transit 372 (800109) P&CB. 303 Moodie. Cutover date changed to TBD from November 04. The migration was rescheduled due to MPLS Network upgraded. The business was notified of the reschedule.
2014-11-04 |  | Patricia H | Transit 2014 (800651) 515 Westmorland Rd. Changed Branch Category from P&CB_INS to P&CB.
2014-11-04 |  | Patricia H | Transit 15420 (809030) 515 Westmorland Rd. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed.
2014-11-04 |  | Patricia H | Transit 6832 (801671) 2900 Warden Ave. Changed Branch Category from P&CB_INS to P&CB.
2014-11-04 |  | Patricia H | Transit 11338 (809031) 2900 Warden Ave. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed.
2014-11-04 |  | Patricia H | Transit 5942 (801548) 5171 Sandhurst Circle. Changed Branch Category from P&CB_INS to P&CB.
2014-11-04 |  | Patricia H | Transit 12990 (809032) 5171 Sandhurst Circle. Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed.
2014-11-04 |  | Patricia H | Added AR number CR 00101384 for October 30 to November 12 and CR 00101399 for November 13 to November 26.
2014-11-05 |  | June W. | updated the T_65_35 and T_3 Actual Communications
2014-11-05 |  | June W. | TR 2039 _ Added IPT = 1 to column AR
2014-11-05 |  | June W. | TR 15347 _ Inserted Line 235 _ RBVP ID 809034 _ INS _ Fanshawe, London ON
2014-11-06 |  | Linda H | Removed data from Cutover cell
2014-11-06 |  | Linda H | Removed 1_JAN_00 from Training column
2014-11-06 |  | Linda H | Changed Audit date from 15_ Jan_ 01 to 30_Dec_14 803060 _ 90508
2014-11-06 |  | Linda H | Column BE duplicate no longer required
2014-11-07 |  | John | Ran script to update column AV, AX, AZ and BA
2014-11-10 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-11 |  | Linda | MPLS upgrade required per Bell Network team. RBC to confirm Sites with Cutover dates : 800682 2122, 800955 3282 , 800703 2182, 802898 16113, 800062 222, 801422 5137 Sites with no cutover dates : 800813 2702, 800217 767, 801203 4183, 801443 5283, 801646 6718, 801843 7862, 803094 90608, 800046 160, 800870 2940, 801217 4262, 803120 90736, 803147 90829
2014-11-11 |  | Linda | Co_ordinate Cutover with 801720_7233 _ 801342 4682
2014-11-11 |  | Linda | Res Site803064 90514 fr Feb 12 to 5 overbooked DS sites in ON
2014-11-11 |  | Linda | Due to distance, requesting these two transits be scheduled on Tues & TH completed T_2 & T_ activities on same day 801949 8291 schedule for 13_Jan_15 800061 221 res from 5_Jan_15 to 15_Jan_15
2014-11-13 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-17 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-17 |  | Serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates. ADDED sites to be re_cabled…6422.372.422.
2014-11-18 |  | Linda | RBC request to schedule 803066_90522 to Jan 8 2105 _ 803075_ 90541 to Jan 15, 2015
2014-11-18 |  | Linda | RBC Request to schedule 800053_189 and 90453 to Dec 4th * 7 DS employees moving from Queen to Wicksteed
2014-11-18 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-19 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-20 |  | Linda | Elaine req'g earlier date for 801156 _3922 res from Mar 26 to Jan 12 _ Pending RBC approval
2014-11-20 |  | Linda | Added cutover dates for 803066_ 90522 Jan 8, 2015 and 803075_90541 Jan 15, 2015 (Per Donna's request )
2014-11-20 |  | Linda | Added cutover date of Dec 4th for 800053 _90453 * DS site moving from Queen to Wicksteed
2014-11-20 |  | Linda | Nov 13: TR 3182 cutover date TBD fr Mar 26 due to Cabling requirements
2014-11-20 |  | Linda | Nov 13: TR 5855 cutover date fr Mar 19 to Jun 11 2015 due to Cabling requirements
2014-11-20 |  | Linda | Nov 19: TR 4175 cutover date fr Apr 01 to Apr 20 due to Cabling requirements
2014-11-20 |  | Linda | On Nov 13 Elaine confirmed 802361 TR 10761 is NOT migrating on Dec 04, 2014. Updated cutover date and comments
2014-11-21 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-21 |  | Linda | Placed on hold pending TELCO order confirmation _ RBC providing NDD 803132 90805 _ 801324 4540 _ 801430_5179 _ 801662 6807_ 800721_2299 _ 801943 8259 _ 801902 8030_ 809015 3587
2014-11-21 |  | Linda | Removed cutover date and updated comments for 800798_2591 on hold renovations
2014-11-21 |  | Linda | Nov 21: Donna advised site will be ready Nov 28th _ Linda to confirm resources for T_@ and T_0 first _ second week of Dec Nov 19: 800851_8523 on hold pending cabling _ switch upgrade
2014-11-23 |  | Patricia H | Transit 2810 (800834) 7157 120TH ST, BC. Removed cutover date from Nov. 25th, new due date TBD pending Telco confirmation.
2014-11-23 |  | Patricia H | Transit 1836 (800618) updated the City from Quebec to La Prairie
2014-11-23 |  | Patricia H | Added AR number C00108238 for November 27 to December 10
2014-11-23 |  | Patricia H | Added AR number C00108251 for December 11 to 17. However no other cutover dates are populated for the remainder of December after December 11th.
2014-11-23 |  | Patricia H | Transit 90721 (803113) Added IP to column AR
2014-11-23 |  | Patricia H | Transit 6462 (801617) Changed address from 4022 Sheppard Ave. E to 3807 Sheppard Ave E. M1T 3L5. Added IP to column AR.
2014-11-23 |  | Patricia H | Transit 8000 (801894) Inserted comment to cutover date; the migration for this location should be coordinated with Transit 8030 and 3587 at 707 Fort as the buildings are connected.
2014-11-23 | Pat A | Patricia H | Transit 7311 (801727) Added Tech Name Eric Charland 450_755_7735
2014-11-23 | Pat A | Patricia H | Transit 8811 (802039) Added Tech Name Daniel Champagne 819_371_ 8475
2014-11-23 | Pat A | Patricia H | Transit 2431 (800757) Added Tech Name MOHAMMED KANSARI 418_928_1676
2014-11-23 | Pat A | Patricia H | Transit 775 (800220) Added Tech Name MOHAMMED KANSARI 418_928_1676
2014-11-24 |  | Linda | 803165 Transit 90865 SIP change from Mar 2015 to Yes
2014-11-24 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-24 |  | Violeta G. | Updated columns BY to CE(not used columns) with Branch manager name,phone number , MCC name, phone number, RMO and MMO name and Region
2014-11-24 |  | Violeta G. | Aligned columns with centrex counts by location, DM to DO, added flag for IP _not in use yet need to consolidate counts by similar entries in location , updated legend colors
2014-11-25 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-25 |  | Brenda | Updated MPLS Upgrade Date for TR#84,116, 126, 189, 232, 258, 402, 440,597, 617, 1141, 1216, 1256, 1822, 2189, 2562, 3111, 3362, 3382, 3622, 3672, 3692, 4104, 4910, 5439, 5522, 6621, 155
2014-11-25 |  | Brenda | Updated MPLS Upgrade Date & POE Completion Date for TR#1662, 2852, 2972
2014-11-25 |  | Brenda | Changed MPLS Required to Yes & update MPLS Order Submisson Date for TR#2122, 3282, 2182, 222, 2702, 4183, 5283,7862, 4262, 160, 2940
2014-11-25 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-26 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications for month of November
2014-11-25 |  | Violeta G. | Updated columns BV_BX with DS Branch Manager, DS Branch Admin and DS BTS
2014-11-26 |  | Linda | 800374 1280 Family day res from Feb 9 to Feb 10 800167 563 Family Day Pending Bell Resource 801973 8500 Mar 11 to TBD Replacement site 801508_5722 802898 16113 Mar 16 to TBD Replacement site800029_116 801640 6640 Mar 17 to TBD Replacement site 800080_258 800371 1278 Mar 19 to TBD Replacement site 801375_1278 800954 3280 Mar 23 to TBD Replacement site 801547_5922 800738 2370 Res Mar 24 to TBD Replacement site 800361_1256 801361 4800 Reschedule Mar 25 to TBD Replacement site TBD 801582 6160 Mar 26 to TBD Replacement site TBD 801546 5920 31 Mar 31 to TBD Replacement site TBD 803082 90561 Family Day Res from Feb 16 to Feb 18 801505 7323 Family Day Res from Feb 16 Feb 18 800317 1141 Feb 16 Added Site QC 801638 6621 Feb 16 Added Site QC 801264 4392 Family Day Res from Feb 16 to Feb 2 801216 4252 Family Day Res from Feb 16 to Feb 3 801432 5192 Family Day Res from Feb 16 to Feb 12 8011391 3882 Family Day Res from Feb 16 to Feb 11 800183 622 Family Day Res from Feb 16 to Feb 11
2014-11-26 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 01371, 02400, 03392, 01672, 01532, 00888, 00458
2014-11-26 |  | Violeta G. | Updated counts in columns DM_DO where complete_flag='done'
2014-11-26 |  | Patricia H | Updated column A from Phase 2 Pilot to Roll out
2014-11-27 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 90326 00912 03869 01102 08319 06857 09409 00662 07212 01942 07921 01704 02755 06781 08291 02071
2014-11-27 |  | Bell (Pat Armstrong) | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-11-27 |  | Linda | 800851_8523 Res Cutover from Nov 20 to Dec 10 _ pending RBC approval
2014-11-27 |  | Linda | 800785_2502 Res from Dec 8 to Dec 11 ( Set Dpeloyment Dec 10) _ RBC request
2014-11-27 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 5400 128 1236 392 775 90581 4356 1312 541
2014-11-27 | Pat A | Patricia H | Transit 5 (800002) Added technician's information, Column AN
2014-11-27 |  | Patricia H | Transit 458 (800126) Updated Branch category to P&CB instead of P&CB_INS
2014-11-27 |  | Patricia H | Transit 15308_11214 (809040) 1520 Major Mackenzie Dr. Row inserted to represent INS with cutover date of January 12. Branch Audit Date to be populated.
2014-11-28 |  | Linda | Updated Dec Audit dates
2014-11-28 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 1341 2164 720 1108 143 86 3221 41 1012 744 4356
2014-12-01 |  | Linda | 802442 12113 Removed cutover _ Branch closing Replacement Site 800611_1822
2014-12-01 |  | Linda | 800682 _ 2122 June confirmed MPLS is req'd Cutover date chged from Jan 15 to TBD Replacement site 800878_2972
2014-12-01 |  | Linda | 802361 TR 10761 Res to Feb 9 with other 4 LOBS
2014-12-01 |  | Linda | Added 801071_3672 / 801637_6612 / 801648_6722 to meet March quota
2014-12-01 |  | Linda | 800109 _ 372 TBD Cabling required Co_ordinate with 803060 _ 90508
2014-12-01 |  | Linda | 801943_ TR 8259 original install date of Nov 20 – requested due date ( Red Deer Alberta) _ January 6 16:30
2014-12-01 |  | Linda | 801902 _ 8030& 809015_3587 original install date of Nov 20 – pending due date
2014-12-01 |  | Linda | 801324 _ 4540 original install date of Nov 25 – Dec 10 19:30
2014-12-01 |  | Linda | 800834 2810 original install date of Nov 25 – requested due date January 22 19:30
2014-12-01 |  | Linda | 803132_ 90805 original install date of Nov 25 – requested due date unknown pending due date
2014-12-01 |  | Linda | 800812_2699 original install date of Nov 27 – requested due date (AB) January 14 16:30
2014-12-01 |  | Linda | 803135_ 90808 Res from Nov 27 to Dec 11
2014-12-01 |  | Linda | 800362 _ 1259 original install date of Dec 2nd – requested due date January 21 20:30
2014-12-01 |  | Linda | 801430 _ 5179 original date of November 17 requested due date of Dec 10 20h30
2014-12-01 |  | Linda | 803165_ 90865 original install date of December 8 requested due date January 26 15:30
2014-12-01 |  | Linda | 800702 _ 2169 Village Square original install date of December 8 – requested due date January 28 20h30
2014-12-01 |  | Linda | 801662_ 6807 Calgary original due date Nov 17 (pending new due date)
2014-12-01 |  | Linda | 800721_ 2299 Winnipeg Manitoba original date of Nov 18 – pending new due date)
2014-12-01 |  | serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates. ADDED sites to be re-cabled , TR 3002, 2462, 7121. Date changes on TR 122, 3062, 3042.
2014-12-01 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-02 |  | Marcus | Updated Column BQ to "All Transits" - Included transits for Dec 2014 - Mar 2015.
2014-12-02 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 90717 10180 5 7120 12791460 182 1123 1291 90453 189 4786 3120 5992 2242 3922
2014-12-02 |  | Brenda | Updated Column AE - Switch POE - TR#3692, 6887
2014-12-02 |  | Brenda | Updated Column AF - MPLS Upgrade Required to be Yes - TR#5802, 4002, 7692,5302
2014-12-02 |  | Brenda | Updated Column AF - MPLS Completion Dates - TR#2124, 4702 ,4962, 5261, 5272, 5382, 5582, 5882, 6002, 6172,6422, 6662, 7378, 7782, 7902, 8122, 8561, 8971, 9242, 9837, 15286, 7882,1682,3742
|  | Marcus | Updated T35/65 Communication 90500
2014-12-03 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-02 |  | David | Updated Column AL for site: 801902 + 809015 from TBD to 1/21/2015, 803132 from TBD to 1/19/2015, 800702 from 1/28/2015 to 12/8/2014, 801662 from TBD to 1/13/2015, 800721 from TBD to 1/26/2015.
2014-12-02 |  | David | Updated Column AK for audit date reschedules for the following sites: 800580/1704 from 12/19 to 12/2, 801156/3922 from 12/24 to 12/3, 803075/90541 from 12/31 to 12/9, 800255/888 from 12/31 to 12/10, 800989/3392 from 12/30 to 12/11, 800878/2972 from 12/31 to 12/15, 809040/15308/11214 from 12/22 to 12/16, and 803066/90522 from 12/22 to 12/17
2014-12-03 |  | Patricia H | Transit 90814 (809041) 2950 Glen Drive, Coquitlam BC. Added a row for DS representation at this address as some of the users from 960 Quayside will move here in February. Technology, audit date and training date etc. to be populated.
2014-12-03 |  | Patricia H | Transit 12113 (802442) 1220 Lebourgneuf Street, Quebec City, Quebec. Removed from the Scheduled tab and placed for reference in the Deleted sites tab. This location is closing. Linda H already noted that site replacement needed.
2014-12-04 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 90500 1457 1659 1200 8160 7310 5220 226 1307 117 4409 4000 2169 1534 836 1891 90637 2972 886
2014-12-04 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-04 |  | Patricia H | Transit 90814 (809042) 2950 Glen Drive, Coquitlam BC. Changed RBVP ID from 809041 to 809042 requested by Violeta.
2014-12-04 |  | Patricia H | Transit 6892 (801678) Updated Branch category to P&CB instead of P&CB/INS
2014-12-04 |  | Patricia H | Transit 15316 (809041) 5222 130th Ave SE. Row inserted to represent INS with cutover date of February 09. Branch Audit Date to be populated.
2014-12-04 |  | Patricia H | Transit 960 (800275) 9296 Main St, Chilliwack. Changed branch category to P&CB from Co-hab
2014-12-04 |  | Patricia H | Transit 90808 (809039) 9296 Main St, Chilliwack. Row inserted to represent DS with cutover date of February 05. Branch Audit Date, training etc to be populated.
2014-12-04 |  | Patricia H | Transit 314 (800092) 222 Monetee Masson. Updated Branch category to P&CB instead of P&CB/INS
2014-12-04 |  | Patricia H | Transit 15266 (809037) 222 Monetee Masson U7. Row inserted to represent INS with cutover date of November 28, updated for record purposes
2014-12-05 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 447 90411 4695 702 641 1901 8249 5790 2949 124 354 56 90500 1457 1659 1200 8160 7310 5220 447 226 901 1307 1177 4409
2014-12-05 |  | Marcus | Updated Column BQ to "All Transits" - Included transits for April - May 2015
2014-12-05 |  | John | Ran script to update column AV, AX, AZ and BA
2014-12-05 |  | David | Updated Column AL for site 800785 cutover date from 12/10 to 12/11 due to conflict with xmas party (via Patricia H)
2014-12-05 |  | David | Updated Column AL for site 5179 cutover date from 12/10 to 1/12 due to TELUS rejections
2014-12-05 |  | David | Updated Column AL for site 4540 cutover date from 12/10 to 12/11 due to TELUS unable to do cutovers past 8pm - changed to next morning cutover at 6:30am.
2014-12-05 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 238 257 1951 4442 8523 5680 8049
2014-12-05 |  | Marcus | Updated Column BQ "All Transits" - Included transits for May - Sept 2015
2014-12-08 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-08 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 8400 4508 5030 320 1106 1144 7191 2091 8067 4540 2502 6389 4990 1988 4541
2014-12-09 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-09 |  | serena | Updated dates and number of phones in Standalone column. Updated re_cabling dates.
2014-12-10 |  | Linda | 801402_5050 Cutover date TBD from Apr 1 - Site under construction
2014-12-10 |  | Linda | Added Proposed dates for Feb 16-19 ; Transits will be listed on change log once the Propsed dates are approved
2014-12-10 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 5462 9311 4392 2162 7822 2319 1560 2319 320 2244 3462 8440 543
2014-12-10 |  | Marcus | Added NEW Insurance transits 15289 15230 16103/15309 15274/11269
2014-12-10 |  | Linda | 803030_90311 Placed on hold pending Bandwidth upgrade
2014-12-10 |  | Linda | 803135_ 90808 Res from Dec 11 to TBD - site under construction
2014-12-10 |  | Linda | 800050_180 Cutover res fr Feb 5 to TBD pending MPLS upgrade
2014-12-11 |  | Patricia H | Transit 176 (800204) 7133 -7031 120th St, Delta BC. Removed from the schedule tab and placed in the Deleted Sites tab. The branch has closed, Donna has already requested site replacement.
2014-12-11 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-11 |  | Marcus | Added NEW PB Transit 10768
2014-12-11 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 10768
`11-Dec |  | Marcus | Updated Columns DM & DN ( Centrex & VoIp counts) from Dec to Mid-Jan.
2014-12-11 |  | Marcus | Inserted NEW columns DO (Total Counts), DP (Centrex or IP)
2014-12-12 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 4520 2165 2157 7287 1599 8052 2542 2157 4252 6221 3592
2014-12-12 |  | Marcus | Updated Columns DM-DR
2014-12-12 |  | Marcus | Updates Column CD (MMO Name - Feb,March & April - Removed Heather Baxter and added Odell Sinclair)
2014-12-12 |  | Marcus | Added NEW Insurance Transits 16107/15272 15123/15275
2014-12-12 |  | Marcus | Updated Columns DM-DR
2014-12-13 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 4366 5282 2552
2014-12-13 |  | Marcus | Updated Columns DM-DR with Centrex & VoIP counts
2014-12-14 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 16258 1989 7619 2752 2931 3282 1282 3102
2014-12-14 |  | Marcus | Added NEW PB Transit 10758
2014-12-15 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 4682 7233 9037 3942 3902 3382 3582 7323 5952
2014-12-15 |  | Marcus | Updated Columns DM-DR
2014-12-16 |  | Marcus | Updated Columns BT_BU with T3 & T65_35 Actual Communications _ Transits 90522 2072 1766 4461 5342
2014-12-16 |  | Marcus | Updated Columns DM-DR up to July 2015
2014-12-16 |  | Brenda | Updated Column AG - MPLS Completed - TR#982, 6352, 7741, 7882, 1682,3639,3732
2014-12-16 |  | Brenda | Updated Column AH - MPLS Order Sent - TR#2920,4240,2560,1440, 1090, 2240, 2890,4080, 7840, 2800, 5802, 4002, 5302, 7692
2014-12-16 |  | Brenda | Updated Column AE - Switch POE - TR#3732
2014-12-16 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 4312. 5522. 322.
2014-12-17 |  | Patricia H | Added AR number CR 00115494 for January 5th to 7th.
2014-12-17 |  | Patricia H | Added AR number CR 00115510 for January 8th to 21st.
2014-12-17 |  | Patricia H | AR number CR 00112190 created for T2 set placements for December 31st to January 02nd. This is not reflected on the schedule as no migrations are occuring during this time period.
2014-12-17 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-17 |  | Linda | Req from Laura to change Audit date from Jan 5 to Dec 18th on the following LOB ,809045_15230,809046_15289, TR15419 is not on the master RBC to add
2014-12-17 |  | Linda | 801949 8291 scheduled for 13_Jan_15 is placed on hold - SIP not avialable
2014-12-17 |  | Linda | 809045 15230/12114 Chg cutover from Jan 19 2019 to Jan 19 2015
2014-12-18 |  | Marcus | Updated Columns BU with T65 Actual Communications _ Transits 1360 4800 3452 3232 6022 6032 3882 5633 16481 6800 7159 90514 5072 1141 6621 1280 1040 1486
2014-12-18 |  | Marcus | Updated Column BQ "ALL Transits" 1622 1922 90571 15289/13177 15230/12114 16103/15309 886 90805 10758 90808 15316
2014-12-18 |  | Marcus | Confirmed cutover dates for Transits 1822 2972 90805 7233 5952 3902 4842 3382 4461 2552 5282 4366 3942 4392 4252 3282 90514 5072 1141
2014-12-18 |  | Marcus | Confirmed audit dates for Transits 2972 9037
2014-12-18 |  | Marcus | Created NEW column DS "Comparision of Total Count Vs Total Branch Centrex"
2014-12-18 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-18 |  | Marcus | Confirmed cutover dates for Transits 2299 2810 5179 6621
2014-12-18 |  | Marcus | Updated Colmun BQ "ALL Transits 2299
2014-12-18 |  | Marcus | Updated Columns DM-DR
2014-12-18 |  | Marcus | Updated Columns BU with T65_AC TR 7360 2782 5362 2978 3882 1262 4222 6672 1322 3832
2014-12-18 |  | Marcus | Confirmed cutover dates for Transits 3882 622 4180
2014-12-19 |  | Marcus | Updated Columns DM-DR
2014-12-22 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-22 |  | Marcus | Updated Columns BU with T65_AC TR 2772 9047 2071 1831 2072 1766 1504 4219 4529 2440 1894 5192 90337 3981
2014-12-22 |  | Marcus | Removed Transit 5302 RBVP ID 801449. Transit Record in Deleted Sites Tab.
2014-12-22 |  | Marcus | Confirmed cutover dates for Transits 5192 1280
2014-12-23 |  | Linda | 801662_6807 Cutover res from Jan 13 to Jan 20th (RBC req)
2014-12-23 |  | Linda | 800903 _ 3051 res from April 7 to April 14
2014-12-28 |  | Marcus | Fixed Row heights & column widths
2014-12-28 |  | Marcus | Updated Columns BU with T65_AC TR 501 1224 10761 5142 6702
2014-12-29 |  | Marcus | Updated Columns BU with T65_AC TR 1442 90541 221 4842 1380 1822 90571 8022 15308 16103/15309 3942 1002 90453 189 90808 5120 960 5229 5222 80 5839 319 1461 6840 1934 1436
2014-12-29 |  | Marcus | Confirmed cutover dates for Transits 8022
2014-12-29 |  | Marcus | Updated AR for TR 1822 10768 (CR 00115510), TR 15230/12114 (CR 00115510)
2014-12-29 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-29 |  | Marcus | Updated Columns BU TR 15112 (Southport), 15289/13177 (Hazeldean)
2014-12-29 |  | Marcus | Updated Columns DM-DR with Centrex & VoIP counts
2014-12-29 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2014-12-30 |  | Linda | 801359_4786 placed on hold pending recabling
2014-12-30 |  | Linda | 801205_4202 Updated cutover date from Mar 17 to Jan 22
2014-12-30 |  | Marcus | Updated Columns BT & BU TR 2419 4530 563 5520 5137 1312 501 1102 1704 1297 490
2014-12-30 |  | Marcus | Added NEW TR 15419/13241
2014-12-31 |  | Marcus | Updated Column BQ "All Transits"
2014-12-31 |  | Marcus | Updated Columns BU TR 1753
2015-01-02 |  | Marcus | Updated Column BQ "All Transits"
2015-01-02 |  | Marcus | Updated Columns BU TR 1920 4202
2015-01-05 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-05 |  | serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates.
2015-01-05 |  | Marcus | Updated Centrix count for 100 King St. TR 10768 90571
2015-01-05 |  | Marcus | Updated Columns BT TR 1442 1380 1224 1012 912 90522 90500 16103/15309 15289/13177 15316/13218
2015-01-05 |  | Marcus | Updated Columns BT TR 2772 9047 2071 2072 1766 5600
2015-01-06 |  | Marcus | Updated Columns BT TR 3520 5399 3610 7437 4160 7680 3160 5489 8110 782
2015-01-06 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-07 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-07 |  | Robert Rehders | Added Column DT and DU containing Trunk group information current as of January 7th
2015-01-08 |  | Marcus | Updated Columns BT TR 90571 10768 3922 458 5179 6781 1822 90561
2015-01-08 |  | Marcus | Confirmed cutover dates TR 3840 90561
2015-01-08 |  | Marcus | Added NEW TR PH&N 11831 INS TR 15250 15400 15303 15304 15268 15407 15267 15273
2015-01-08 |  | Marcus | Site Address Correction TR 15274 / Updates to COL K "Site Names" & Col V "Postal Codes"
2015-01-08 |  | Marcus | Updated LOB RBVP ID 802361 801645 802336
2015-01-08 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-08 |  | Marcus | Added TWO PB TR 10763 14533
2015-01-08 |  | Marcus | Updated Columns BT TR 15400
2015-01-08 |  | Marcus | Updated T65/T3 Comms TR PH&N 11831 INS TR 15250 15400 15303 15304 15268 15407 15267 15273
2015-01-09 |  | Linda | Updated column BF to reflect Bell West not TELUS 803134_90806 & 801493_5600
2015-01-09 |  | John | Ran script to update column AV, AX, AZ and BA
2015-01-09 |  | Marcus | Updated Column BT TR 2080 200 2699 3392 1672 1532 90839
2015-01-09 |  | Marcus | Updated Column BU TR 229 2018 3840 90715 14533 90313 10763
2015-01-09 |  | Marcus | Confirmed cutover date TR 90715
2015-01-09 |  | Marcus | Added NEW DS TR 90865
2015-01-09 |  | Marcus | Add NEW RBVP IDs TR 11271 15302 11831 15250 15400 15303 15304 15268 15407 15267 15273 10763 14533
2015-01-12 |  | Linda | Rescheduled 61 Audit dates due to RRSP freeze (highlighted purple - Dates are tentative pending Bell's final review and resource availablity draft to RBC will be sent Jan 13
2015-01-12 |  | Marcus | Updated Column BT & BU TR 11831 15308 4509 15419/13241
2015-01-12 |  | Marcus | Branch Category correction TR 10756 to PB, TR 16481 to PH&N
2015-01-12 |  | Marcus | Added NEW PB TR 10754 10755 10757 10759 10760 10762 10764 10765 10769 10772 10773 10774 10775 10776 10777 13917
2015-01-12 |  | Marcus | Updated Column BQ "All Transits" for PB TRs
2015-01-12 |  | Marcus | Updated Column BT& BU TR 10758 2972 221
2015-01-12 |  | Marcus | Added NEW PB TR 14143 14483 14903 15670 16482 17306 17739 809
2015-01-12 |  | Marcus | CC config TR 1822 AS 14 to 21, BB 3M to 5M, 90571 (RBVP ID: 803084) AS 37 to 25, BB 10M to 20M
2015-01-12 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-13 |  | Marcus | Updated Column BT & BU TR 90825 480 3180 324 1095 1632 2301 2602 1061
2015-01-13 |  | Marcus | Confirmed cutover date & audit TR 90825 480 3180 324 1095 1632 2301 2602 1061
2015-01-13 |  | Marcus | Updated total count TR 90839
2015-01-13 |  | Marcus | Flagged GU Locations TR 10755 15670
2015-01-13 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-15 |  | Marcus | Updated Column BT & BU TR 7233 4682 4356 9037 5952 541 7817 90805 1952 1271 6612 4362 922 616 1962 8580 4629
2015-01-15 |  | Marcus | Confirmed audit & cutover dates TR 7817 3672 1952 6612 4362 922 616 1962 8580 4629
2015-01-15 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-16 |  | Marcus | Updated Column BT & BU TR 744 3902 3582 4842 3382 5072 6807 90806
2015-01-16 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-16 |  | David | added in additional holidays that affects audit dates
2015-01-16 |  | Marcus | Updated Column BT & BU TR 8030 1141 6621 2182 10777 182 1123 1291 2147 15230/12114 16103/15309
2015-01-16 |  | Marcus | Confirmed cutover date & audit TR 8030
2015-01-18 |  | Linda | 800325_1177 Res from Mar 9th to TBD - due to SIP availablity - New ETA March 27th
2015-01-18 |  | Linda | Updated SIP to YES : KITIMAT, CRESTON, DRUMHELLER, SMITHERS, REVELSTOKE, PARKSVILLE, BURNS LAKE, Wetaskiwin, STETTLER, DRAYTON VALLEY, BONNYVILLE, PONOKA, LADYSMITH, SECHELT, SPARWOOD BRANCH, FAIRVIEW BRANCH, MERRITT , VANDERHOOF, OLIVER , FORT ST JAMES, WHITECOURT, PINCHER CREEK, SYLVAN LAKE, QUALICUM BEACH, MISSION, TABER, LACOMBE, Beaumount, Neepawa, Thompson The Pas, Stonewall, Dauphin, Cold Lake, Surry, Kelowna , MILL BAY, Powell RIver, Victori, GERALDTON
2015-01-18 |  | Linda | 800594_ 1760 Chagned cutover date from Jan 13 to Jan 28
2015-01-18 |  | Linda | 809052_10758 Placed on hold due to move - Cutover with TR 2591
2015-01-18 |  | Linda | 801505_7323 move back to Feb 18th to cutover with other LOB
2015-01-18 |  | Linda | 802928_16481 … RBC confirm if transit was changed to 2561
2015-01-18 |  | Linda | 800119_422 Apr 8 to TBD pending site readiness
2015-01-18 |  | Linda | 800880_2978 TBD from Mar 25 - SIP N/A
2015-01-19 |  | Marcus | Updated Column BU TR 1222 3082 1362 4002 812 5722 2941 3578 1259 15274/11269 15289/13177
2015-01-19 |  | Marcus | Confirmed cutover date & audit TR 5722
2015-01-19 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 482.6342.4942.1334.3012.4513.4786.2242.
2015-01-19 |  | Marcus | Removed GU locations TR 10760 809 17739 10772 15670 10774 10755 7310 4506
2015-01-20 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-20 |  | Marcus | Updated Column BT & BU TR 5130 834 90731 9219 2810 4461 90500 4882 7582 2621 4202 1131 2244 886
2015-01-20 |  | Marcus | Confirmed cutover dates TR 5130 834 9219
2015-01-20 |  | Marcus | TR 90736 Updated Col AP to BS
2015-01-21 |  | Linda | 809058_14500 Added cutover date Mar 5th to align with cutover date for P&CB LOB
2015-01-21 |  | Linda | Jan 21: Adding Cutover date of March 11 - was removed from schedule Require data populated by Friday Jan 23
2015-01-21 |  | Linda | Updated Audit dates res from Feb 16 - Mar 5
2015-01-21 |  | Marcus | Updated Column BT & BU TR 116 724 1742 6722 90865 901 2299 8399 477 226 5949 4817 683 4662
2015-01-21 |  | Marcus | Updated RBVP 809053 change of address
2015-01-21 |  | Marcus | DNS status for cutover date for TR 15303 15304 15268 15407 15267 15273 10754 10757 10759 10762 10764 10765 10773 10774 10775 10776 10777 13917 14143 14483 14903 16482 17306
2015-01-21 |  | Marcus | Updated Branch Category TR 2419 to Cash Services, postal code correction
2015-01-21 |  | Marcus | Updated TR 90341 address
2015-01-22 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-22 |  | Marcus | Updated Column BT & BU TR 641 873 8577 8022 702 90411
2015-01-22 |  | Marcus | Removed TR 90468 duplicate
2015-01-23 |  | John | Ran script to update column AV, AX, AZ and BA
2015-01-23 |  | Marcus | Updated Column BT & BU TR 3901 1552 7472 4701 1493 258 842 913 2442 84 90855 750 1144 2552 5342 1549 7191 1260 2091
2015-01-23 |  | Marcus | Added and Updated Column DV (Total count greater than total branch centres) - details in header comments (DV1)
2015-01-23 |  | Marcus | Added Column DW - Original Concurrent Calls, , Added Column DY - Total Bandwidth
2015-01-23 |  | Marcus | Added and Updated Column DX - CC Flag
2015-01-23 |  | Marcus | Updated Column AS (Concurrent Calls) for Feb - July based on circuit sizing
2015-01-24 |  | Marcus | Updated Columns V, DM-DR, DV
2015-01-26 |  | Linda | 803041_90341 scheduled for Feb 19th pending RBC approval
2015-01-26 |  | Linda | 803135_ 90808 Res from TBD to Feb 18 pending RBC approval
2015-01-26 |  | Linda | 802898_16113 Res fr TBD to April 1 pending RBC approval
2015-01-26 |  | Marcus | Update Col DY (Total Bandwidth) Feb - Aug
2015-01-26 |  | Marcus | Added Col DZ (BW Flag) and updated
2015-01-26 |  | Marcus | Removed 803014_63322 (invalid unit)
2015-01-26 |  | Marcus | Updated Col AS (CC) & Col DZ (Total BW TR) 16113 2419 15419/13241 4817
2015-01-26 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 2093. 7782. 5112. 8661.2242.
2015-01-26 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW TR) TR 6032 90416 10765 15112 8802 6032 1724 382 8000 2301 4682 7233 3462 3587 8030 1493 1492 6800
2015-01-26 |  | Marcus | Added NEW INS TR 15327/13211
2015-01-26 |  | Marcus | Updated Col BT TR 6402 1458 5282 4366 3942 3462 629
2015-01-26 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-26 |  | Linda | 803041_90341 scheduled for Feb 18th pending site readiness
2015-01-26 |  | Marcus | Updated Col BU TR 2762 3482 4910 2642 1763 5429 90314 2409
2015-01-26 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 15123/15275
2015-01-26 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 10763 90808 10766 6202 683 14326 10756 582 3777 563 4002 90551 15419/13241
2015-01-27 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-29 |  | Marcus | Removed empty rows 895-911
2015-01-29 |  | Marcus | Updated Col BU & BT TR 2561 90706 8370 7319 2900 5462 1834 6832 4392 5922 2162 4342 7822 2642
2015-01-29 |  | Marcus | Updated TR 2561 category to P&CB, TR 10761 category to PN&H
2015-01-29 |  | Marcus | Added TR PB 91 , 14259
2015-01-29 |  | Marcus | Sequenced 800724, 809058, 802357 ;
2015-01-29 |  | Marcus | Updated new address for TR 91 & 107658, current address in the comments
2015-01-29 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-01-30 |  | Marcus | Updated Col BU & BT TR 6221 2157 4252 7269 5500 8052 3592 8000
2015-01-30 |  | Marcus | Updated "All Transits" Column
2015-01-30 |  | Marcus | Updated TR 622 site address - see comments
2015-01-30 |  | Marcus | TR correction 1493 to 4701
2015-01-30 |  | Marcus | Update Col BP Activity Records Jan 22 to 26 C00120123; Jan 27 to Feb 18 C00120126
2015-01-30 |  | Marcus | Added PB 809090_809
2015-01-30 |  | Marcus | Sequenced 800207_563 & 809071_1504
2015-02-02 |  | Linda | 802774_15112_13268_11263 Res cutover from Feb 3 t oFeb 24th due to additional scope of work for TR 13268 ( Bell CR 008)
2015-02-02 |  | Linda | 809052_10758, 800798_2591, 808090 _ 0091 res to March 13th (Bell CR 009_
2015-02-02 |  | Linda | 809071_15327/13211Co-HAB segreagted from P&CB Accepted for March 16th Cutover date
2015-02-02 |  | Linda | 800672_2091 Res from Jan 28th to March 26th pending Business approval
2015-02-02 |  | Linda | RBVP ID 803075 transit 90541 Cutover fr Jan 15 To TBD pending Bandwidth upgrade
2015-02-02 |  | Leslie | Cleanup column titles and updated Legend. Confirmed Acceptable Sort Rules. Set columns AI and AJ for MPLS Upgrade Schedule use. Cleaned up fill and border formatting to reduce file size.
2015-02-02 |  | Marcus | Updated Col BU & BT TR 3102 1282 2752 3752 5120 2931 1482 2712 2781 3262 1256 1146 1851 90836
2015-02-02 |  | Leslie | Fixed shading in col BQ, 'All Transits'
2015-02-03 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 902. 8562. 3032. 8596. 3956. 1802. 2732.7842. 864. 6192.2882. 5102. 4302. 6222. 6662. 162. 7942. 7952. 1062. 3362. 4922. 202. Updated recabling dates for sites needing to be followed up with PND labeled PND RENO for TR 2702. 5560. 6508. 4080. 1711. 5575. 8720.
2015-02-03 |  | Marcus | Updated Col BU & BT TR 3041 3172 5812 3322 90808 960 1292 4222 1002 1322 6672 1302 222 3142 3412
2015-02-03 |  | Marcus | Inserted comment regarding recabling for TR 5000
2015-02-03 |  | Marcus | Added PH&N 809092_TR3417
2015-02-03 |  | Marcus | Updated CC (Col DO) for 2 Bloor TR 90428 6702 10761 11831
2015-02-03 |  | Brenda | 5802, 490,2109,7692,90322, 600, 90333, 540, 991, 180, 1050, 1440, 7121, 3277, 5619, 5029, 4089, 1402, 7379, 2920, 2360,
2960, 760, 1472,4722, 3002, 7942, 1592, 7602, 533, 342, 846, 732,4862,1722, 362,
2015-02-04 |  | Linda | 801833_7822 res fr Feb 2 to Feb 4 - Weather
2015-02-04 |  | Linda | 800528_1632 Cutover date was changed on Jan 30 to Feb 9th - Changed cutover date back to March 5th No record of approving a date change for Feb 9th
2015-02-04 |  | Linda | Updated columns DT&DU
2015-02-04 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-04 |  | Marcus | Reformatted the change log and repost the change log legend
2015-02-04 |  | Marcus | Updated Col BU & BT TR 2982 5200 90721
2015-02-04 |  | Marcus | Updated TR 90721 site address
2015-02-04 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 90721
2015-02-04 |  | Marcus | Added TR PH&N 1330 and sequenced with other cohabs - see comments ; Added 809093_TR2448 ; Updated INS TR 15112 to include 11263 & 13268
2015-02-04 |  | Marcus | Removed 809091_TR91 [ Cohab with 10758 ]
2015-02-04 |  | Marcus | Updated Col K-R for INS TR 15345, 11271, 15432, 15287, 15347, 15442, 15266, 15289/13177, 15230/12114, 15316/13218, 15250, 15123/15275, 15419/13241, 15327/13211, 16113
2015-02-04 |  | Marcus | RBVP ID correction 809078 to 808094
2015-02-04 |  | Marcus | Updated Col BU & BT TR 90428 6702 10761 5229 1307 6892 1622 5633 15123/15275
2015-02-05 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 809042_90814, 809041_15316/13218, 809057_15250, 809066_14533, 809052_10758, 809071_15327/13211, 801658_7473, 800685_2132, 803092_90601, 801678_6892
2015-02-05 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 803099_90621, 803098_90621, 800275_960, 809039_90808
2015-02-05 |  | Marcus | Updated Col L-R (hours of operation) - TR 4222 5229 1622 6032 3882 5142 3981 5192 8067 7120 4409 1952 5520 4362 922 4002 5722 4508 5030 4662. Verfied OP hours from Feb to Mid-March.
2015-02-06 |  | Marcus | Updated Col BU & BT TR 1280 3832 6032 6022 80 3232 1753 3452 5839 15250 4142 5942 3642 3962 6742 3641
2015-02-06 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) TR 801505_7323, 803082_90561, 809065_10763, 809078_1330
2015-02-06 |  | Marcus | Updated Col L-R (hours of operation) - TR 4910 4342 5922 6800 4800 3262 7360 3412 4142 3642; Verified OP hours till end of March.
2015-02-06 |  | John | Ran script to update column AV, AW, AX
2015-02-06 |  | David | 801565 transit 6032 postponed due to site contact's availability issues in conducting the audit. Also issuse with identifying which numbers needs to be converted and which doesn't (only 20 could be identified out of a total of around 130) - a new date for this site to be provided
2015-02-09 |  | Marcus | Re-added 801726_TR7310
2015-02-09 |  | Marcus | Updated Col BU & BT TR 319 2782 5362 6840 3882 1262 622 1461 1724 9857 4282 3762 6542 15419/13241 15327/13211
2015-02-09 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-09 |  | Marcus | Adjusted pre-audit due dates (Column CV) - Ontario/Quebec from -15 to -17 under 50 counts (Col DO), and -20 for over 50. Western sites from -45 to -47 for all counts
2015-02-09 |  | Marcus | Removed 801726_TR7310
2015-02-09 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 7121. 8059. 8699. 3982. 422. 3002. 3442. 1252. 7862. 2462. 202. 6422. 4922.
2015-02-09 |  | Linda | Transit 1632, 2602, 8067, 1460, 1279, 7120, 1095 , 1061, 324 Res from Mar 5th to Mar 4th
2015-02-09 |  | Linda | Transit 2301 . 15400/11181 Rews from Mar 5th to Mar 17th
2015-02-10 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-10 |  | Brenda | MPLS Completions(AG)TR#266,322,610,1248,1309,1752,2222,2512,3542,3632,4162,4812,5452,7599,7732,7930,8042,8258,9107,15405
2015-02-10 |  | Brenda | MPLS Remove date - TR#886, Change MPLS required to Yes - TR#982
2015-02-10 |  | Brenda | MPLS changed to Yes to No, not required as already upgraded as by TC. TR#608,3021, 3132,3411,3972,4960,7440,8060,8080,90752,90771,90851
2015-02-10 |  | Brenda | POE Required - change to Yes - TR#2142,3182,541,3972,1040
2015-02-10 |  | Brenda | POE Switch Completed - TR#732,1282,1472,1802,2732,3832,4262,7742,553,2891,7381,7731,9181,1090,1680,1920,3862,4120,7929,8040,8148,9859,90836
2015-02-10 |  | Marcus | Added 809095_TR3551 - 3100 Le Carrefour Blvd
2015-02-10 |  | Marcus | Updated Col L-R (hours of operation) - TR 15400/11181, 12990, 11338, 15102, 15306, 12992, 15268, 15407, 15303, 15407, 15267, 15288, 15273, 16107/15272, 15420, 13147, 15257, 15304, 15420
2015-02-10 |  | Marcus | Updated Col BU & BT TR 7381, 3600, 1894, 5192, 90337, 3981, 1436, 5142, 1934
2015-02-10 |  | Marcus | Comfirmed cutover dates for TR 7381
2015-02-10 |  | Marcus | Updated AR Records (Feb 19th to Mar 4th -- Exception to Freeze CR 00126876) & (Mar 5th to Mar 18th -- Regular schedule CR 00127055)
2015-02-10 |  | Marcus | Updated Column DV formula [Total Count (DO) vs Branch Centres (AP)] - explanation in the header comment
2015-02-11 |  | Linda | Scheduled Western Sites - May 4 - May 19
2015-02-11 |  | Marcus | Updated Col BU & BT TR 582, 6752, 6701, 7323, 90561, 10763, 1330, 90814
2015-02-11 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for May/June/July
2015-02-11 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for INS TR 12990, 15257, 12991, 11338, 16107/15272, 15306, 15102, 15286, 12992, 15288, 15268, 15303, 15407, 15227, 15405, 15273, 15420
2015-02-11 |  | Marcus | Updated Col L-R (hours of operation) - TR 11263 / 13268 / 15112 10655 SOUTHPORT
2015-02-11 |  | Marcus | Updated Column DX formula [CC Flag] - explanation in the header comment
2015-02-12 |  | Marcus | Updated Col BU & BT TR 382, 6640, 459, 8719, 3722, 6651, 9987, 150, 272, 802
2015-02-12 |  | Marcus | Updated Column BQ (All Transits)
2015-02-12 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-12 |  | Linda | 802444_12991 & 809056_11831 res from TBD to March 25
2015-02-12 |  | Linda | 800278_982 res to April 1
2015-02-12 |  | Linda | Res from April 2 to April 6 800084_272 , 800042_150, 802324_9987, 801082_3722
2015-02-12 |  | Linda | Updated column AK to sync with DB
2015-02-12 |  | Linda | May schedule completed pending Bell approval
2015-02-12 |  | Linda | Res Ins Sites pending Bell approval 809032_12990, 809022_15257, 802444_12991, 801671_11338, 809051_16107, 809023_15306, 809027_15102, 809002_15286, 809024_12992, 809020_15288
2015-02-13 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-13 |  | Linda | Correction to Laura’s email RBVPID should 809031 _ Transit 11338 ~ 801671 is associated with P&CB Transit 6832 Both sites scheduled for May 4
2015-02-13 |  | Linda | 802774_11263 / 13268 / 15112 Res fr Feb 24th to TBD Pending Approval
2015-02-16 |  | Marcus | Updated Col BU & BT TR 5152, 7722, 2591, 10758, 90313, 14533, 803135_90808, 34, 509, 402, 9107, 1309, 2970, 8802, 24, 3551, 6640, 6462, 8221, 4602, 42, 4082, 982, 90341
2015-02-16 |  | Marcus | 802361 Transit correction (10761), TR 3417 address correction
2015-02-16 |  | Marcus | Added TR 809096_90512
2015-02-17 |  | Laura | Changes to 802898_16113 updated business hours and associated transits with that site
2015-02-17 |  | Linda | 802898_ 16113 Res to April 21st
2015-02-17 |  | Linda | 809093_2448 added Feb 10 cutover date
2015-02-17 |  | Linda | 801913_8080 May 20 / 801935_8197 May 25 Pending Bell approval
2015-02-17 |  | Linda | 800803_2640 Res fr May 4th to May 19th
2015-02-17 |  | Brenda | MPLS Order Status -Pending TR#1082,3202,34,85,150,157,201,302,1325,1334,1342,1824,4585,4620,8220,6231,7151,8197,8327,909,502,3032
2015-02-17 |  | Brenda | MPLS Upgrade Required - NO - TR#9971,1336,7091,90301,1402,7091,
2015-02-17 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for blank cutover dates (70)
2015-02-17 |  | Marcus | Updated Col V (Postal Codes)
2015-02-17 |  | Marcus | Snapshot of Col AP (Total Branch Centrix) in Col EA
2015-02-18 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for current May & June cutover dates (147 transits), Updated Col V (Postal Codes)
2015-02-18 |  | Marcus | Deleted duplicate TR 7200, RBVP (801711).
2015-02-18 |  | Marcus | Updated Col BU & BT TR 5439, 8300, 90829, 394, 2640
2015-02-18 |  | Marcus | Updated hours of operation TR 90635, 90538, 8249, 16258, 9399
2015-02-19 |  | Linda | Transit 5729 Removed cutover date - SIP NA
2015-02-19 |  | Linda | 801565_6032 Res from TBD to April 14 809074_107865 Scheduled for April 9th
2015-02-19 |  | Linda | 809096_90512 scheduled for April 6 pending Bell approval
2015-02-19 |  | Linda | 10766 Res fr April 27 to June 18th to cutover with other LOBs " 803070 90535 , 809092 3417 scheudled for June 18th
2015-02-19 |  | Linda | 802774_ 15112_13268_11263 Res fr TBD to March 9th
2015-02-19 |  | Linda | 809064_15273 Added to May 4 to cutover with 800158 _ 533
2015-02-19 |  | Linda | 803074_90538_ Scheduled Apr 1 pending Bell approval
2015-02-19 |  | Linda | 803096_90613 Scheduled for May 5 pending Bell approval
2015-02-19 |  | Linda | 809060_15304 scheduled april 28 to cutover with 802074_9077
2015-02-19 |  | Linda | 90537_90537, shceduled May 14 Pending Bell approval 803076_90542 shceduled May 19 Pending Bell approval
2015-02-19 |  | Linda | Updated Column E populated blank cells
2015-02-19 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for DS sites with blank cutover dates TR 90531, 90288, 90776, 90542, 90270, 90832, 90555, 90571, 90565, 90853, 90809, 90865, 90270, 90546, 90635, 90752, 90812, 90631, 90283, 90761, 90270, 90615, 90282, 90286, 90851, 90839, 90605
2015-02-19 |  | Marcus | Updated DS hours of operation
2015-02-19 |  | Marcus | Updated Col BU & BT TR 90323, 7473
2015-02-20 |  | John | Ran script to update column AV, AW, AX
2015-02-22 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for sites with blank cutover dates. Validated addresses and postal codes.
2015-02-22 |  | Marcus | Removed 809053_TR90865 - See comments in 803138_TR90809
2015-02-22 |  | Marcus | Updated Col CC (Regions). Standarized Col K,S, T, U, W
2015-02-22 |  | Marcus | Updated Col BU & BT TR 90538, 8372, 90416, 10765, 8641, 492, 9277, 5422, 373, 7950, 8080, 3042, 332, 4902, 3062, 2189, 3051, 5101, 9181, 6582, 6572, 144, 7451, 8060, 7599, 6820
2015-02-23 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-23 |  | Serena | Updated dates and number of phones in Standalone column. Updated re-cabling dates for TR 5467. 4427. 3757, 4687, 4167, 7497, 4622, 4120, 4720, 560, 1860, 5440, 5040, 1090, 880, 2560, 9950, 2890, 2240, 4640.
2015-02-23 |  | Marcus | Category Clean-Ups
2015-02-23 |  | Marcus | Added TR15311, 12994 / 11181
2015-02-23 |  | Marcus | Updated "All Transits" Column
2015-02-23 |  | Marcus | Updated Col BT TR 442, 8932, 7522
2015-02-24 |  | Linda | Working on June Schedule
2015-02-24 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-24 |  | Brenda | MPLS Updates to TR#34,85,150,157,201,302,354,894,1109,1119,1288,1325,1334,1342,1639,1819,1082,1824,2000,2052,2539,2649,2820,2869,2962,2979,3032,3199,3451,3880,3202,3920,4359,4480,4585,4620,4670,5220,5440,6231,7049,7200,7947,8039,8189,8197,8229,8919,9179,9459, |  |  | 9073490812
2015-02-24 |  | Linda | 800392 1336 25-May , 801412 5080 28-May , 800622 1860 21-May , 801477 5509 28-May , 801760 7497 28-May , 809032 12990 30-Mar Co-ord with 801760_7497 1 truck roll
2015-02-25 |  | Linda | Sites scheduled in April placed on hold due to MPLS upgrade requirements : 800142 490 , 800006 34, 800679 2109, 800147 502, 800042 _150
2015-02-25 |  | Linda | 809031_11338 Res fr May 4 to April 6th Site is opening on April 19th Need service prior to April 19th
2015-02-25 |  | Linda | 809024_ 12992 Res from May 14 to May 21 ¦ 801786_7662 from May 21 to May 14 to accommodate INS site 12992
2015-02-25 |  | Linda | Dundas and Spadina, TR 6752 & TR 7473 on hold RENO ETA 2016
2015-02-25 |  | Linda | 800850_2852 res fr May 27 to may 20 to accommodate INS site 809020_15288 May 27th
2015-02-25 |  | Linda | Added tech names for TR 3762 & 3262
2015-02-25 |  | Marcus | Reviewed and updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW) for March cutovers
2015-02-25 |  | Marcus | Updated "All Transits" Column
2015-02-25 |  | Marcus | Updated Col BU TR 8380, 6720, 8640, 846, 8340, 6827, 90811, 10756, 15257, 12990, 1860, 1278, 6520, 1336
2015-02-25 |  | Marcus | Sequenced Phase 1 Pilot
2015-02-26 |  | Marcus | Applied consistent format in (Column V)
2015-02-26 |  | Marcus | Updated RMO & MMO
2015-02-26 |  | Marcus | Cohab Split - Added DS 809098_TR90270, 809099_TR90763, 809100_TR90809, 809101_TR90282
2015-02-26 |  | Marcus | Verified hours of operations for March cutover dates
2015-02-26 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-27 |  | Pat Armstrong | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-02-27 |  | David | TR 3762 changed to TBD from March 31 via Linda/Serena: this is the site that has asbestos....we were told to stop recabling until the asbestos has been rectified. this site will need to be pushed out a few months.
2015-03-01 |  | Marcus | Updated Col BU TR 7930, 8272, 1061, 8541, 8067, 1095, 324, 2602, 5080, 1460, 2370, 1632, 1279, 7497, 90512, 90711, 2159, 5592, 6802, 7542, 4175, 4102, 7572, 2391, 7941, 15327/13211, 1336
2015-03-02 |  | Serena | Updated dates and number of phones in Standalone column.
2015-03-02 |  | Marcus | Updated Col BU TR 11338, 15400/11181, 5762, 597, 6622
2015-03-02 |  | Marcus | Updated RMO & MMO, All-Transits
2015-03-02 |  | Marcus | Category Clean-Ups
1900-01-01 |  | Marcus | Updated P&CB TR 177 to PH&N 16309
2015-03-02 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-02 |  | Linda | _941 was scheduled for April 22 but cutover Sept 30 2014 Updated Master with correct cutover date
2015-03-02 |  | Linda | Res fr April 16 to May 21 - co-ord with co-hab site 803052_90439 - Change site treatment from P&CB to PB / RBC req
2015-03-03 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-03 |  | Brenda | MPLS upgrade Required - NO - TR#5220, 8327, 90571
2015-03-03 |  | Brenda | Updated Target Date and constraint forTR#5802,150,490,2109,34,7692,502,90333,90734,991,90853,1050,549,180,212,201,6000,1372,160,1288,1109,1119,8382,400,560,1639,1325,1879,2539,2649,2869,1819,2979,3199,1240,838,1440,1680,2800,3649,5029,4329,4359,5619,6231,4585,2000,2052,2360,5000,2450,7049,2820,2830,3451,7379,2920,1334,2940,3040,354,3032,3277,3920,8039,4080,3702,8059,8149,7121,8189,4240,4400,4480,4670,4720,4760,3880,8589,4242,9399,9459,8229,4627,8567,7947,8197.
2015-03-03 |  | Marcus | Updated Col BU TR 2941, 90621, 16345, 8982, 7792, 6061, 431, 90832
2015-03-03 |  | Marcus | Updated AR #s for the March 9-18th migrations including TR2591, TR 11263 / 13268 / 15112
2015-03-03 |  | Marcus | Updated site treatment (Column F) for TR 1146 as PB
2015-03-03 |  | Linda | SIP available in Brandon MB 800226_787 & 800228_797
2015-03-03 |  | Linda | Updated column BD with NPA
2015-03-03 |  | Linda | Updates SIP from 0 sites Yes Transits : 15442, 15266, 90565, 15345, 15308, 10768, 2080, 15289/13177, 15230/12114, 16103, 15274. 90865, 90808, 15250, 2448, 14533, 3160, 11176, 787, 797, 222
2015-03-03 |  | Linda | Updated 54 Western sites and non sip sites with April 1 2016 cutover date
2015-03-04 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-04 |  | Marcus | Updated Col BU TR 1952, 922, 3672, 4409, 6612, 1271, 4362, 5520, 16309
2015-03-04 |  | Marcus | Updated site treatment (Column F) for TR 2409 as PB
2015-03-04 |  | Marcus | Updated PH&N hours of operation
1900-01-03 |  | Marcus | Updated TR# 4482 branch category to P&CB and site treatment to PB
2015-03-06 |  | John | Ran script to update column AV, AW, AX
2015-03-06 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-06 |  | Marcus | Updated Col BT & BU TR 616, 1362, 4912, 5722, 3082, 1222, 15123/15275, 4695, 812, 4002, 563, 5501, 90701, 90809, 1457, 8160, 2182, 1962, 1200, 7692, 1659, 1240, 434, 6202, 9998, 5971, 9077
2015-03-06 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-09 |  | Serena | Updated dates and number of phones in Standalone column.
2015-03-09 |  | Marcus | Updated Col BT & BU TR 4508, 1106, 1131, 7582, 5030, 2621, 4882, 15419/13241, 320, 8400, 84
2015-03-10 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-10 |  | Brenda | Updated POE Switch dates- TR#1040,3610,3812,2142,3972,640,1543,4122,9851- TR#90701 no switch required
2015-03-10 |  | Brenda | Updated MPLS order info for TR#2920,2109,490 changing from Telus to Bell
2015-03-10 |  | Brenda | Updated MPLS order info for SIP-no, TR#1878, 3198,5838,618,4953,7818,4298,761,3748,3668,4408,2648,90762,5597,2087,2208,3638,774,3308,3528,2607,5178,2097,2997,1957,3633,527,1567,2477,2098
2015-03-10 |  | Pat A. | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-10 |  | Marcus | Removed duplicated columns. Updated Legend.
2015-03-10 |  | Marcus | Updated Col BT & BU TR 9082, 6160, 4120, 8991, 8111, 7711, 10758, 2591, 5052, 2102, 232
2015-03-10 |  | Marcus | Removed training date for RBVP 801969 TR 8400. Training will not be provided for this site.
2015-03-10 |  | Marcus | Removed GU Location 220 Portage (Winnipeg) RBVP ID 809094
2015-03-10 |  | Marcus | Added TR 2196, 15318/13267, 15229/11287
2015-03-11 |  | Linda | Updated comments on pending approvals. Due to cabling requirements ; Placed TR 1860 on hold pending NDD
2015-03-11 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-11 |  | Marcus | Updated Legend
2015-03-11 |  | Marcus | Updated Col BT & BU TR 116, 1742, 543, 4627, 7760, 724, 6377, 6277
2015-03-11 |  | Marcus | Updated "All Transits" Column
2015-03-11 |  | Marcus | Removed TR 17322, 6752, 10774, 7473, 5050, (moved to deleted sites),
2015-03-12 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-12 |  | Marcus | Updated Col BT & BU TR 7731, 4262, 8661, 533, 2342, 6832, 8440, 2152, 842, 90583, 2319, 258, 1492, 4701, 1040, 2301, 3551, 2152, 15400/11181, 842, 4409, 11263 / 13268 / 15112
2015-03-12 |  | Marcus | Added NEW Column (CX): Multi-Floors Flag; Updated Legend; Populated for April 2015
2015-03-12 |  | Marcus | Updated "All Transits" Column
2015-03-12 |  | Marcus | Added NEW Column (CY): # Transits - Counts the number of transits in a location (Col BQ). Updated Legend. Updated counts for populated "All transits"
2015-03-13 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-13 |  | Marcus | Updated "All Transits" Col & "# Transits" Col
2015-03-13 |  | Marcus | Updated Col BT & BU TR 12990, 15327/13211 (DUNDAS & WILMAR), 902, 1560
2015-03-14 |  | Marcus | Updated Col BT & BU TR 1552, 2442, 3901, 913, 2165, 7472, 7287, 1599, 4530, 5261,
2015-03-14 |  | Marcus | Updated "All Transits" Col & "# Transits" Col
2015-03-16 |  | Linda | Western and QC confirmed for June
2015-03-16 |  | Linda | 800928 _ 3172 Res fr Mar 25 to May 27 due to renos
2015-03-16 |  | Linda | 801047_3622 : Res from May 7 to April 27 - Not approved by Bus New Proposed date May 12
2015-03-16 |  | Serena | Updated dates and number of phones in Standalone column. TR 1062 changed to PND RENO.
2015-03-16 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-16 |  | Marcus | Updated Col BT & BU TR 1989, 3482, 7619, 2642, 4910, 1783, 90314, 16258, 2762, 1722, 362, 4089, 5920
2015-03-16 |  | Marcus | Changed TR8372 to TR1496
2015-03-16 |  | Marcus | Updated CI-CN
2015-03-16 |  | Linda | 803157_90855 Res from April 29 to May 13 pending FS approval
2015-03-16 |  | Linda | 802324_9987 Bus N/A on April 6 - Res to April 8 -
2015-03-17 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-17 |  | Marcus | Updated Col CI-CL CTX & IP counts
2015-03-17 |  | Marcus | Updated Col BT & BU TR 6182, 2132, 90322, 90536, 90613, 90511, 1662
2015-03-18 |  | Linda | 803157_ 90855 : Confirmed for May 13 809027_15102: Confirmed for May 12 801047_3622 :Confirmed for April 29 800359 _1248 Confirmed for April 27
2015-03-19 |  | Linda | Updated tech info column AN
2015-03-19 |  | Linda | 809105_ 15318/13267 scheduled July 13 / 809106_15229/11287 Jul 16 pending Bell FS approval
2015-03-19 |  | Linda | Working on Western Schedule July-Sept
2015-03-19 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-19 |  | Marcus | Updated Col BT & BU TR 1834, 1834, 5922, 2400, 6800, 4992, 6147, 8149, 7159, 4342, 1042, 5502, 1882, 7602
2015-03-19 |  | Marcus | Updated activity records (Col BP) March 19th to April 4th --- CR 00130112
2015-03-19 |  | Marcus | Updated Col BT & BU TR 90509, 90345, 7902, 2212, 5522, 3021, 4800, 1146, 3262, 2712, 1851, 1482, 1256, 2781, 7920
2015-03-20 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-21 |  | Linda | AB schedule for July & Aug confirmed
2015-03-21 |  | Linda | 803157_90855 Confirmed for May 13
2015-03-21 |  | Linda | 800622_1860 Cutover res to June 15 Audit confirmed for April 17
2015-03-21 |  | Linda | 800679_2109 Site will be ready June - Propose vutover date of Aug 12
2015-03-21 |  | Linda | 801641_6651 T-2 & T-0 Res to April 8 ¦ NDS April 10 (Branch closed Tues and Thur)
2015-03-22 |  | Marcus | Updated Col BT & BU TR 12991, 4482, 222, 1486, 5812, 3041, 1360, 7360, 3322, 11831, 732, 7741, 7742, 8122, 4862, 3411, 90836, 3639
2015-03-23 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-03-23 |  | Marcus | Updated Col BT & BU TR 3692, 4722, 15257, 11338, 3412, 3142, 2982, 1592, 8088, 6762, 7712, 3710,
2015-03-23 |  | Marcus | Updated CTX/IP/Total user counts columns
2015-03-23 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW)
2015-03-24 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2105-03-24 |  | Brenda | 909 - upgrade - no, 6498 - change to 2015, MPLS completion - 5802,90322,90333,8149,4242,3702,6498,4329,2109
2015-03-25 |  | Linda | 809102_15311 / 11125 Updated cutover date from June 4 to July 2014 -Laura confirmed INS was completed with P&CB
2015-03-25 |  | Linda | 809103_ 12994 / 11181 Updated cutover date from June 18 to Dec 1 2014 Laura confirmed site migrated with P&CB LOB
2015-03-25 |  | Linda | 802444_ 12991 tentatively res fr Mar 25 to Apr 28 pending RENOs
2015-03-25 |  | Linda | 801702_ 7121 Res June 4 to June 25 (Cabling scheduled for June 4)
2015-03-25 |  | Linda | 801863_7942 Res from June 22 to July 16 pending cabling
2015-03-25 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-25 |  | Marcus | Updated Col BT & BU TR 4529, 3461, 5942, 3622, 1248, 2440, 382, 5892, 6352, 9837, 4642, 90537, 4180, 2091, 3777, 2880, 2419, 1248, 90327, 3642, 4142, 3962,
2015-03-25 |  | Marcus | Updated pre-audit formulas
2015-03-25 |  | Marcus | Updated floor flag for may cutover
2015-03-25 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-26 |  | Marcus | Updated Col BT & BU TR 6247, 6907, 4620, 863, 608, 6231, 8567, 3199, 4282, 1504, 6542, 5137,
2015-03-26 |  | Marcus | Updated Column BQ (All Transits) & Column CY (# Transits)
2015-03-26 |  | Marcus | Removed PB 809077_TR10773 (10117 JASPER AVE-SUITE 1400 - GU Location ). Moved to deleted sites tab
2015-03-26 |  | Marcus | Updated Col BT & BU TR 642, 7842, 6172, 8371, 838
2015-03-27 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-27 |  | Marcus | Added Retail by Design column (RbD): Column CZ. Identitied sites undergoing RbD. Legend Updated
2015-03-27 |  | Marcus | Added Collision Date with DICE & DICE Collision Window (Col DA & DB). Identified sites with DICE collisions - Total:44
2015-03-27 |  | Marcus | Updated Col BT & BU TR 7662, 4312, 3182, 4786, 2562, 3732, 2852, 15288, 482, 90835, 7440, 797, 582, 982, 3662, 9857
2015-03-29 |  | Linda | 800049_16309 res from May 6 to Sept 10
2015-03-29 |  | Linda | 800679_2109 res fr Aug 12 to Aug 11
2015-03-29 |  | Linda | 803069 90533 res fr Jun 18 to jun 25
2015-03-30 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-03-30 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-03-30 |  | Marcus | Updated Col BT & BU TR 90436, 90348, 12992, 14326, 90542, 802, 1110, 2920, 6701, 15306,
2015-03-30 |  | Marcus | Updated DICE collision window (Col DB) - Total:33 - Apr: 2 sites ; May: 2 sites ; June: 14 sites ; July 9 sites ; Aug 9 sites **Filter by Colour
2015-03-31 |  | Linda | 90327 & 6742 Res from March 30 to TBD pending CM fix
2015-03-31 |  | Linda | 90416 & 10765 Res from April 9 to Jul 16 Customer request
2015-03-31 |  | Marcus | Added Collision Date with SilverPeak & SilverPeak Collision Window (Col DC & DD) - Total: 9 **Filter by Colour
2105-03-31 |  | Brenda | Updated switch poe completed - TR#2142, 3182, 3972, 1040
2015-03-31 |  | Brenda | Updated Parent Info for POE, MPLS Device Name and speed for Children 15123/15275,14259,15318/13267,15304,15273,15308,10768
2015-03-31 |  | Brenda | Update info for new branch TR#2196
2015-03-31 |  | Marcus | Updated Col BT & BU TR 4602, 272, 90512, 14259, 15306, 15273, 12991
2015-04-01 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-01 |  | Marcus | Updated Col BT & BU TR 4082, 1472, 5399, 4962, 3520, 42, 8221, 2142, 5585, 3111, 1371, 792,
2015-04-01 |  | Marcus | Updated "All Transits" Col & "# Transits" Col
2015-04-01 |  | Marcus | Removed duplicate TR 5220 --- site previously migrated
2015-04-01 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-01 |  | Linda | 801649/6742- Res to April 8 pending RBC approval 803074/90538- Res April 8 pending RBC approval 800463/1504 Res April 13 pending RBC approval
2015-04-01 |  | Linda | Update Trunk Group info Columns CP & CQ
2015-04-02 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-02 |  | John | Ran script to update column AV, AW, AX
2015-04-05 |  | Marcus | Updated Col BT & BU TR 3277, 5382, 90508, 1216, 372, 1022, 8971, 5382, 3277, 90715, 90323, 5152, 7722, 24, 7680, 1496, 8802, 14483, 90851, 8039, 5200, 8000,
2015-04-06 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-04-07 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-07 |  | Marcus | Updated Col BT & BU TR 3172, 7751, 8561, 5882, 2874, 90731, 5040, 4130, 1420
2015-04-07 |  | Marcus | Updated Col DO (Total Count) Col AS (CC) & Col DZ (Total BW)
2015-04-07 |  | Marcus | TR# Correction: 63771 to 90771
2015-04-07 |  | Marcus | Updated RbD Flags
2015-04-07 |  | Marcus | Updated Branch Category TR 16345 to PB
2015-04-08 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-09 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-09 |  | Marcus | Updated Col BT & BU TR 15318/13267, 4760, 5840, 1827, 6032, 4902, 3062, 332, 3042, 492, 8110, 5489, 8641, 3160, 5422, 9277, 10756, 782, 90587, 6342, 4942
2015-04-09 |  | Marcus | Moved 803105_TR90701 (333 7TH AVE SW - 14TH FLR CALGARY AB) --- Out of scope
2015-04-10 |  | Linda | TR 15229 res from July 16 to June 8 *** TR 14694 will be added June 8 (3 users)
2015-04-10 |  | Linda | Cold Lake - TR 429 res from May 19 to April 2016 SIP N/A ( incorrect NPSNXX on Master) Correct from 780594 to 780639
2015-04-10 |  | Linda | Removed Trng dates from DS IPT sites : 90323, 90511, 90829, 90613, 90721, 90855, 90537, 90811
2015-04-10 |  | Linda | TR 90327 Res to April 14
2015-04-10 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-11 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-04-13 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-04-14 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-14 |  | Marcus | Update Col BP Activity Records April 16th & April 29th - Regular schedule C00142711
2015-04-14 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates & showed dd pushed to Sept 10 for #2196 (site under construction)
2015-04-15 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-15 |  | Marcus | Added 809107_TR14903 PB 195-315 8th Ave SW Calgary
2015-04-16 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-16 |  | Marcus | Aligned master's Pre-Audit due dates with dashboard for western sites
2015-04-16 |  | Marcus | Moved 809106_TR15229/11287 195-315 8th Ave SW Calgary & 809107_TR14903 PB 195-315 8th Ave SW Calgary to deleted tab ---- GU Location; out of scope
2015-04-16 |  | Marcus | Updated "All Transits" Col BQ & "#Transits" Col CY
2015-04-17 |  | John | Ran script to update column AV, AW, AX
2015-04-17 |  | Marcus | Updated RMO & MMO info for Alberta & Territories Columns "CD" & "CE"
2015-04-17 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-20 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-20 |  | Marcus | Updated "All Transits" Col BQ
2015-04-20 |  | Linda | 802898_ 11259_16113 Virtual Way Res fr April 21 to TBD - POE issues
2015-04-20 |  | Linda | 801775_7602 res fr May 7 to April 28
2015-04-20 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). Updated Perth (TR 442) end date to May 30, 2015.
2015-04-21 |  | Brenda | Updated AG, AI, AJ - TR#1372,7751,6247,6907,991,1240,2920,4627,6377,85,1453,6147,3032,502,354,7121,3451,160,150,34,6231,8567,3199,4585,8382,157,838,2052,8039,1334,3277,4760,8197,8040,4720,90734,201,1094,3649,2940,1325,7947,2979,490,2109,180,212,549,1109,1119,1288,1639,1879,2539,2649,4359,5029,5619,7049,7379,8059,8189,8229,8589,9179,9399,9459,7600,8480
2015-04-22 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-22 |  | Marcus | Verified and aligned pre-audit dates
2015-04-22 |  | Marcus | Updated Multi-floor flags for all June 2015 cutovers
2015-04-22 |  | Marcus | Updated "All Transits" Col BQ
2015-04-22 |  | Marcus | Removed 809090_TR809 - 200 Bay Toronto. Moved to deleted sites.
2015-04-22 |  | Marcus | RBVP ID correction 808086 to 809086
_ 90736 res from July 21 to June 11
Updated tech info column AN
802898_11259 /16113 Res from April 21 to May 4
2015-04-23 |  | David | Updated AK for 803120, 801368, 801480, 800894, 800682, 801846, 801652, 801809, 801080, 800509, 809002, 801350, 803042, 803061 to be aligned with actual audit dates.
|  | David | added in June 15, 2015 as a holiday for ON to be consistent with Dashboards holiday list.
2015-04-23 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-23 |  | Marcus | Updated collisions with DICE column "DA" & "DB" - May-Aug migrations --- Total counts 45
2015-04-24 |  | Linda | Updates technician info column AN
2015-04-24 |  | Linda | Updated columnd BH CP CQ
2015-04-24 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-24 |  | Marcus | Updated "All Transits" Col BQ
2015-04-24 |  | Brenda | Updated dates in Columns AG, AH, AI, AJ, DE, DF for priority sites - 151
2015-04-27 |  | Linda | Updated cutover date for TR 2102 April 29
2015-04-27 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-04-27 |  | Brenda | Updated comments in Column AJ to Pending DC ckt install for 1567,2477,2098,6907,4627,6377,6147,8567,3277,8040,7947,90761,9879,90762,2978,8288,1768,5828,2318,998,2217,6767,4167,4427,4518,1548,4848,8698,1697,1047,7268,897,6768,2538,618,5857,3748,4408,2648,5597,2087,3638,3308,3528,2607,5178,2097,2997,1957,527,2737
2015-04-27 |  | Marcus | Updated column "BU" & "BT" with T35/65 Communications
2015-04-27 |  | Marcus | Verified and aligned pre-audit dates
2015-04-27 |  | Leslie | Updated Col AI for forward MPLS Upgrades scheduled. Added MPLS Upgrade Requirement & Status columns DG, DH, DI with formulae
2015-04-28 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-04-28 |  | Marcus | Verified and aligned pre-audit dates (Alberta)
2015-04-28 |  | Marcus | Update Col 'BP' Activity Records April 30th & May 13th - Regular schedule C00142712
2015-04-28 |  | Marcus | Removed PB 809086_TR14259 (9499 137TH AVENUE-UNIT 1032). Moved to deleted sites tab.
2015-04-29 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-04-29 |  | Marcus | First communications dates for BC, Alberta, Manitoba aligned and verified with DASH
2015-04-29 |  | Marcus | Verified and aligned pre-audit dates (BC June 2015)
2015-05-01 |  | John | Ran script to update column AV, AW, AX
2015-05-01 |  | David | Updated Column AN (tech names)
2015-05-01 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-01 |  | Marcus | Updated 800876_TR2962 address 5539 Main St. to 5501 Manotick Main St.
2015-05-04 |  | Marcus | Removed 803068_TR90531 50 QUEEN ST W SUITE #300 (- No DS users at this location) . Moved to deleted sites tab
2015-05-04 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-04 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). End date changed for TR 9879 from June 22 to May 19th. End date changed for TR 8699 from July 6th to June 8th.
2015-05-05 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates & showed dd changes for #490 & #7751
2015-05-05 |  | David | Updated audit dates column AK, and 2891's new cutover date to may 25. 5010 and 90809 res to 8/11 pending Elaine's confirmation. Transit 2891 to May 27
2015-05-05 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-05 |  | Marcus | Updated TR 4812 address from 237 MAIN ST to 7307 HWY 26-PO BOX 910
2015-05-05 |  | Marcus | Updated Branch Category TR3630 from P&CB/DS to P&CB only. DS is not in this location
2015-05-05 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-06 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-06 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-07 |  | David | Updated column "AL" with cutover dates for transit 90809, 5010, 14143, 10777
2015-05-07 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-07 |  | David | Updated column 'AK' with audit date for 809062 TR15407
2015-05-07 |  | David | Updated column 'AL' with new cutover dates for 801006 3451, 801702 7121, 801326 4585, 801487 5575
2015-05-08 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-08 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-11 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-11 |  | Marcus | Moved 801959_TR8371 to deleted sites tab.
2015-05-11 |  | Marcus | Updated 801025_TR3542 address
2015-05-12 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-12 |  | David | Updated column "AL" with cutover date for 10777 to show it the users at this location was already migrated on 1/21/2015.
2015-05-13 |  | Pat | Updated column "AN" with tech information & confirming column "AL" to ensure correct cutover dates
2015-05-13 |  | Brenda | Updated MPLS Upgrade dates(column AG) 2920, 1453,150,6231,8039,1334,8197,3649,212,5063
2015-05-13 |  | Brenda | Updated Column AJ - 3032, 354,34, 7121,2052,1187
2015-05-13 |  | Brenda | Updated MPLS Ckt Install (column DE) 6767,6907,201,2203,1240,7600,4167,4427,1548,2920,7593,4848,8698,4627,90762,1697,1047,6377,8288,7268,897,150,1768,6768,2538,6231,5828,1878,5838,6147,2318,618,7818,8567,998,4298,4585,2217,2322,2109,3748,4408,90761,5597,2087,4518,9879,3308,3528,2607,5178,2097,2997,2737,527
2015-05-13 |  | Brenda | changed TR#90541 to MPLS Upgrade required - yes
2015-05-13 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-13 |  | Marcus | Updated Col BP Activity Records May 14 to 28 - Regular schedule C00150991
2015-05-13 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates & date changes to transits #201 #3032 #354
2015-05-14 |  | David | Updated cutover date for 8480 and 4130 (swapped).
2015-05-14 |  | David | Updated audit date as per client request for 3649 due to availablity
2015-05-14 |  | David | Updated 803118 90734, 803142 90812, 803160 90857 to remove ADA NDS requirement as per client approval
2015-05-15 |  | John | Ran script to update column AV, AW, AX
2015-05-19 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates & date changes to transits #201 #3032 #354
2015-05-19 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). TR 90301 added to re-cable list as it was aquired 'as is' and is not up to RBC cabling standards. Date to be determined.
2015-05-19 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates & date changes to transits #201 #3032 #354
2015-05-19 |  | Brenda | Removed Target Date for TR#6247,85, 3032,354,34, 7121,3199,2052,2940,1325,8059,5619,5029,7379,1109,1639,180,549,8589,3418,2208
2015-05-19 |  | Brenda | Updated Column DE-Install date 158,558,8808,8148,2868,7928,3198,824,3668,7840,5288.
2015-05-19 |  | Brenda | Updated Column AQ MPLS Migration - TR#90853
2015-05-20 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-21 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-21 |  | Marcus | Removed 809079_TR10775 1055 W GEORGIA ST-5TH FLR Vancouver BD; GU Location. Move to the deleted sites tab.
2015-05-21 |  | Marcus | Updated MCC & Branch mgr for May cutover
2015-05-22 |  | David | Updated next day support to indicate remote NDS was approved for TR 14483
2015-05-22 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-22 |  | Marcus | Added New Column to monitor CWN Cache Mode project (Column DE)
2015-05-22 |  | Marcus | Updated TR3702 address to 2534 County Rd 29 Pakenham (orginally 2534 Graham St)
2015-05-25 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-25 |  | Marcus | Added data validation rule on RBVP ID (column C) - only unique RBVP ID can be entered
2015-05-25 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-05-25 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-05-25 |  | Leslie | Update MPLS Upgrade Required Date for "Priority 48" sites to be 5 days less than Cutover Date. Corrected formulae to handle blank MPLS Upgrade Target Date. Corrected cutover date for TR201 s/b Sept 1, 2015
2015-05-25 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-05-26 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-05-26 |  | Brenda | Updated MPLS upgrade date column AG - 1325, 2109, 4760
2015-05-26 |  | Brenda | Updated MPLS Target Date column DG - 34, 85,3277, 4627,6147,6377,6907,7947,224, 824,1874,3413,7593
2015-05-27 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-05-28 |  | Pat | Updated Column "AN" with tech information
2015-05-28 |  | David | Updated Column "AK" with new audit dates for transits 90812, 90416, 10765, 90546
2015-05-28 |  | David | Updated Column AL with new cutover dates for 6247, 803141 (90811) - 6247 is pending MPLS upgrade, 90811 is a resch
2015-05-29 |  | John | Ran script to update column AV, AW, AX
2015-05-29 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-05-29 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-05-29 |  | Marcus | Added 809106_TR90851 707 Fort St. Victoria, BC
2015-06-01 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-01 |  | David | Updated cutover date for TR 5585, 17306 and 90811
2015-06-01 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). Date Change for TR 4167. Moved up to June 22nd - 27th from July.
2015-06-01 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-06-01 |  | Marcus | Column G (Transit) - Prompts warning whenever a non-unique transit number is added
2015-06-01 |  | Marcus | Column S (Site Address) - Prompts warning whenever a non-unique site address is added
2015-06-02 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-03 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-04 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-04 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-06-04 |  | Marcus | Removed 809075_TR10769 PB 383 RICHMOND ST-SUITE 803 --- Address already migrated. Moved to deleted sites tab
2015-06-05 |  | Brenda | Updated Column DG MPLS Target Date 4585,838,4720,7600,2322,2203,85,201,1240,1325,2979,3277,7840, 1187, 8288,1768,5828,2318,6767,998,2217,4167,4427,1548,4848,8698,1697,1047,7268,897,3668,90761,6768,2538,1878,5838,618,4958,5857,3748,4408,2648,5597,2087,3638,4518,3308,6168,3528,2607,5178,2097,2997,1957,527,2737,1567,2477,2098
2015-06-05 |  | Brenda | Updated Column DR MPLS Install Date 838,3418,6169,4298,1325
2015-06-05 |  | Brenda | Updated Column AG MPLS Upgrade Date - 4720,7600,1440,2322,2203,7840
2015-06-08 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-08 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-06-08 |  | Marcus | Updated counts & CC/BW for TR 90453
2015-06-08 |  | Leslie | Update MPLS Upgrade Required Date for 90301. Added formulas for status
2015-06-08 |  | David | Update cutover dates for: 2196 (June 18) 90453 (July 8th), 1240 (moved from June to TBD pending MPLS upgrade), 801679 (June 29th)
2015-06-09 |  | Marcus | Updated address for TR90453 from 2175 Queen St to 45 Wicksteed
2015-06-09 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-10 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-10 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-06-10 |  | Marcus | Added 809108_TR90453 2175 Queen St. E-Suite 2 updated hours and counts
2015-06-10 | David | Marcus | Added TR90453 with July 6 2015 cutover
2015-06-10 |  | Marcus | Updated RBVP ID for TR 90453 45 Wicksteed to 809109 (old: 801598)
2015-06-11 |  | Marcus | Updated RBVP ID for TR 90543 - 809108: 45 Wicksteed ; 809109:2175 Queen St. E. Floor 2
2015-06-12 |  | John | Ran script to update column AV, AW, AX
2015-06-12 |  | Marcus | Updated column 'BU' & 'BT' with T35/65 Communications
2015-06-12 | David | Marcus | Updated 803030_TR90311 cutover from June 2 to June 11
2015-06-12 |  | Marcus | Reviewed and Updated addresses for June cutovers
2015-06-15 |  | Marcus | Update Branch contacts for June-Aug cutovers columns BV-CB
2015-06-15 |  | Marcus | Updated columns 'BU' & 'BT' with T35/65 Communications
2015-06-15 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-06-16 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-16 |  | Marcus | Updated column ''BT'' with T3 communications
2015-06-16 |  | Marcus | Updated activity records (Col BP) C00154827 for June 1 to 13 ; C00157860 for June 13 to 26
2015-06-16 |  | Marcus | Reviewed counts for July-Sept cutover
2015-06-17 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-17 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-18 |  | David | Updated Audit + Training column and requirements for 90301, 14143. Updated Cutover date for 90591, 90851, 3762, 3199
2015-06-19 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-19 |  | Brenda | Updated MPLS Upgrade Date (column AG) 6907,4627,6377, 85,6147,34,8567,4585,838,3277,2979,7947,8480,7593,2978,5828,3658,2318,224,4167,4240,4958,4080,5597,6080,2800
2015-06-19 |  | Brenda | Updated MPLS issue/constraint (column AJ) 1187, 90762,8288,1760,998,2217,6767,4427,1548,4848,8698,1697,1047,7268,897,6768,2538,1878,5838,618,5857,3748,3668,4408,2648,90761,2087,3638,4518,9879,3308,3528,2607,5178,2097,2997,1957,527,2737,1567,2471,2098
2015-06-19 |  | Brenda | Removed date from MPLS Upgrade Date (column AG) 1325
2015-06-19 |  | Marcus | Updated column ''BT'' with T3 communications
2015-06-22 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). Added re-cable dates for TR 9242 & 90301.
2015-06-22 |  | David | Updated Cutover times for 809072 / 10762 and 809073 / 10764 to reflect users were migrated October 2014. Updated 803091/90591 cutover date to reflect July 2014 migration.
2015-06-23 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-23 |  | Marcus | Updated column ''BT'' with T3 communications
2015-06-24 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-24 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-24 |  | David | Removed old cutover date of July/2014 for TR 8081 as we're looking to for a new date for this pilot site
|  | David | Updated Audit and Cutover dates for TR 1240, 5029, 1639, 212, 90853, 4359, 2539
2015-06-26 |  | John | Ran script to update column AV, AW, AX
2015-06-26 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-26 |  | Marcus | Updated column ''BT'' with T3 communications
2015-06-26 |  | Brenda | Updated column DF - TR#2539,6247,7121
2015-06-26 |  | Brenda | Updated column AJ - TR#2539,4359,7121
2015-06-26 |  | Brenda | Updated column DQ - TR#2539,4359,7121,6247
2015-06-26 |  | Brenda | Removed space from column AG - TR#1325
2015-06-26 |  | Brenda | Column AF - MPLS Upgrade Requested changed to Yes - TR#90301
2015-06-29 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-06-30 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-06-30 |  | kathy | updated column AJ - TR#23630,998,1639,7928,180,3529,8698,2538,3198,6169,2450,2240,2560,1879,3748,3668,4408,824,2208,3528,2800,2533,3413,5288,3880
2015-06-30 |  | kathy | updated column AH TR#3529,8699,4518,6829,6279,880,7929
2015-06-30 |  | kathy | updated column AG TR#558,2538,6169,3748,3668,4408,3528,2533,3413,3880
2015-06-30 |  | kathy | updated column DF TR#90734,778,1639,180,2208,4518
2015-06-30 |  | Leslie | Updated cutover date for 90301 and 16309 to Sept 1st as placeholder until cutover plan/date can be confirmed
2015-06-30 |  | Leslie | Updated MPLS Upgrade Target date col DG for 90734
2015-06-30 |  | Leslie | Updated MPLS required date col AI for 90808, 90541
2015-06-30 |  | Leslie | Added new columns for PRI/Gateway Decommissioning Tracking, populated some data for transits being piloted through the new process
2015-07-02 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-02 |  | Marcus | Update Col BP Activity Records June 27 to 10th --- C00163485
2015-07-02 |  | Marianna | Updated col DG for Transit 7121, 4359
2015-07-02 |  | David | Updated cutover dates for 801596 6247, 800935 3199, 800056 201, 800657 2052, 800228 797, 801914 8081
2015-07-02 |  | David | Added additional tech names for TR 90416
2015-07-06 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-06 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-07-06 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-07 |  | kathy | updated column AG - 527,897,1047,1187,1957,2087,4427,2217,2477,2607,2737,2997,5857,6767 corrected
2015-07-07 |  | kathy | updated AH - 90808,90301,1874,1680
2015-07-07 |  | kathy | updated AJ - 90808,7121,618,2539
2015-07-07 |  | kathy | updated AG - 7121,618,2539
2015-07-08 |  | Marcus | Added two new fields: Pager & Add-on
2015-07-08 |  | Marcus | Update Col BP Activity Records July 8-10 --- C00163485
2015-07-08 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-08 |  | Marcus | Updated Multi-floor flags for all July & Aug 2015 cutovers
2015-07-08 |  | Marcus | Updated address for TR8480 to 590 PARK ROYAL N , WEST VANCOUVER , BC, V7T 1H9
2015-07-09 |  | David | Updated cutover dates for sites moved to Sept 1st + April 2016: 800657, 801596, 800898, 800105, 800049, 90734, 2940, 1325, 6247 (moved to Aug 12 tentatively)
2015-07-10 |  | John | Ran script to update column AV, AW, AX
2015-07-10 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-13 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z). Re-cabling dated added for TR 1062. Was to be a reno but reno didn't happen. Going forward with re-cabling the branch.
2015-07-13 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-14 |  | David | Updated cutover dates for 2052, 801596, 800228
2015-07-15 |  | David | Updated cutover dates for 4359 801256, 800870 2940, 800388 1325, 90734
2015-07-15 |  | Brenda | Updated MPLS Install Date (DF) 2052
2015-07-15 |  | Brenda | Updated MPLS Issue/constraint (AJ) 2052, 90734,1639,1047,1187,1548,1768,2098,2477,2737,3198,5857,7268,90762,2217,7928,2607
2015-07-15 |  | Brenda | Update MPLS Completion (AG)90734,1639,1047,1187,1548,1768,2098,2477,2737,3198,5857,7268,90762,2217,7928,2607
2015-07-16 |  | David | Updated cutover date for 800226
2015-07-16 |  | David | Updated tech info column AN
2015-07-17 |  | Marcus | Updated column ''BT''& BU with T3/T35/T65 communications
2015-07-20 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-20 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-07-20 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-20 |  | Violeta | Updated actual communications date T3 for tr#4329,4687,8610,8500,90812
2015-07-21 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-21 |  | Brenda | Updated MPLS Completion Column AG - TR#1957
2015-07-21 |  | Brenda | Updated MPLS Issue/Contraint - TR#3353
2015-07-22 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-24 |  | John | Ran script to update column AV, AW, AX
2015-07-24 |  | Violeta | Updated actual communications date T3 for tr#3362,4330,90571,90601
2015-07-24 |  | Leslie | Updated Change record details for July 13-Aug 7 migrations. Corrected MPLS Required Dates for all branches moved out to 2016. Updated cutover date for RBVPID 800105, TR 354 -- moved to April 2016.
2015-07-24 |  | Leslie | Updated col's DL and DM for PRI/Gateway Inventory feeding Decommissioning process - 125 Rows = Y for PRI, 4 Rows to Review
2015-07-24 |  | Violeta | Updated actual communications date T3 for tr#2960,2979,4960,7947
2015-07-24 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-07-27 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-07-27 |  | Violeta | Updated actual communications date T3 for tr#1062,3680,4922
2015-07-31 |  | Brenda | Updated Column AG - MPLS Completed - TR#527,897,2087,6767,6768,8288,5178,2208,8538
2015-07-31 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-08-04 |  | Violeta | Updated actual communications date T3 for tr#2900,1819,3630
2015-08-06 |  | Linda | 800657_2052 Res to Aug 25
2015-08-06 |  | Violeta | Updated actual communications date T3 for tr#2109,5010,7600,90809
2015-08-07 |  | John | Ran script to update column AV, AW, AX
2015-08-07 |  | Violeta | Updated actual communications date T3 for tr#212,573
2015-08-10 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-08-11 |  | Violeta | Updated actual communications date T3 for tr#787,14143
2015-08-12 |  | Pat | Updated column "AN" with tech information / confirming column "AL" to ensure correct cutover dates
2015-08-17 |  | Violeta | Updated actual communications date T3 for tr#3280,4130,91851,1639,894,90857
2015-08-18 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-08-18 |  | Brenda | Updated column AG and AJ - TR#2052,6247,180,7379,6168,158,1878,3418,4298,5288,8148,8808
|  | Linda | Update Trunk Group info Columns CP & CQ
2015-08-24 |  | Violeta | Updated actual communications date T3 for tr#2539,1730,10776,90734,90862, tr#5029 and tr#1240 delayed
2015-08-24 |  | Brenda | Updated AJ - 90808, 2960, 1240, 5619, 2240
2015-08-24 |  | Brenda | Updated MPLS=Y - 1342
2015-08-24 |  | Brenda | Updated AG - removed date - TR#2960
August |  | Brenda | Updated AG - added dates- 2869, 824, 1874,558,2868,4848,6000, 5838, 7408,2890.
2015-09-01 |  | kathy | Updated AG - 90301, 1050, 3200 Updated AJ - 90541, 5000, 1879, 201 Updated AH 1342
2015-09-01 |  | John | Ran script to update column AV, AW, AX
2015-09-02 |  | Leslie | Cutover Date set to April 1, 2016 for MPLS delays at 1240, 5029. Call Quality risk mitigation for 90853, 90862, and 10776
2015-09-02 |  | Leslie | Updated PRI Gateway = Y for transits 1678 and 1712
2015-09-17 |  | John | Ran script to update column AV, AW, AX
2015-09-28 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-09-29 |  | Brenda | Updated MPLS Completions - TR#90301,2960,5619,2240,2890,90761,3638,4427,549,1288,2560,2997,1325,778,3308,2450
2015-10-02 |  | John | Ran script to update column AV, AW, AX
2015-10-02 |  | Brenda | no updates completed.
2015-10-13 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-10-14 |  | Patricia | Transit 5207 (801435) Added to Master for 2016 migration. Reference: Unable to rescue the migrations in time for the Pilot cutoff of July 31st. Dropped from the Pilot based on a decision from Ernie/John that we could assess our processes with the number of pilot migrations we had from ON, PQ, BC, and AB. MB was declared a risk going into Rollout. Previous cutover date July 24/2014
2015-10-14 |  | Patricia | Transit 9974 (802319) Added to Master for 2016 migration. Reference: Unable to rescue the migrations in time for the Pilot cutoff of July 31st. Dropped from the Pilot based on a decision from Ernie/John that we could assess our processes with the number of pilot migrations we had from ON, PQ, BC, and AB. MB was declared a risk going into Rollout. Previous cutover date July 31/2014
2015-10-15 |  | John | Ran script to update column AV, AW, AX
2015-10-15 |  | Serena | Updated dates and number of phones in Standalone column (Y & Z).
2015-10-28 |  | John | Ran script to update column AV, AW, AX
2015-12-09 |  | John | Ran script to update column AV, AW, AX
2016-02-17 |  | Leslie | Removed all out of scope branches leaving only 203 rows for 2016 - did not move them to Deleted sites tab). Deleted columns not needed. Reordered columns. Corrected MPLS Upgrade status formulas, updated MPLS Upgrade Status details based on Jackie's Feb 16 file (As of Feb 17: 48 upgrades left to complete for the 203 migrations in 2016)
TBD |  | John | ACTION: John Marro to update script for new col location of Speed, VLAN, etc…..
2016-02-18 |  | Leslie | Updated the MPLS Upgrade Target Date (col BV) in the Master for those locations that have a confirmed Circuit Install target date (col BU). For those 16 locations that don’t have a target date for the circuit install, we’ve added a forecast of June for their circuit install date. Jackie and team will continue to push to get the best dates possible.
2016-03-01 |  | Leslie | Update MPLS Circuit Upgrde Target Date and MPLS Upgrade Target Date for TR's 663, 5104, 7703 based on input from Jackie/Brenda.
2016-03-03 |  | Leslie | Updated MPLS Circuit Upgrade Target Date for 1214, 5393. Updated MPLS Upgrade issue description for transits 5029, 6279, 8189, 9249
2016-03-11 |  | Violeta | Updated pre-audit dates for Maritime provinces (Newfoundland, Nova Scotia, New Brunswick and PEI).
2016-03-11 |  | Kris | Updated cutover schedule. Dates confirmed for April & May
ACCEPTABLE SORT RULES -- 1st Level - Cutover Date (Oldest to Newest), 2nd level - Site Address (A-Z), 3rd Level - Branch Category (Z-A putting P&CB at the top for co-habs)
LEGEND
Static Data (manually maintained) COMMENTS must be updated for any changes to a row's data
SIP Avail, Audit, Tech & Cutover Details, Trunk Info (Bell)
Planning Data (RBC)
DID, phone, user, conc call info (Violeta)
Communications & Activity Management Details (RBC)
MPLS Upgrade Schedule Details -- RBC, Brenda
MPLS Status Details - RBC, Leslie
Re-Cabling & Standalone Phone Cabling Schedule Details - RBC/CRE, Serena
TOTAL Line COUNT FOR ADDRESS, Concurrent Call Config for Address -- FILLED IN ON PARENT ROW ONLY!
John Marro columns updated via Automation
Trunk Group Information (Bell)
Post-Migration Activities Tracking - RBC, Analysts
HOWTO USE AUTOMATION
Pre_req
RBVPscript.vbs in Documents folder
SessionList.txt in Documents folder
RBVPscript.txt in Documents folder
Bandwidth validation
Go to this site
https:__spxgroup.rbc.com_wnp0_03688Ja00001288_SitePages_Home.aspx
Under Branch Migration
Migration Schedule Development
Master Schedule
Find the latest Master File Listing and open
Highlight the device names found in column AJ and copy
Paste the device listing into this file
Save this file
Open SecureCRT and select Script then Run and Select the RBVPscript.vbs from your documents folder
This will login to every device, run the necessary commands and log it to the RBVPscript.txt file in your Documents folder
If the script has an error, open the RBVPscript.txt and determine the last site to log data, open the SessionList.txt
and find this site and delete all locations above it. Then restart the script and it will auto append to the file to
continue logging sites.
Once the script is complete, open the master schedule and the RBVPscript.txt in Excel
Select Delimited in Excel and then Next and select Comma as the delimiter.
Create 2 columns beside AU (Device) and then paste this formula in the first created column (AV)
VLOOKUP(AU2,RBVPscript.txt!$A$1:$K$1807,2,FALSE)
Paste this formula in AW
IF(AV2=AX2,1,0)
Select the AW column and then filter on it and exclude 1, only have 0 and #N_A
These are the sites that have either changed in the past week or need manual review. For example, if it shows #N_A it
could be that the bandwidth was upgraded and the device name was changed as dual VPN will change the hostname.
Manually review each of these sites and update the necessary fields, hostnames and Current Service Speed.
The Assigned IPT, Data, Data Other columns can be updated from the same seed file but using the following formulas
IPT VLAN (AX)
VLOOKUP(AU2,RBVPscript.txt!$A$1:$J$1807,4,FALSE)
Data (AZ)
VLOOKUP(AU2,RBVPscript.txt!$A$1:$J$1807,5,FALSE)
Data Other (BA)
VLOOKUP(AU2,RBVPscript.txt!$A$1:$J$1807,6,FALSE)

## Schedule
Branch Category | RBVP ID | SIP Availability Date | Transit | Site Name | Hours of Op Monday | Hours of Op Tuesday | Hours of Op Wednesday | Hours of OP Thursday | Hours of Op Friday | Hours of Op Saturday | Hours of Op Sunday | Site address | Site city | Province | Site postal/zip | Branch Paging Requ | Preaudits due date/ T17/T47 | Branch Audit Due Date | Banch Audit Complete Date | Cutover Date | COMMENTS | RBC ACTIVITY RECORD | All Transits | RBC Analyst | Field Prime | On Site Training | Tech Prime | T35/T65 | T3 Communication | Communication Actual Date T3 | Actual Communication Date T65 | DS Branch Manager | DS Branch Admin | DS BTS | Branch Manager | Branch manager phone | MCC | MCC phone | Region | MMO Name | RMO Name | Centrex incl analog) by location | VOIP by location | Total Lines | Total Phones | Total User Counts | Centrex or VoIP | VM by location | Flag_complete | Concurrent Calls | Multi-Floor Flag | # Transits | Add-Ons per Branch | NPA NXX | OCN of NPANXX/ OCN du IR/NXX | Prov. | Rate Centre/ Circonscription | PSTN CLLI (if known/s'il est connu) | Regulated/Unregulated Réglementé/ Non Réglementé | Trunk Group Number | Trunk Group Name/ID | Non-Emergency Stand Alone Phones Target Date | Non-Emergency Stand Alone Phones Completion Date | Number of Non-Emergency Stand Alone Phones Completed | Re-Cabling Required Y/N | Re-Cabling Target Completion Date | MPLS Upgrade Required? | MPLS upgrade date | MPLS Order Submission Date | MPLS Upgrade Required Date | MPLS Upgrade Issue or Constraint | MPLS Circuit Install Date | MPLS Upgrade Target Date | MPLS Upgrade Status | Cutover Date minus Upgrade Target Date | MPLS Upgrade Requirement/Group | Device | Current Service Speed | Speed Kbps | IPT VLAN | PRI Decom Complete (Date) | 1FL Migrations Complete (Date) | Centrex Out Orders for Migrated # (Bell) (Date) | Centrex Out Orders for Migrated # (Non-Bell) (Date) | Centrex Out Orders (Disconnects) (Date) | Phone Pickup Complete (Date)
P&CB | 800740 | 2016-05-17 | 2374 | MONCTON NORTH BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 1955 MOUNTAIN RD | MONCTON | NEW BRUNSWICK | E1G1A8 |  | 2016-03-14 | 2016-04-11 |  | 2016-04-25 |  |  |  |  | Unisys |  |  | 2016-01-25 | 2016-04-20 | [5 empty] | Joni Dobson | 5068703703 | Isabelle Roussel-Pelletier | 5068703796 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 18 | 2 |  |  | 20 | Centrex |  | done | 9 |  |  |  | 506870 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | 2016-04-20 | 2015-09-03 | 2 | N | N/A | no | [9 empty] | e02374br1 | 5M | 5000 | 10.137.240.1/25
P&CB | 800105 | Yes/Oui | 354 | BRITANNIA & GLEN ERIN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 6040 GLEN ERIN DR | MISSISSAUGA | ONTARIO | L5N3M4 |  | 2016-04-01 | 2016-04-07 |  | 2016-04-26 | Oct 30: MPLS upgrade req'd Changed cutover from Feb 18 to TBD 7/9: RBC advised to move this to April 2016 |  | 354, 8625, 13976, 17211, 17434 |  | Bell Canada |  |  | 2016-03-08 | 2016-04-21 |  | 2015-05-04 |  |  |  | Kinga Kryza | 9055425380 |  |  | GREATER TORONTO REGION | Angela Ramalho | Dawn Adams-Cheung | 24 | 3 |  |  | 27 | Centrex |  | done | 11 | N | 5 |  | 905542 | BELL CANADA - ON | ON | Streetsville | SSVLON39DS0 | (I) Unregulated / Non Réglementé | 9055696342 | streetsville_01_9055696342 | 2016-04-21 | 2015-06-08 | 0 | N | N/A | Yes | 2015-10-09 | 2014-06-13 | 2016-04-21 | Bell - Construction | Done | Done | Complete | Complete | Priority - 50 | c00354br1 | 3M | 3000 | 10.137.95.1/25
DS | 803029 | Yes/Oui | 90301 | SUB OF 1PVM | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 10665 1ERE AVE, SUITE 210 | SAINT GEORGES | QUEBEC | G5Y6X8 |  | 2016-04-04 | 2016-04-13 |  | 2016-04-27 | 3/11/2015 June schedule approved by Bell Oct 28: MPLS upgrade req'd Changed cutover from Jan 29 to TBD david.lu: 7/9: RBC advised to move to April 2016 due to pending MPLS upgrades as per Davids email MPLS upgrade is required. Site on hold with cutover date of Sept 1 as placeholder (LM) |  | 90301 |  | Bell Canada | Remote training approved |  | 2016-03-09 | 2016-04-22 |  | 2015-05-14 | Jérôme Brassard | Teresa Izzo; Caterina Cristiano; Antoinette Chiara; Josée Vallière |  |  | 514-878-7592 |  |  | QUEBEC |  | Sonia Veilleux | 1 | 1 |  |  | 2 | Equal |  | done | 13 | N | 1 |  | 450536 | BELL CANADA - QC | QC | Beloeil | BLOLPQ22RS1 | (W) Unregulated / Non Réglementé | 450-536-2015 | beloeil_01_4505362015 | 2016-04-22 | 2015-07-10 | 1 | Y | 2015-07-10 | Yes | 2015-09-09 | 2015-07-03 | 2016-04-22 | Completed |  |  | Complete | Complete | Priority - 50 | e90301vr1 | 5M | 5000 | 10.138.127.1/25
P&CB | 801576 | 2016-05-17 | 6113 | HERRING COVE ROAD BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 339 HERRING COVE RD | HALIFAX | NOVA SCOTIA | B3R1V5 |  | 2016-04-12 | 2016-05-10 |  | 2016-05-24 |  |  | 00000, 1506, 4039, 5783, 6113, 8708, 9593, 9883, 15686 |  | Unisys |  |  | 2016-02-23 | 2016-05-19 | [5 empty] | Darlene Croscup | 9024218973 | Dina Spillner | 9024214666 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 22 | 4 |  |  | 26 | Centrex |  | done | 11 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-05-19 | 2014-12-07 | 1 | N | N/A | no | [9 empty] | e06113br1 | 5M | 5000 | 10.136.49.129/25
P&CB | 800597 | 2016-05-17 | 1764 | RICHIBUCTO BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 9393 MAIN ST | RICHIBUCTO | NEW BRUNSWICK | E4W4B6 |  | 2016-04-13 | 2016-05-11 |  | 2016-05-25 |  |  | 00000, 1764, 14582 |  | Unisys |  |  | 2016-02-24 | 2016-05-20 | [5 empty] | Kelly Dunn | 5065234789 | Vicky Leblanc | 5065234788 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 17 | 2 |  |  | 19 | Centrex |  | done | 9 |  |  |  | 506523 | ALIANT TELECOM (NB) | NB | Richibucto | RBTONBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-05-20 | 2015-08-14 | 2 | N | N/A | Yes |  | Done | 2016-05-20 | Bell | 2016-04-14 | 2016-04-28 | OK | 27 | 2016-03-31 | e01764br1 | DSL | 1500 | 10.138.60.129/25
P&CB | 800604 | 2016-05-17 | 1784 | PINE GLEN MALL BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 121 PINE GLEN RD | RIVERVIEW | NEW BRUNSWICK | E1B1V5 |  | 2016-04-14 | 2016-05-12 |  | 2016-05-26 |  |  | 00000, 1426, 1784, 10108 |  | Unisys |  |  | 2016-02-25 | 2016-05-23 | [5 empty] | Deborah Bayliss | 5068564830 | Tracey Stack | 5068567310 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 16 | 2 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 506870 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | 2016-05-21 | 2015-07-20 | 1 | Y | 2014-03-09 | Yes |  | Done | 2016-05-21 | Bell | 2016-03-24 | 2016-04-07 | OK | 49 | 2016-03-31 | e01784br1 | DSL | 1500 | 10.138.61.1/25
P&CB | 800638 | 2016-05-17 | 1943 | TACOMA CENTRE | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 40 TACOMA DR | DARTMOUTH | NOVA SCOTIA | B2W6E2 |  | 2016-04-14 | 2016-05-12 |  | 2016-05-26 |  |  | 00000, 1506, 1943, 2923, 4039, 5783, 9593, 9883, 9943, 12056, 15977, 17165 |  | Unisys |  |  | 2016-02-25 | 2016-05-23 | [5 empty] | Angela Gloade | 9024218875 | Stuart Greer | 9024218105 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 8 | 3 |  |  | 11 | Centrex |  | done | 6 |  | 12 |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e01943br1 | 5M | 5000 | 10.136.165.1/25
P&CB | 801061 | 2016-05-17 | 3653 | LOWER SACKVILLE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 790 SACKVILLE DR. | LOWER SACKVILLE | NOVA SCOTIA | B4E1R7 |  | 2016-04-18 | 2016-05-16 |  | 2016-05-30 |  |  | 1506, 3653, 6404, 4943, 12056 |  | Unisys |  |  | 2016-02-29 | 2016-05-25 | [5 empty] | Jon Bauld | 9028693065 | Roxanna Riley | 9028692902 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 15 | 1 |  |  | 16 | Centrex |  | done | 8 |  |  |  | 902869 | ALIANT TELECOM (NS) | NS | Sackville | SKVLNS01RS3 | Unregulated / Non Réglementé | 0 | 0 | 2016-05-25 | 2014-12-10 | 3 | N | N/A | no | [9 empty] | e03653br1 | 5M | 5000 | 10.136.36.1/25
P&CB | 802060 | 2016-05-17 | 9003 | PARADISE BANKING CTR | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 1314 TOPSAIL RD | PARADISE | NEWFOUNDLAND | A1L1N9 |  | 2016-04-18 | 2016-05-16 |  | 2016-05-30 |  |  | 8133, 8963, 9003, 9063, 9275, 9353 |  | Unisys |  |  | 2016-02-29 | 2016-05-25 | [5 empty] | Stephen Dawson | 7097825680 | Glenda Gosse | 7097825682 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 709782 | ALIANT TELECOM (NF) | NL | St John's | MTPRNF01DS1 | Regulated / Réglementé | 0 | 0 | 2016-05-25 | 2015-08-25 | 0 | N | N/A | no | [9 empty] | e09003br1 | T1 | 1500 | 10.137.216.1/25
P&CB | 800064 | 2016-05-17 | 224 | BOUCTOUCHE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 15 IRVING BLVD | BOUCTOUCHE | NEW BRUNSWICK | E4S3J4 |  | 2016-04-19 | 2016-05-17 |  | 2016-05-31 |  |  |  |  | Unisys |  |  | 2016-03-01 | 2016-05-26 | [5 empty] | Kevin Elsliger | 5067431831 | Mona Collette | 5067431828 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  |  |  | 506743 | ALIANT TELECOM (NB) | NB | Bouctouche | BTCHNBSCRS0 | Unregulated / Non Réglementé | Need PTN | 0 | 2016-05-26 | 2015-06-18 | 1 | Y | 2014-02-16 | Yes | 2015-06-18 | Sent | 2015-08-01 | Completed | 2015-06-01 |  | Complete | Complete | Aug 1 - per Adam | e00224br1 | T1 | 1500 | 10.138.53.129/25
P&CB | 801408 | 2016-05-17 | 5064 | 335 UNIVERSITY AVE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 335 UNIVERSITY AVE | CHARLOTTETOWN | PRINCE EDWARD ISLAND | C1A4M6 |  | 2016-04-19 | 2016-05-17 |  | 2016-05-31 |  |  | 00000, 5064, 7484, 8024 |  | Unisys |  |  | 2016-03-01 | 2016-05-26 | [5 empty] | Kaye Kelly | 9026297486 | Bonnie Garnhum | 9026289154 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 23 | 4 |  |  | 27 | Centrex |  | done | 11 |  |  |  | 902436 | ALIANT TELECOM (PEI) | PE | Summerside | SMSDPE01RS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-05-26 | 2015-07-20 | 1 | N | N/A | no | [9 empty] | e05064br1 | 3M | 3000 | 10.137.0.129/25
P&CB | 800102 | 2016-05-17 | 334 | CAMPBELLTON BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 161 ROSEBERRY ST | CAMPBELLTON | NEW BRUNSWICK | E3N2H2 |  | 2016-04-20 | 2016-05-18 |  | 2016-06-01 |  |  |  |  | Unisys |  |  | 2016-03-02 | 2016-05-27 | [5 empty] | Lise Savoie | 5067891671 | Shelley Arseneault | 5067891658 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 25 | 2 |  |  | 27 | Centrex |  | done | 11 |  |  |  | 506789 | ALIANT TELECOM (NB) | NB | Campbellton | CMTNNBSCRS0 | Unregulated / Non Réglementé | Need PTN | 0 | 2016-05-27 | 2014-09-25 | 1 | Y | 2014-09-05 | no | [9 empty] | e00334br1 | 5M | 5000 | 10.137.18.1/25
P&CB | 800162 | 2016-05-17 | 553 | BADDECK BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 496 CHEBUCTO ST | BADDECK | NOVA SCOTIA | B0E1B0 |  | 2016-04-20 | 2016-05-18 |  | 2016-06-01 |  |  | 553, 9843 |  | Unisys |  |  | 2016-03-02 | 2016-05-27 | [5 empty] | Leanne Mackinnon | 9022955500 |  |  | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  |  |  | 902295 | ALIANT TELECOM (NS) | NS | Baddeck | BDDKNS01RS1 | Regulated / Réglementé | Need PTN | 0 | 2016-05-27 | 2015-07-13 | 3 | Y | 2014-12-17 | no | [9 empty] | e00553br1 | T1 | 1500 | 10.136.157.129/25
P&CB | 800151 | 2016-05-17 | 514 | ST JOHN'S ABERDEEN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 40 ABERDEEN AVE. | ST JOHN'S | NEWFOUNDLAND | A1A5T3 |  | 2016-04-21 | 2016-05-19 |  | 2016-06-02 |  |  | 00000, 514, 9275, 14583 |  | Unisys |  |  | 2016-03-03 | 2016-05-30 | [5 empty] | Nick Peddle | 7095764712 | Kathleen Waterman | 7095764769 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  |  |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-05-28 | 2015-08-19 | 1 | N | N/A | no | [9 empty] | e00514br1 | T1 | 1500 | 10.136.157.1/25
P&CB | 800305 | 2016-05-17 | 1103 | BRIDGETOWN BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 3 QUEEN ST | BRIDGETOWN | NOVA SCOTIA | B0S1C0 |  | 2016-04-21 | 2016-05-19 |  | 2016-06-02 |  |  | 00000, 1103 |  | Unisys |  |  | 2016-03-03 | 2016-05-30 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 10 | 1 |  |  | 11 | Centrex |  | done | 6 |  |  |  | 902665 | ALIANT TELECOM (NS) | NS | Bridgetown | BRTWNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-05-28 | 2015-07-17 | 2 | N | N/A | Yes |  | Done | 2016-05-28 | Bell | 2016-03-08 | 2016-03-27 | OK | 67 | 2016-03-31 | e01103br1 | DSL | 1500 | 10.138.57.129/25
P&CB | 800050 | Yes/Oui | 180 | BRIDLEWOOD SHOPPING CENTRE | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 |  | 16919 24TH ST SW | CALGARY | ALBERTA | T2Y0J3 |  | 2016-03-31 | 2016-04-11 |  | 2016-06-06 | June and Elaine advised MPLS upgrade req'd Cutover res fr Feb 5 to TBD |  | 180, 1218, 9329, 10449, 10450, 13482, 14256, 17182 |  | Bell Canada |  |  | 2016-03-07 | 2016-06-01 | [5 empty] | Christina McKay | 4032994554 |  |  | ALBERTA & TERRITORIES | Odell Sinclair | Dan Chipak | 15 | 2 |  |  | 17 | Centrex |  | done | 8 |  | 8 |  | 403509 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-06-01 | 2014-07-07 | 2 | N | N/A | Yes | 2015-08-11 | 2014-05-05 | 2016-06-01 | Completed | 2015-07-23 |  | Complete | Complete | July 30 - 24 AB | w00180br1 | 5M | 5000 | 10.136.53.1/25
P&CB | 800678 | 2016-05-17 | 2105 | KELSEY DRIVE | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 61 KELSEY DR | ST JOHN'S | NEWFOUNDLAND | A1B5C8 |  | 2016-04-25 | 2016-05-23 |  | 2016-06-06 |  |  | 2105, 14583, 2105, 9063, 14583 |  | Unisys |  |  | 2016-03-07 | 2016-06-01 | [7 empty] | Nicholle Vicars | 7097588340 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 6 | 22 |  |  | 28 | IP |  | done | 12 |  |  |  | 709738 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e02105br1 | 5M | 5000 | 10.32.134.1/25 | Y
P&CB | 800787 | 2016-05-17 | 2533 | HALIFAX NS ALMON ST BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 5805 ALMON ST | HALIFAX | NOVA SCOTIA | B3K1T7 |  | 2016-04-25 | 2016-05-23 |  | 2016-06-06 |  |  | 1506, 2533, 7666, 9593, , 12056, 17785 |  | Unisys |  |  | 2016-03-07 | 2016-06-01 | [5 empty] | Debbie Fader | 9024214396 | Ryrie Vandewater | 9024214076 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 27 | 4 |  |  | 31 | Centrex |  | done | 13 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-01 | 2015-05-05 | 3 | N | N/A | Yes | 2015-06-25 | 2015-04-21 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - per Adam | e02533br1 | T1 | 1500 | 10.136.47.1/25
DS | 803024 | 2016-05-17 | 90282 | INC-ST JOHN NEW BR | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 44 CHIPMAN HILL | SAINT JOHN | NEW BRUNSWICK | E2L2A9 |  | 2016-04-25 | 2016-05-23 |  | 2016-06-06 |  |  | 00000, 90277, 90282 |  | Unisys |  |  | 2016-03-07 | 2016-06-01 |  |  | Tom Gribbons | Clayton Mitchell | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 32 | 6 |  |  | 38 | Centrex |  | done | 19 |  | 3 |  | 506433 | ALIANT TELECOM (NB) | NB | Sussex | SUSXNBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-01 | 2015-08-13 | 1 | N | N/A | no | [9 empty] | e90282vr1 | 5M | 5000 | 10.138.96.129/25
P&CB | 800163 | 2016-05-17 | 554 | DALHOUSIE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 388 WILLIAM ST | DALHOUSIE | NEW BRUNSWICK | E8C2X2 |  | 2016-04-26 | 2016-05-24 |  | 2016-06-07 |  |  | 00000, 554, 14582 |  | Unisys |  |  | 2016-03-08 | 2016-06-02 | [5 empty] | Michel Diotte | 5066841829 | Cindy Fecteau | 5066841831 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  |  |  | 506684 | ALIANT TELECOM (NB) | NB | Dalhousie | DLHSNBSCRS0 | Unregulated / Non Réglementé | Need PTN | 0 | 2016-06-02 | 2014-11-15 | 1 | Y | 2014-09-26 | no | [9 empty] | e00554br1 | T1 | 1500 | 10.136.158.1/25
P&CB | 800839 | Yes/Oui | 2820 | LADYSMITH BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 527 FIRST AVE | LADYSMITH | BRITISH COLUMBIA | V9G1A7 |  | 2016-04-04 | 2016-04-12 |  | 2016-06-07 | 1/18/2015: Sip Avail Nov 18 2014 |  | 2820, 4301, 13057 |  | Bell Canada |  |  | 2016-03-08 | 2016-06-02 | [5 empty] | Allison Brind | 2502456016 | Heather Pierce | 2502456000 | BRITISH COLUMBIA | Heather Marshak | Timothy Carmack | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  | 3 |  | 250245 | TELUS | BC | Ladysmith | LDYSBC01RS1 | (I) Regulated / Réglementé | 0 | 0 | 2016-06-02 | 2015-04-16 | 2 | N | N/A | Yes | 2015-12-03 | 2015-06-26 | 2016-06-02 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w02820br1 | 5M | 5000 | 10.136.9.1/25
P&CB | 801407 | 2016-05-17 | 5063 | NEW GLASGOW BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 91 PROVOST ST | NEW GLASGOW | NOVA SCOTIA | B2H2P5 |  | 2016-04-26 | 2016-05-24 |  | 2016-06-07 |  |  | 5063, 14188, 14535, 16665 |  | Unisys |  |  | 2016-03-08 | 2016-06-02 | [5 empty] | Melanie Beck | 9027557707 | Chanda Harder | 9027557712 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 20 | 1 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 902755 | ALIANT TELECOM (NS) | NS | New Glasgow | NWGLNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-02 | 2014-08-29 | 2 | Y | 2014-07-21 | Yes | 2015-05-05 | 2015-02-18 | 2016-03-31 | Bell - pending |  |  | Complete | Complete | 2016-03-31 | e05063br1 | 3M | 3000 | 10.138.70.129/25
P&CB | 802079 | 2016-05-17 | 9103 | CORNER BROOK BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 66 WEST ST | CORNER BROOK | NEWFOUNDLAND | A2H2Z3 |  | 2016-04-26 | 2016-05-24 |  | 2016-06-07 |  |  | 123, 8133, 9063, 9103, 9275, 13937 |  | Unisys |  |  | 2016-03-08 | 2016-06-02 | [7 empty] | Stephanie Hedderson | 7096394003 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 20 | 1 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 709639 | ALIANT TELECOM (NF) | NL | Corner Brook | CRBKNF02DS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-02 | 2015-05-02 | 1 | N | N/A | no | [9 empty] | e09103br1 | 5M | 5000 | 10.137.39.129/25
P&CB | 800063 | 2016-05-17 | 223 | ANNAPOLIS ROYAL BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 248 ST GEORGE ST | ANNAPOLIS ROYAL | NOVA SCOTIA | B0S1A0 |  | 2016-04-27 | 2016-05-25 |  | 2016-06-08 |  |  | 00000, 233 |  | Unisys |  |  | 2016-03-09 | 2016-06-03 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  |  |  | 902532 | ALIANT TELECOM (NS) | NS | Annapolis Royal | ANRLNS01RS1 | Regulated / Réglementé | Need PTN | 0 | 2016-06-03 | 2014-11-19 | 1 | Y | 2014-07-27 | Yes |  | Done | 2016-06-03 | Bell | 2016-04-08 | 2016-04-22 | OK | 47 | 2016-03-31 | e00223br1 | DSL | 1500 | 10.138.53.1/25
P&CB | 800233 | 2016-05-17 | 824 | BROOKSIDE MALL BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 435 BROOKSIDE DR | FREDERICTON | NEW BRUNSWICK | E3A8V4 |  | 2016-04-27 | 2016-05-25 |  | 2016-06-08 |  |  | 00000, 824, 934, 1524, 8014, 9404, 14582, 15997 |  | Unisys |  |  | 2016-03-09 | 2016-06-03 | [5 empty] | Samantha Bosca | 5064502317 | Jenna Rattie | 5064502309 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 20 | 3 |  |  | 23 | Centrex |  | done | 10 |  | 8 |  | 506450 | ALIANT TELECOM (NB) | NB | Fredericton | FCTNNBSC45C | Unregulated / Non Réglementé | 0 | 0 | 2016-06-03 | 2015-08-04 | 3 | N | N/A | Yes | 2015-08-18 | 2015-04-20 | 2015-08-01 | Completed | 2015-06-02 |  | Complete | Complete | Aug 1 - per Adam | e00824br1 | T1 | 1500 | 10.138.55.129/25
P&CB | 800376 | Yes/Oui | 1288 | BEAUMONT BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 6304 50TH STREET | BEAUMOUNT | ALBERTA | T4X0B6 |  | 2016-04-04 | 2016-04-13 |  | 2016-06-08 | 1/18/2015: Sip avial Nov 3 2014 |  | 1288, 1489, 8749, 10453, 16394 |  | Bell Canada |  |  | 2016-03-09 | 2016-06-03 | [5 empty] | Amanda Cleaves | 7809297917 | Tracey Sheppard | 7809297909 | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 19 |  |  |  | 19 | Centrex |  | done | 9 |  | 5 |  | 780929 | TELUS | AB | Beaumont | BUMTAB01RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-06-03 | 2015-07-07 | 2 | N | N/A | Yes | 2015-08-24 | 2015-04-21 | 2016-06-03 | Completed |  |  | Complete | Complete | July 30 - 24 AB | w01288br1 | 5M | 5000 | 10.136.235.129/25
P&CB | 800606 | 2016-05-17 | 1793 | BURNSIDE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 202 BROWNLOW AVE-STE 100-CAMBR | DARTMOUTH | NOVA SCOTIA | B3B1T5 |  | 2016-04-27 | 2016-05-25 |  | 2016-06-08 |  |  | 00000, 1506, 1793, 4039, 9393, 9883, 12056, 14912, 14913 |  | Unisys |  |  | 2016-03-09 | 2016-06-03 | [5 empty] | Jim Hall | 9024214254 | Elena Lalabekova | 9024214277 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 27 | 7 |  |  | 34 | Centrex |  | done | 13 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-03 | 2014-12-17 | 1 | N | N/A | no | [9 empty] | e01793br1 | 5M | 5000 | 10.137.24.129/25
P&CB | 800252 | 2016-05-17 | 884 | FREDERICTON MAIN BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 504 QUEEN ST | FREDERICTON | NEW BRUNSWICK | E3B5G1 |  | 2016-04-28 | 2016-05-26 |  | 2016-06-09 |  |  | 00000, 884, 934, 4435, 8014, 9404, 10108, 14186 |  | Unisys |  |  | 2016-03-10 | 2016-06-06 | [5 empty] | Kelly Sutton | 5064506211 | Nancy Dunfield | 5064502375 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 36 | 4 |  |  | 40 | Centrex |  | done | 15 |  |  |  | 506450 | ALIANT TELECOM (NB) | NB | Fredericton | FCTNNBSC45C | Unregulated / Non Réglementé | 0 | 0 | 2016-06-04 | 2015-08-10 | 2 | N | N/A | no | [9 empty] | e00884br1 | 5M | 5000 | 10.137.21.1/25
P&CB | 800290 | Yes/Oui | 1050 | SEVENOAKS SHOPPING CENTRE BRANCH | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | Closed | 32900 SOUTH FRASER WAY | ABBOTSFORD | BRITISH COLUMBIA | V2S5A1 |  | 2016-04-06 | 2016-04-14 |  | 2016-06-09 |  |  | 1050, 3316, 12069, 14971 |  | Bell Canada |  |  | 2016-03-10 | 2016-06-06 | [5 empty] | Shirley Wallace | 6048703161 | Els Thune | 6048703178 | BRITISH COLUMBIA | Michele Curley | Timothy Carmack | 32 | 3 |  |  | 35 | Centrex |  | done | 14 |  | 4 |  | 604870 | TELUS | BC | Abbotsford | ABFDBC01DS3 | (I) Unregulated / Non Réglementé | 604-755-1008 | abbotsford_01_6047551008 | 2016-06-04 | 2015-01-15 | 4 | N | N/A | Yes | 2015-10-23 | 2014-05-05 | 2016-06-04 | Pending Circuit Installation |  |  | Complete | Complete | Aug 1 - 27 BC | w01050br1 | 5M | 5000 | 10.136.58.1/25
P&CB | 801333 | 2016-05-17 | 4623 | MIDDLE MUSQUODOBOIT BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | Closed | Closed | 12332 HIGHWAY 224 | MIDDLE MUSQUODOBOIT | NOVA SCOTIA | B0N1X0 |  | 2016-04-28 | 2016-05-26 |  | 2016-06-09 |  |  | 00000, 4623 |  | Unisys |  |  | 2016-03-10 | 2016-06-06 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 7 | 1 |  |  | 8 | Centrex |  | done | 5 |  |  |  | 902384 | ALIANT TELECOM (NS) | NS | Musquodoboit | MDMTNS02RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-04 | 2015-05-01 | 3 | N | N/A | Yes |  | Done | 2016-06-04 | Bell | 2016-03-29 | 2016-04-12 | OK | 58 | 2016-03-31 | e04623br1 | DSL | 1500 | 10.136.172.129/25
DS | 803022 | 2016-05-17 | 90275 | RBC INVESTMENTS | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 10 FORT WILLIAM PL-SUITE 803 | ST JOHNS | NEWFOUNDLAND | A1C5P9 |  | 2016-04-28 | 2016-05-26 |  | 2016-06-09 |  |  | 00000, 90275 |  | Unisys |  |  | 2016-03-10 | 2016-06-06 |  |  | Gary Corcoran | Pauline Halliday | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 15 | 3 |  |  | 18 | Centrex |  | done | 11 |  | 2 |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-06-04 | 2015-08-25 | 0 | N | N/A | no | [9 empty] | e90275vr1 | 5M | 5000 | 10.137.58.1/25
P&CB | 800026 | 2016-05-17 | 113 | AMHERST BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 103 VICTORIA ST E | AMHERST | NOVA SCOTIA | B4H1X9 |  | 2016-05-02 | 2016-05-30 |  | 2016-06-13 |  |  | 00000, 113, 9262, 16665 |  | Unisys |  |  | 2016-03-14 | 2016-06-08 | [5 empty] | Sarah Boss | 9026675471 | Tammy Gagnon | 9026676393 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 21 | 2 |  |  | 23 | Centrex |  | done | 10 |  | 4 |  | 902667 | ALIANT TELECOM (NS) | NS | Amherst | AMHRNS01RS2 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-08 | 2014-10-20 | 2 | N | N/A | no | [9 empty] | e00113br1 | T1 | 1500 | 10.136.104.1/25
P&CB | 800027 | 2016-05-17 | 114 | BATHURST BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 230 MAIN ST | BATHURST | NEW BRUNSWICK | E2A1A8 |  | 2016-05-02 | 2016-05-30 |  | 2016-06-13 |  |  | 00000, 114, 1426, 1781, 7474, 8014, 9314, 10108, 14446, 14582 |  | Unisys |  |  | 2016-03-14 | 2016-06-08 | [5 empty] | Heather Manning | 5065471042 | Barbara Roy | 5065471041 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 35 | 9 |  |  | 44 | Centrex |  | done | 16 |  |  |  | 506547 | ALIANT TELECOM (NB) | NB | Bathurst | BTSTNBSC54C | Unregulated / Non Réglementé | 0 | 0 | 2016-06-08 | 2015-08-12 | 5 | N | N/A | no | [9 empty] | e00114br1 | 5M | 5000 | 10.137.17.129/25
P&CB | 800908 | Yes/Oui | 3089 | CARDSTON BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | Closed | Closed | 204 MAIN ST | CARDSTON | ALBERTA | T0K0K0 |  | 2016-04-07 | 2016-04-18 |  | 2016-06-13 |  |  | 00000, 1625, 3089, 7379, 8589, 9893, 9955, 13994 |  | Unisys |  |  | 2016-03-14 | 2016-06-08 | [5 empty] | Sharon | 0 |  |  | ALBERTA & TERRITORIES | Odell Sinclair | Dan Chipak | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  | 8 |  | 403653 | TELUS | AB | Cardston | CSTNAB01RS2 | Regulated / Réglementé | 0 | 0 | 2016-06-08 | 2014-12-01 | 1 | Y | 2014-11-23 | no | [9 empty] | w03089br1 | T1 | 1500 | 10.136.197.1/25
P&CB | 801214 | Yes/Oui | 4240 | 3RD AVENUE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 2925 3RD AVE | PORT ALBERNI | BRITISH COLUMBIA | V9Y2A6 |  | 2016-04-08 | 2016-04-18 |  | 2016-06-13 |  |  | 00000, 4240, 8890, 13056, 13057, 15041 |  | Bell Canada |  |  | 2016-03-14 | 2016-06-08 | [7 empty] | Alicia Kent | 2507202955 | BRITISH COLUMBIA | Heather Marshak | Timothy Carmack | 24 | 3 |  |  | 27 | Centrex |  | done | 11 |  | 6 |  | 250720 | TELUS | BC | Port Alberni | PTAIBC01DS1 | (C) Regulated / Réglementé | 0 | 0 | 2016-06-08 |  |  | N | N/A | Yes | 2015-05-06 | 2014-08-26 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w04240br1 | 5M | 5000 | 10.136.1.1/25
DS | 803021 | 2016-05-17 | 90270 |  | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 296 MAIN ST | YARMOUTH | NOVA SCOTIA | B5A1E4 |  | 2016-05-02 | 2016-05-30 |  | 2016-06-13 |  |  | 00000, 960, 3316, 9963, 9967, 14829, 14971, 16953, 90270, 90808 |  | Unisys |  |  | 2016-03-14 | 2016-06-08 |  |  | Stewart Robinson | Emily Hynes; Barbara Alward | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 5 | 5 |  |  | 10 | Equal |  | done | 8 |  | 10 |  | 902893 | ALIANT TELECOM (NS) | NS | Truro | HLFXNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-08 | 2014-12-18 | 2 | N | N/A | no | [9 empty] | e90270vr6 | 5M | 5000 | 10.32.4.65/26
P&CB | 800251 | 2016-05-17 | 883 | BEDFORD BR | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 1597 BEDFORD HWY | BEDFORD | NOVA SCOTIA | B4A1E7 |  | 2016-05-03 | 2016-05-31 |  | 2016-06-14 |  |  |  |  | Unisys |  |  | 2016-03-15 | 2016-06-09 | [5 empty] | Rachel Stone | 9024217418 | Myra Lucia | 9024217425 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 37 | 5 |  |  | 42 | Centrex |  | done | 16 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-09 | 2014-11-19 | 5 | N | N/A | no | [9 empty] | e00883br1 | 5M | 5000 | 10.137.20.129/25
P&CB | 800306 | 2016-05-17 | 1104 | GRAND FALLS BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 305 BROADWAY BLVD | GRAND FALLS | NEW BRUNSWICK | E3Z2K3 |  | 2016-05-03 | 2016-05-31 |  | 2016-06-14 |  |  | 00000, 1104, 8014, 9404, 14186 |  | Unisys |  |  | 2016-03-15 | 2016-06-09 | [5 empty] | Carole Mulherin | 5064739740 | Pierre Bellefleur | 5064739757 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 23 | 1 |  |  | 24 | Centrex |  | done | 10 |  |  |  | 506473 | ALIANT TELECOM (NB) | NB | Grand Falls | GDFLNBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-09 | 2015-08-13 | 2 | N | N/A | no | [9 empty] | e01104br1 | 5M | 5000 | 10.138.13.1/25
P&CB | 800333 | 2016-05-17 | 1213 | BRIDGEWATER BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 565 KING ST | BRIDGEWATER | NOVA SCOTIA | B4V1B3 |  | 2016-05-03 | 2016-05-31 |  | 2016-06-14 |  |  | 00000, 1213, 4953, 9274, 9843, 14535, 14913, 15977, 90270 |  | Unisys |  |  | 2016-03-15 | 2016-06-09 | [7 empty] | Missy Swinimer-Romkey | 9025438372 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 26 | 3 |  |  | 29 | Centrex |  | done | 12 |  |  |  | 902543 | ALIANT TELECOM (NS) | NS | Bridgewater | BRWRNS02RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-09 | 2014-12-06 | 5 | N | N/A | no | [9 empty] | e01213br1 | 5M | 5000 | 10.137.22.129/25
P&CB | 801351 | 2016-05-17 | 4733 | MIDDLETON BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 6 COMMERCIAL ST | MIDDLETON | NOVA SCOTIA | B0S1P0 |  | 2016-05-03 | 2016-05-31 |  | 2016-06-14 |  |  | 00000, 993, 4733, 9903, 14535 |  | Unisys |  |  | 2016-03-15 | 2016-06-09 | [5 empty] | Brent Mcneil | 9028254474 | Erica Gates | 9028255753 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 18 | 3 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 902825 | ALIANT TELECOM (NS) | NS | Middleton | MDANNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-09 | 2014-12-16 | 2 | N | N/A | no | [9 empty] | e04733br1 | T1 | 1500 | 10.136.173.129/25
P&CB | 802049 | Yes/Oui | 8919 | STETTLER BRANCH | 17:00 | 17:00 | 17:00 | 19:00 | 17:00 | closed | Closed | 4920 51ST ST | STETTLER | ALBERTA | T0C2L0 |  | 2016-04-08 | 2016-04-19 |  | 2016-06-14 | 1/18/2015: Sip Avail Nov 18 2014 |  | 00000, 8749, 8919, 9878, 9882, 9955, 13998, 14578, 16376 |  | Unisys |  |  | 2016-03-15 | 2016-06-09 | [5 empty] | Valerie Odell | 4037429269 | Janet Boice | 4037429255 | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 24 | 3 |  |  | 27 | Centrex |  | done | 11 |  | 9 |  | 403742 | TELUS | AB | Stettler | STLRAB01RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-06-09 | 2015-05-23 | 2 | Y | 2015-02-02 | Yes | 2016-01-25 | 2015-04-21 | 2016-06-09 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w08919br1 | DSL | 1500 | 10.136.6.129/25
DS | 803156 | Yes/Oui | 90853 | DOMINION SECURITIES - SIDNEY BC | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 2491 BEVAN AVENUE | SIDNEY | BRITISH COLUMBIA | V8L1W2 |  | 2016-04-11 | 2016-04-19 |  | 2016-06-14 | david.lu: 6/24: moved back into schedule as per Leslie's request 6/8: moved to TBD as per Linda's 1pm call - pending MPLS upgrade Call quality risk mitigation, move to 2016 |  | 90853 |  | Bell Canada | 2016-04-02 | Anthony Yaseyko @ 250-220-3312 | 2016-03-15 | 2016-06-09 |  | 2015-06-26 | Dwane Ford | Sharon Stewart | [5 empty] | BRITISH COLUMBIA |  |  | 13 | 1 |  |  | 14 | Centrex |  | done | 10 | N | 1 |  | 250655 | TELUS | BC | Saanich | SDNYBC01DS1 | (W) Unregulated / Non Réglementé | 250-665-7989 | saanich_01_2506657989 | 2016-06-09 | 2015-03-25 | 1 | N | N/A | Yes | 2015-03-25 | 2014-09-24 | 2015-08-01 |  |  |  | Complete | Complete | Aug 1 - 27 BC | w90853vr1 | 5M | 5000 | 10.136.221.1/25
P&CB | 800388 | Yes/Oui | 1325 | CHESTERMERE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 196 CHESTERMERE STATION WAY | CALGARY | ALBERTA | T2P1C9 |  | 2016-04-11 | 2016-04-20 |  | 2016-06-15 | david.lu: 7/15: moved to 2016 7/9: pending MPLS due date - moved to Sep 1st as placeholder tentatively |  | 1325, 9955, 10448, 10450, 14548, 15986 |  | Bell Canada |  | Adam Maucieri @ 403-829-5373 | 2016-03-16 | 2016-06-10 |  | 2015-04-20 |  |  |  | Mellissa Dang | 4032045174 | Ramanpreet Sidhu | 4032045169 | ALBERTA & TERRITORIES | Blair Munholland | Dan Chipak | 17 | 0 |  |  | 17 | IP |  | done | 8 | N | 6 |  | 403204 | TELUS | AB | Calgary | CLGRAB10DS0 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-06-10 | 2015-04-05 | 2 | N | N/A | Yes | 2015-09-24 | 2015-02-19 | 2016-06-10 | Completed | 2015-09-03 |  | Complete | Complete | Priority - 50 | w01325br1 | 3M | 3000 | 10.137.220.129/25
P&CB | 800445 | Yes/Oui | 1440 | CRESTON BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 1008 CANYON ST | CRESTON | BRITISH COLUMBIA | V0B1G0 |  | 2016-04-12 | 2016-04-20 |  | 2016-06-15 | 1/18/2015: Sip Avail Nov 18 2014 |  | 1440, 7700, 8820 |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [5 empty] | Julie Chiste | 2504026822 | Lorelei Makeiv | 2504026816 | BRITISH COLUMBIA | Dana McCombie | Timothy Carmack | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  | 3 |  | 250428 | TELUS | BC | Creston | CETNBC01RS1 | (I) Regulated / Réglementé | 0 | 0 | 2016-06-10 | 2015-04-22 | 2 | Y | 2015-02-27 | Yes | 2015-04-22 | 2014-08-25 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w01440br1 | 5M | 5000 | 10.136.4.1/25
P&CB | 801381 | 2016-05-17 | 4953 | NEW GERMANY BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 5253 HIGHWAY 10 | NEW GERMANY | NOVA SCOTIA | B0R1E0 |  | 2016-05-04 | 2016-06-01 |  | 2016-06-15 |  |  |  |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 10 | 1 |  |  | 11 | Centrex |  | done | 6 |  |  |  | 902644 | ALIANT TELECOM (NS) | NS | New Germany | NWGRNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-10 | 2015-05-06 | 1 | Y | 2014-09-27 | Yes |  | done | 2016-06-10 | Bell | 2016-04-11 | 2016-04-25 | OK | 51 | 2016-03-31 | e04953br1 | DSL | 1500 | 10.138.70.1/25
P&CB | 801417 | 2016-05-17 | 5103 | NEW MINAS BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 20:00 | closed | Closed | 9256 COMMERCIAL ST | NEW MINAS | NOVA SCOTIA | B4N4A9 |  | 2016-05-04 | 2016-06-01 |  | 2016-06-15 |  |  | 00000, 5103 |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [5 empty] | Shelley O'Donnel- Johnston | 9026818707 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 18 | 2 |  |  | 20 | Centrex |  | done | 9 |  |  |  | 902681 | ALIANT TELECOM (NS) | NS | Kentville | BDFRNS02CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-10 | 2015-04-30 | 2 | N | N/A | Yes |  | Done | 2016-06-10 | Bell | 2016-03-11 | 2016-03-27 | OK | 80 | 2016-03-31 | e05103br1 | DSL | 1500 | 10.138.71.1/25
P&CB | 801634 | 2016-05-17 | 6603 | CHARLOTTE STREET BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 404 CHARLOTTE ST | SYDNEY | NOVA SCOTIA | B1P1E2 |  | 2016-05-04 | 2016-06-01 |  | 2016-06-15 | DS 90270 one employee 404 Charlotte St Sydney BC |  | 00000, 6404, 6603, 9076, 9473, 9593, 9843, 9883. 14163, 14188, 14535, 90270 |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [5 empty] | Jaime Dawson | 9025677460 | Angela Hall | 9025677456 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 27 | 3 |  |  | 30 | Centrex |  | done | 12 |  | 11 |  | 902567 | ALIANT TELECOM (NS) | NS | Sydney | SYDNNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-10 | 2015-01-20 | 4 | N | N/A | no | [9 empty] | e06603cr1 | 5M | 5000 | 10.137.164.1/25
P&CB | 802085 | 2016-05-17 | 9153 | GANDER BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 78 ELIZABETH DR | GANDER | NEWFOUNDLAND | A1V1J8 |  | 2016-05-04 | 2016-06-01 |  | 2016-06-15 |  |  | 00000, 123, 9063, 9153, 9275 |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [5 empty] | Lisa Abbott | 7092561602 |  |  | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 23 | 3 |  |  | 26 | Centrex |  | done | 11 |  |  |  | 709256 | ALIANT TELECOM (NF) | NL | Gander | GNDRNFXARSC | Unregulated / Non Réglementé | 0 | 0 | 2016-06-10 | 2015-08-10 | 1 | N | N/A | no | [9 empty] | e09153br1 | T1 | 1500 | 10.136.184.129/25
DS | 809098 | 2016-05-17 | 90270 | NS RBCDS INC-HALIFAX | [7 empty] | 404 CHARLOTTE ST | SYDNEY | NOVA SCOTIA | B1P1E2 |  | 2016-05-04 | 2016-06-01 |  | 2016-06-15 |  |  | 00000, 6404, 6603, 9076, 9473, 9593, 9843, 9883. 14163, 14188, 14535, 90270 |  | Unisys |  |  | 2016-03-16 | 2016-06-10 | [9 empty] | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 2 | 0 |  |  | 2 | Centrex |  | done | 5 |  | 11 |  | 902567;902736;902849 | [7 empty] | 2016-06-10 | 2015-07-13 | 0 | N | N/A
P&CB | 800269 | 2016-05-17 | 934 | FREDERICTON-PROSPECT ST BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 1206 PROSPECT ST-UNIT 3 | FREDERICTON | NEW BRUNSWICK | E3B3C1 |  | 2016-05-05 | 2016-06-02 |  | 2016-06-16 | Ins 15268 1206 PROSPECT ST , FREDERICTON , NB |  | 00000, 934, 4435, 8014, 9404, 11102, 14186, 14582, 15268 |  | Unisys |  |  | 2016-03-17 | 2016-06-13 | [5 empty] | Jillian Penney | 5064502353 | Sharon Lockhart | 5064502388 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 26 | 2 |  |  | 28 | Centrex |  | done | 12 |  | 9 |  | 506450 | ALIANT TELECOM (NB) | NB | Fredericton | FCTNNBSC45C | Unregulated / Non Réglementé | 0 | 0 | 2016-06-11 | 2015-08-10 | 0 | N | N/A | no | [9 empty] | e00934cr5 | Other | 1500 | 10.136.45.129/25
P&CB | 800616 | 2016-05-17 | 1833 | COLE HARBOUR BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 1022 COLE HARBOUR RD | DARTMOUTH | NOVA SCOTIA | B2V1E7 |  | 2016-05-05 | 2016-06-02 |  | 2016-06-16 |  |  | 00000, 1506, 1833, 2985, 4039, 6404, 6533, 7666, 7943, 8531, 9593, 9843, 9943, 17307 |  | Unisys |  |  | 2016-03-17 | 2016-06-13 | [7 empty] | June Craig | 9024214375 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 39 | 12 |  |  | 51 | Centrex |  | done | 18 |  | 14 |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-11 | 2014-12-16 | 4 | N | N/A | no | [9 empty] | e01833br1 | 5M | 5000 | 10.137.114.1/25
P&CB | 801435 | Yes/Oui | 5207 | ST ANNE`S & AVONDALE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 167 ST ANNE'S RD | WINNIPEG | MANITOBA | R2M2Z7 |  | 2016-04-12 | 2016-04-21 |  | 2016-06-16 | Nov. 26: Updated column A from Phase 2 Pilot to Roll out. NOTE**PH Oct. 14**Added to Master for 2016 migration. Reference: Unable to rescue the migrations in time for the Pilot cutoff of July 31st. Dropped from the Pilot based on a decision from Ernie/John that we could assess our processes with the number of pilot migrations we had from ON, PQ, BC, and AB. MB was declared a risk going into Rollout. Previous cutover date - July 24/2014 |  | 5207, 6939 |  | Bell Canada |  |  | 2016-03-17 | 2016-06-13 | [5 empty] | Medardo Espinoza | 2049886103 | Darcie Sabeski | 2049884198 | MAN/SASK NORTHWEST ONTARIO | Jeff Zacharias | Rob Loeppky | [8 empty] | 7 |  | 2 |  | 204988 | MTS Inc. | MB | Winnipeg | WNPGMB02DS2 | (C) Unregulated / Non Réglementé | 204-318-1717 | winnipeg_01_2043181717 | 2016-06-11 | 2014-06-26 | 1 | N | N/A | no | [9 empty] | w05207br1 | T1 | 1500 | 10.136.202.129/25
INS | 809061 | 2016-05-17 | 15268 | FREDERICTON-PROSPECT ST BRANCH | 17:00 | 17:00 | 19:00 | 19:00 | 17:00 | Closed | Closed | 1206 PROSPECT ST | FREDERICTON | NEW BRUNSWICK | E3B2C2 |  | 2016-05-05 | 2016-06-02 |  | 2016-06-16 |  |  | 00000, 934, 4435, 8014, 9404, 11102, 14186, 14582, 15268 |  | Aliant |  |  | 2016-04-28 | 2016-06-13 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 4 | 0 |  |  | 4 | Centrex |  |  | 4 |  | 9 |  | 506450;506451;506870; | [7 empty] | 2016-06-11 | 2015-08-10 | 1 | N | N/A
P&CB | 800115 | Yes/Oui | 400 | HASTINGS & ROSSER BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 4382 EAST HASTINGS ST | BURNABY | BRITISH COLUMBIA | V5C2J9 |  | 2016-04-15 | 2016-04-25 |  | 2016-06-20 | Oct 28: MPLS upgrade req'd Changed cutover from Jan 14 to TBD |  | 00000, 400, 11687, 14167, 14930, 14988, 15012, 15529, 15602 |  | Bell Canada |  |  | 2016-03-21 | 2016-06-15 |  | 2014-10-14 |  |  |  | Laurentia Robbins | 6046655909 | Salvatore Mele | 6046655912 | BRITISH COLUMBIA | Mauro Susi | Timothy Carmack | 24 | 1 |  |  | 25 | Centrex |  | done | 11 |  | 9 |  | 604665 | TELUS | BC | Vancouver | VANCBC014XD | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-06-15 | 2014-07-04 |  | Y | 2014-07-04 | Yes | 2015-12-08 | 2014-05-05 | 2016-06-15 | Pending Circuit Installation | Done | Done | Complete | Complete | Aug 1 - 27 BC | w00400br5 | Other | 1500 | 10.136.54.1/25
P&CB | 800312 | Yes/Oui | 1119 | BONNYVILLE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 5028 50TH AVE SUITE #104 | BONNYVILLE | ALBERTA | T9N2G8 |  | 2016-04-14 | 2016-04-25 |  | 2016-06-20 | 1/18/2015: Sip Avail Nov 18 2014 |  | 1119, 7599, 7927, 9955, 10453 |  | Unisys |  |  | 2016-03-21 | 2016-06-15 | [5 empty] | Carol Vasseur | 7808268880 | Carrie Ann Darr | 7808268888 | ALBERTA & TERRITORIES | Nicole Gratton | Dan Chipak | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  | 5 |  | 780826 | TELUS | AB | Bonnyville | BNVLAB03RS1 | (W) Regulated / Réglementé | 0 | 0 | 2016-06-15 | 2015-01-19 | 1 | Y | 2015-01-19 | Yes | 2016-01-25 | 2015-04-21 | 2016-06-15 |  | done | done | Complete | Complete | July 30 - 24 AB | w01119br1 | DSL | 1500 | 10.136.24.129/25
P&CB | 800334 | 2016-05-17 | 1214 | HARVEY BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 1941 ROUTE 3 | HARVEY STATION | NEW BRUNSWICK | E6K1K3 |  | 2016-05-09 | 2016-06-06 |  | 2016-06-20 |  |  |  |  | Unisys |  |  | 2016-03-21 | 2016-06-15 | [9 empty] | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 10 | 1 |  |  | 11 | Centrex |  | done | 6 |  |  |  | 506366 | ALIANT TELECOM (NB) | NB | Harvey Station | HVSTNBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-15 | 2015-01-14 | 0 | Y | 2014-03-09 | Yes |  | Done | 2016-06-15 | Bell | 2016-03-16 | 2016-03-27 | OK | 85 | 2016-03-31 | e01214br1 | DSL | 1500 | 10.138.59.1/25
P&CB | 801428 | 2016-05-17 | 5173 | NEW WATERFORD BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 3414 PLUMMER AVE | NEW WATERFORD | NOVA SCOTIA | B1H4K4 |  | 2016-05-09 | 2016-06-06 |  | 2016-06-20 |  |  | 00000, 5173 |  | Unisys |  |  | 2016-03-21 | 2016-06-15 | [5 empty] | Joleen Ross | 9028624581 | Jeannie Camilli | 9028624573 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 12 | 2 |  |  | 14 | Centrex |  | done | 7 |  |  |  | 902862 | ALIANT TELECOM (NS) | NS | New Waterford | NWFRNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-15 | 2015-07-13 | 1 | Y | 2014-11-28 | Yes |  | Done | 2016-06-15 | Bell | 2016-04-11 | 2016-04-25 | OK | 56 | 2016-03-31 | e05173br1 | DSL | 1500 | 10.138.71.129/25
P&CB | 802233 | 2016-05-17 | 9753 | TRINITY BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 17 WEST ST | TRINITY | NEWFOUNDLAND | A0C2S0 |  | 2016-05-09 | 2016-06-06 |  | 2016-06-20 |  |  |  |  | Unisys |  |  | 2016-03-21 | 2016-06-15 | [9 empty] | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 7 | 1 |  |  | 8 | Centrex |  | done | 5 |  |  |  | 709464 | ALIANT TELECOM (NF) | NL | Port Rexton | MTPRNF01DS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-15 | 2015-08-12 | 2 | N | N/A | no | [9 empty] | e09753br1 | T1 | 1500 | 10.136.187.1/25
P&CB | 800643 | 2016-05-17 | 1963 |  | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | 226 WATER ST | ST. JOHN'S | NEWFOUNDLAND | A1C1A9 |  | 2016-05-10 | 2016-06-07 |  | 2016-06-21 |  |  | 00000, 123, 514, 1684, 1963, 8133, 8963, 9275, 9403, 9453, 13937, 14165, 14583, 14461 |  | Unisys |  |  | 2016-03-22 | 2016-06-16 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 8 | 0 |  |  | 8 | Centrex |  | done | 5 |  | 14 |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-06-16 | 2015-08-25 | 0 | N | N/A | no | [9 empty] | e01963br1 | 5M | 5000 | 10.136.236.129/25
P&CB | 801306 | Yes/Oui | 4480 | POWELL RIVER | 17:00 | 17:00 | 17:00 | 18:00 | 17:00 | Closed | Closed | 7035 BARNET STREET | POWELL RIVER | BRITISH COLUMBIA | V8A1Z9 |  | 2016-04-18 | 2016-04-26 |  | 2016-06-21 | 1/18/2015 SIP avail Nov 2014 |  | 00000, 4301, 4480, 13056, 13057, 15041 |  | Bell Canada |  |  | 2016-03-22 | 2016-06-16 | [5 empty] | Kim Friedel | 6044142002 | Beverly Werner | 6044142010 | BRITISH COLUMBIA | Heather Marshak | Timothy Carmack | 15 |  |  |  | 15 | Centrex |  | done | 8 |  | 6 |  | 604485 | TELUS | BC | Westview | PWRVBC01DS1 | (W) Unregulated / Non Réglementé | 0 | 0 | 2016-06-16 | 2015-09-24 | 1 | N | N/A | Yes |  | 2015-06-26 | 2016-06-16 | Telus | 2016-01-13 | 2016-03-07 | OK | 106 | Aug 1 - 27 BC | w04480br1 | DSL | 1500 | 10.136.15.1/25
P&CB | 801497 | Yes/Oui | 5619 | FAIRVIEW BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | 10201 110TH ST | FAIRVIEW | ALBERTA | T0H1L0 |  | 2016-04-15 | 2016-04-26 |  | 2016-06-21 | 1/18/2015: SIP available Nov 18, 2014 |  | 5619, 9955 |  | Unisys |  |  | 2016-03-22 | 2016-06-16 | [5 empty] | Tracy Petereit | 7808357182 |  |  | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 12 | 1 |  |  | 13 | Centrex |  | done | 7 |  | 2 |  | 780835 | TELUS | AB | Fairview | FRVWAB01RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-06-16 | 2015-05-30 | 2 | Y | 2015-06-01 | Yes | 2015-09-18 | 2014-06-26 | 2016-06-16 | Completed |  |  | Complete | Complete | Recovered - AB | w05619br1 | 5M | 5000 | 10.136.0.129/25
P&CB | 801665 | 2016-05-17 | 6823 | TRURO BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 940 PRINCE ST | TRURO | NOVA SCOTIA | B2N1H5 |  | 2016-05-10 | 2016-06-07 |  | 2016-06-21 |  |  | 00000, 5783, 6823, 9843, 14188, 14445, 14535, 14931, 15977 |  | Unisys |  |  | 2016-03-22 | 2016-06-16 | [5 empty] | Stephen Gallant | 9028975534 | Andrea McNally-Saywood | 9028978493 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 60 | 16 |  |  | 76 | Centrex |  | done | 24 |  |  |  | 902897 | ALIANT TELECOM (NS) | NS | Truro | HLFXNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-16 | 2014-12-10 | 5 | N | N/A | no | [9 empty] | e06823br1 | 5M | 5000 | 10.137.117.1/25
P&CB | 802206 | 2016-05-17 | 9453 | MAIN BR - ST JOHNS | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 226 WATER ST | ST JOHNS | NEWFOUNDLAND | A1C1A9 |  | 2016-05-10 | 2016-06-07 |  | 2016-06-21 |  |  | 00000, 123, 514, 1684, 1963, 8133, 8963, 9063, 9275, 9453, 13937, 14165, 14583, 14661 |  | Unisys |  |  | 2016-03-22 | 2016-06-16 | [5 empty] | David Works | 7095764754 | Geraldine Peyton | 7095764767 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 28 | 0 |  |  | 28 | Centrex |  | done | 12 |  |  |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-06-16 | 2015-08-06 | 3 | N | N/A | no | [9 empty] | e09453br1 | 5M | 5000 | 10.137.41.1/25
P&CB | 800048 | 2016-05-17 | 170 | DIEPPE NB BR (CO-HAB WITH INSUR) | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 231 CHAMPLAIN ST | DIEPPE | NEW BRUNSWICK | E1A1N9 |  | 2016-05-11 | 2016-06-08 |  | 2016-06-22 | Ins 15267 231 CHAMPLAIN ST-SUITE 101 , DIEPPE , NB |  | 170, 1426, 8014, 9279, 10047, 11898, 13279, 15267, 16972 |  | Unisys |  |  | 2016-03-23 | 2016-06-17 | [5 empty] | Ghislain Bernard | 5068703740 | Josee Cyr | 5068703736 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 19 | 39 |  |  | 58 | IP |  | done | 20 |  | 9 |  | 506870 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e00170cr1 | 10M | 10000 | 10.32.5.1/26 | Y
P&CB | 800161 | Yes/Oui | 549 | CAL-MARDA LOOP BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 2035 33RD AVE SW | CALGARY | ALBERTA | T2T1Z5 |  | 2016-04-18 | 2016-04-27 |  | 2016-06-22 |  |  | 549, 17182 |  | Bell Canada |  |  | 2016-03-23 | 2016-06-17 | [5 empty] | Jenn Gregory | 4032922206 | Gemma Lee | 4032928289 | ALBERTA & TERRITORIES | Kathy Marrinan | Dan Chipak | 14 |  |  |  | 14 | Centrex |  | done | 7 |  | 2 |  | 403292 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-06-17 | 2015-08-04 | 3 | N | N/A | Yes | 2015-09-14 | 2014-05-05 | 2016-06-17 | Completed |  |  | Complete | Complete | July 30 - 24 AB | w00549br1 | 5M | 5000 | 10.136.55.129/25
P&CB | 800356 | Yes/Oui | 1240 | COMO LAKE VILLAGE SHOPPING CENTRE | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 1962 COMO LAKE RD | COQUITLAM | BRITISH COLUMBIA | V3J3R3 |  | 2016-04-19 | 2016-04-27 |  | 2016-06-22 | Oct 28: MPLS upgrade req'd Changed cutover from Jan 29 to TBD david.lu: 6/24: moved back into schedule as per Leslie's request 6/8: moved to TBD as per Linda's 1pm call - pending MPLS upgrade MPLS delay -- move to 2016 |  | 00000, 1240, 1653, 8890, 14972 |  | Bell Canada |  | Yinka Alexander @ 604-340-1627 Purwanto Hadi @ 604-679-8618, | 2016-03-23 | 2016-06-17 | delayed | 2015-06-26 |  |  |  | Nadine Tucker | 6049335342 | Cindy Muscroft | 6049335347 | BRITISH COLUMBIA | Mauro Susi | Timothy Carmack | 25 | 3 |  |  | 28 | Centrex |  | done | 12 | N | 5 |  | 604933 | TELUS | BC | Port Moody | CQTLBC01CT1 | (C) Unregulated / Non Réglementé | 778-272-8599 | port_moody_01_7782728599 | 2016-06-17 | 2015-02-12 | 2 | Y | 2014-02-21 | Yes | 2015-10-15 | 2015-02-27 | 2016-06-17 |  | done | done | Complete | Complete | Priority - 50 | w01240br1 | DSL | 1500 | 10.136.18.1/25
INS | 802778 | 2016-05-17 | 15227 | CLAYTON PARK, HALIFAX | 17:00 | 17:00 | 19:00 | 19:00 | 17:00 | Closed | Closed | 287 LACEWOOD DR-UNIT 110 | HALIFAX | NOVA SCOTIA | B3M3Y7 |  | 2016-05-11 | 2016-06-08 |  | 2016-06-22 |  |  | 5783, 13277, 15227, 15283 |  | Unisys |  |  | 2016-03-23 | 2016-06-17 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 7 | 0 |  |  | 7 | Centrex |  | done | 5 |  | 4 |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-17 | 2014-12-10 | 0 | N | N/A | no | [9 empty] | e15227sr1 | 5M | 5000 | 10.137.54.1/25
INS | 809063 | 2016-05-17 | 15267 | DIEPPE, NB | 17:00 | 17:00 | 19:00 | 19:00 | 17:00 | 17:00 | Closed | 231 CHAMPLAIN ST, SUITE 101 | DIEPPE | NEW BRUNSWICK | E1A1N9 |  | 2016-05-11 | 2016-06-08 |  | 2016-06-22 |  |  | 170, 1426, 8014, 9279, 10047, 11898, 13279, 15267, 16972 |  | Aliant |  |  | 2016-05-04 | 2016-06-17 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 8 | 0 |  |  | 8 | Centrex |  | done | 5 |  | 9 |  | 506859;506870; | [7 empty] | N/A | N/A | N/A | N | N/A
P&CB | 800623 | 2016-05-17 | 1874 | SACKVILLE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 103 MAIN ST | SACKVILLE | NEW BRUNSWICK | E4L4B1 |  | 2016-05-12 | 2016-06-09 |  | 2016-06-23 |  |  | 1426, 1874, 5728, 10108 |  | Unisys |  |  | 2016-03-24 | 2016-06-20 | [5 empty] | Laura Landriault | 5063641940 | Terri Hope-Tooley | 5063641942 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 20 | 1 |  |  | 21 | Centrex |  | done | 10 |  | 4 |  | 506536 | ALIANT TELECOM (NB) | NB | Sackville | SKVLNBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-18 | 2015-08-17 | 1 | N | N/A | Yes | 2015-08-17 | 2015-04-21 | 2015-08-01 | Completed | 2015-06-26 |  | Complete | Complete | Aug 1 - per Adam | e01874br1 | T1 | 1500 | 10.137.248.129/25
P&CB | 800951 | Yes/Oui | 3257 | MORDEN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | Closed | Closed | 289 STEPHEN ST | MORDEN | MANITOBA | R6M1V2 |  | 2016-04-19 | 2016-04-28 |  | 2016-06-23 |  |  | 3257, 3349, 9914, 9940, 13987, 17176 |  | Bell Canada |  |  | 2016-03-24 | 2016-06-20 | [5 empty] | Jeff McAulay | 2048222379 | Miranda Rowson | 2048222370 | MAN/SASK NORTHWEST ONTARIO | Justin Cornett | Rob Loeppky | 20 | 2 |  |  | 22 | Centrex |  | done | 10 |  |  |  | 204822 | MTS Inc. | MB | Morden | MRDNMB01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-18 | 2014-07-04 | 1 | Y | 2014-07-16 | no | [9 empty] | w03257br1 | 5M | 5000 | 10.138.119.129/25
P&CB | 801704 | 2016-05-17 | 7153 | COLDBROOK CENTRE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 6615 HWY #1 | COLDBROOK | NOVA SCOTIA | B4R1B6 |  | 2016-05-12 | 2016-06-09 |  | 2016-06-23 |  |  | 5103, 7153, 14535 |  | Unisys |  |  | 2016-03-24 | 2016-06-20 | [5 empty] | Shelley Barker | 9026793888 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 14 | 2 |  |  | 16 | Centrex |  | done | 8 |  |  |  | 902679 | ALIANT TELECOM (NS) | NS | Kentville | BDFRNS02CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-18 | 2015-05-01 | 2 | Y | 2014-07-20 | Yes |  | Done | 2016-06-18 | Bell | 2016-03-07 | 2016-03-27 | OK | 88 | 2016-03-31 | e07153br1 | DSL | 1500 | 10.138.74.129/25
P&CB | 801717 | 2016-05-17 | 7213 | WEST PUBNICO BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 968 ROUTE #335 | WEST PUBNICO | NOVA SCOTIA | B0W3S0 |  | 2016-05-12 | 2016-06-09 |  | 2016-06-23 |  |  |  |  | Unisys |  |  | 2016-03-24 | 2016-06-20 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  |  |  | 902762 | ALIANT TELECOM (NS) | NS | Pubnico | PBNCNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-18 | 2015-07-13 | 1 | Y | 2014-10-18 | no | [9 empty] | e07213br1 | T1 | 1500 | 10.136.179.1/25
P&CB | 800630 | 2016-05-17 | 1904 | QUISPAMSIS BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 169 HAMPTON RD. | QUISPAMSIS | NEW BRUNSWICK | E2E2R3 |  | 2016-05-16 | 2016-06-13 |  | 2016-06-27 |  |  |  |  | Unisys |  |  | 2016-03-28 | 2016-06-22 | [5 empty] | Karen Hachey | 5068495527 |  |  | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 26 | 3 |  |  | 29 | Centrex |  | done | 12 |  |  |  | 506849 | ALIANT TELECOM (NB) | NB | Rothesay | RHSYNBSC84C | Unregulated / Non Réglementé | 0 | 0 | 2016-06-22 | 2015-08-11 | 2 | N | N/A | no | [9 empty] | e01904br1 | 3M | 3000 | 10.137.63.129/25
P&CB | 800833 | Yes/Oui | 2800 | DELTA BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 5205 LADNER TRUNK ROAD | DELTA | BRITISH COLUMBIA | V4K1W4 |  | 2016-04-22 | 2016-05-02 |  | 2016-06-27 |  |  | 2800 |  | Bell Canada |  |  | 2016-03-28 | 2016-06-22 | [5 empty] | James Richmond | 6048865406 | Jenice Edwards | 6049403262 | BRITISH COLUMBIA | Melanie Bird | Timothy Carmack | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  | 1 |  | 604940 | TELUS | BC | Ladner | DELTBC01DS1 | (I) Unregulated / Non Réglementé | 0 | 0 | 2016-06-22 |  |  | N | N/A | Yes | 2015-06-18 | 2014-09-19 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w02800br1 | 5M | 5000 | 10.136.236.1/25
P&CB | 801722 | 2016-05-17 | 7263 | WESTVILLE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 1813 MAIN ST | WESTVILLE | NOVA SCOTIA | B0K2A0 |  | 2016-05-16 | 2016-06-13 |  | 2016-06-27 |  |  |  |  | Unisys |  |  | 2016-03-28 | 2016-06-22 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 8 | 2 |  |  | 10 | Centrex |  | done | 6 |  |  |  | 902396 | ALIANT TELECOM (NS) | NS | New Glasgow | NWGLNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-22 | 2015-08-05 | 2 | N | N/A | Yes |  | Done | 2016-06-22 | Bell | 2016-03-07 | 2016-03-27 | OK | 92 | 2016-03-31 | e07263br1 | DSL | 1500 | 10.136.222.1/25
P&CB | 801732 | 2016-05-17 | 7373 | WEYMOUTH BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | ROUTE #1 | WEYMOUTH | NOVA SCOTIA | B0W3T0 |  | 2016-05-16 | 2016-06-13 |  | 2016-06-27 |  |  |  |  | Unisys |  |  | 2016-03-28 | 2016-06-22 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 6 | 1 |  |  | 7 | Centrex |  | done | 5 |  |  |  | 902837 | ALIANT TELECOM (NS) | NS | Weymouth | WYMTNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-22 | 2015-01-28 | 3 | N | N/A | no | [9 empty] | e07373br1 | T1 | 1500 | 10.136.253.1/25
P&CB | 801939 | Yes/Oui | 8229 | WHITECOURT BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 5117 50TH AVE | WHITECOURT | ALBERTA | T7S1A1 |  | 2016-04-21 | 2016-05-02 |  | 2016-06-27 | 1/18/2015: SIP available Nov 18, 2014 |  | 1625, 8229, 8749, 9892, 9955, 10451, 14362 |  | Unisys |  |  | 2016-03-28 | 2016-06-22 | [5 empty] | Camden Robinson | 7807064006 | Holly Kerr | 7807786820 | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  | 7 |  | 780706 | TELUS | AB | Whitecourt | WTCOAB04RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-06-22 | 2015-07-15 | 1 | Y | 2014-04-18 | Yes | 2015-11-09 | 2015-04-21 | 2016-06-22 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w08229br1 | 5M | 5000 | 10.136.24.1/25
PH&N | 800049 | Yes/Oui | 16309 | AB PH&N ADVISORY | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | Closed | Closed | 300 5TH AVENUE - SUITE 620 | CALGARY | ALBERTA | T2P3C4 |  | 2016-04-22 | 2016-05-03 |  | 2016-06-28 | 3/22/2015 RBC investigating rejection 2 users may be connected to CC david.lu: 7/9: res to April 2016 as per RBC update due to MPLS upgrades Hickey, Linda M (N367668): Rs from May 6 to Sept 10 pending RBC response LMacLean: Sept 1st is the placeholder date |  | 176, 16309 |  | Bell Canada |  |  | 2016-03-29 | 2016-06-23 |  | 2015-03-04 | [7 empty] | ALBERTA & TERRITORIES | Rhonda Graham | Dan Chipak | 22 | 1 |  |  | 23 | Centrex |  | done | 10 | Y | 2 |  | 403 | BELL CANADA - ON | ON | Toronto | TOROON01DS0 | (C) Unregulated / Non Réglementé | 4163481342 | toronto_01_4163481342 | 2016-06-23 | 2014-10-28 | 2 | N | N/A | no | [9 empty] | w00177br1 | 10M | 10000 | 10.138.95.1/25
P&CB | 800573 | Yes/Oui | 1680 | DAWSON CREEK BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 10324 10TH ST | DAWSON CREEK | BRITISH COLUMBIA | V1G3T6 |  | 2016-04-25 | 2016-05-03 |  | 2016-06-28 |  |  | 00000, 1680, 7700, 8642, 9888, 13490, 14444 |  | Unisys |  |  | 2016-03-29 | 2016-06-23 | [7 empty] | Leanne Lacey | 2507193461 | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 22 | 1 |  |  | 23 | Centrex |  | done | 10 |  | 7 |  | 250719 | TELUS | BC | Dawson Creek | DWCKBC01DS1 | (C) Regulated / Réglementé | 0 | 0 | 2016-06-23 | 2015-03-11 | 3 | N | N/A | Yes | 2015-12-15 | 2015-06-25 | 2016-06-23 |  | done | done | Complete | Complete | Aug 1 - 27 BC | w01680br1 | DSL | 1500 | 10.136.28.129/25
P&CB | 801405 | 2016-05-17 | 5054 | CHARLOTTETOWN BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 83 QUEEN ST | CHARLOTTETOWN | PRINCE EDWARD ISLAND | C1A4A8 |  | 2016-05-17 | 2016-06-14 |  | 2016-06-28 |  |  | 00000, 5054, 7484, 8024, 9044, 9278, 10007, 14187, 15529, 17436 |  | Unisys |  |  | 2016-03-29 | 2016-06-23 | [5 empty] | Mary Macinnis | 9026289100 | Sheena Ramsay | 9026289134 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 53 | 10 |  |  | 63 | Centrex |  | done | 21 |  |  |  | 902628 | ALIANT TELECOM (PEI) | PE | Charlottetown | CHTWPE01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-23 | 2015-01-14 | 4 | Y | 2015-01-16 | no | [9 empty] | e05054br1 | 5M | 5000 | 10.137.116.129/25
P&CB | 801756 | 2016-05-17 | 7483 | WHYCOCOMAGH BRANCH | [7 empty] | 72 VILLAGE RD | WHYCOCOMAGH | NOVA SCOTIA | B0E3M0 |  | 2016-05-17 | 2016-06-14 |  | 2016-06-28 |  |  | 7483 |  | Unisys |  |  | 2016-03-29 | 2016-06-23 | [9 empty] | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 7 | 1 |  |  | 8 | Centrex |  | done | 5 |  |  |  | 902756 | ALIANT TELECOM (NS) | NS | Whycocomagh | WCMGNS02RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-23 | 2015-07-13 | 1 | Y | 2014-10-24 | no | [9 empty] | e07483br1 | T1 | 1500 | 10.136.179.129/25
P&CB | 802089 | 2016-05-17 | 9203 | GRAND FALLS WINDSOR BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 19 CROMER AVE | GRAND FALLS/WINDSOR | NEWFOUNDLAND | A2A2K5 |  | 2016-05-17 | 2016-06-14 |  | 2016-06-28 |  |  |  |  | Unisys |  |  | 2016-03-29 | 2016-06-23 | [5 empty] | Ashley MacDonald | 7094898758 |  |  | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 709489 | ALIANT TELECOM (NF) | NL | Grand Falls | GDFLNF02RSC | Unregulated / Non Réglementé | 0 | 0 | 2016-06-23 | 2014-09-01 | 1 | Y | 2014-08-29 | Yes |  | Done | 2016-06-23 | Bell | 2016-03-09 | 2016-03-27 | OK | 93 | 2016-03-31 | e09203br1 | DSL | 1500 | 10.138.79.1/25
P&CB | 800056 | Yes/Oui | 201 | ELLERSLIE CROSSING SHOPPING CENTRE | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 804 PARSONS RD. S.W. | EDMONTON | ALBERTA | T6X0B4 |  | 2016-04-25 | 2016-05-04 |  | 2016-06-29 | david.lu: 7/2: postponed to april 1/ 2016 due to pending MPLS upgrade (elaine's note on 6/30) 5/28: moved from 6/4 to sept 1 pending MPLS upgrade updates |  | 201, 3223, 4349, 8749, 9679, 9955, 10451, 10452, 10453, 15693 |  | Bell Canada |  |  | 2016-03-30 | 2016-06-24 |  | 2015-04-14 |  |  |  | Denise Vandermeer | 7804486182 | Carmen Flores | 7809444373 | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 23 | 1 |  |  | 24 | Centrex |  | done | 10 |  | 10 |  | 780944 | TELUS | AB | Edmonton | EDTNABXMCG5 | (C) Regulated / Réglementé | 780-670-2348 | edmonton_01_7806702348 | 2016-06-24 | 2015-07-03 | 1 | N | N/A | Yes | 2015-08-25 | 2015-02-19 | 2016-06-24 | Completed | 2015-08-14 |  | Complete | Complete | Priority - 50 | w00201br1 | 3M | 3000 | 10.137.217.1/25
P&CB | 800736 | Yes/Oui | 2360 | KAMLOOPS-SAHALI BR (COLUMBIA PLACE) | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | Closed | 1210 SUMMIT DR-UNIT 400 | KAMLOOPS | BRITISH COLUMBIA | V2C6M1 |  | 2016-04-26 | 2016-05-04 |  | 2016-06-29 |  |  | 00000, 1830, 2360, 10695, 11920, 13053, 16395 |  | Unisys |  |  | 2016-03-30 | 2016-06-24 | [5 empty] | Dwight Harris | 2503143846 | Glenna Cooper | 2503143812 | BRITISH COLUMBIA | Dana McCombie | Timothy Carmack | 24 | 1 |  |  | 25 | Centrex |  | done | 11 |  | 7 |  | 250314 | TELUS | BC | South Kamloops | KMLPBC01DS2 | (W) Regulated / Réglementé | 250-434-1228 | southkamloops_01_2504341228 | 2016-06-24 | 2014-08-06 | 3 | N | N/A | Yes |  | 2014-05-06 | 2016-06-24 | Telus | 2016-01-22 | 2016-03-09 | OK | 112 | Aug 1 - 27 BC | w02360br5 | Other | 1500 | 10.136.67.1/25
P&CB | 801771 | 2016-05-17 | 7593 | WINDSOR BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 111 WATER ST | WINDSOR | NOVA SCOTIA | B0N2T0 |  | 2016-05-18 | 2016-06-15 |  | 2016-06-29 |  |  | 00000, 7593, 9843, 14445, 14931, 15928 |  | Unisys |  |  | 2016-03-30 | 2016-06-24 | [7 empty] | James MacDonald | 9027986220 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 18 | 3 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 902798 | ALIANT TELECOM (NS) | NS | Windsor | WNDSNS01RS1 | Unregulated / Non Réglementé | 519-255-9607 | windsor_on_01_5192559607 | 2016-06-24 | 2015-04-30 | 1 | Y | 2014-05-11 | Yes | 2015-06-11 | Sent | 2015-08-01 | Completed | 2015-06-02 |  | Complete | Complete | Aug 1 - per Adam | e07593br1 | T1 | 1500 | 10.138.75.129/25
P&CB | 802096 | 2016-05-17 | 9243 | MOUNT PEARL BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 45 COMMONWEALTH AVE | MOUNT PEARL | NEWFOUNDLAND | A1N1W7 |  | 2016-05-18 | 2016-06-15 |  | 2016-06-29 |  |  | 00000, 514, 8133, 9063, 9243, 9275, 14583, 14661, 16385 |  | Unisys |  |  | 2016-03-30 | 2016-06-24 | [5 empty] | Karen Hollahan | 7095764199 | Lois Fowler | 7097588641 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  | 9 |  | 709758 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-06-24 | 2015-08-25 | 0 | N | N/A | no | [9 empty] | e09243br1 | 3M | 3000 | 10.136.185.129/25
DS | 803019 | 2016-05-17 | 90270 | RBC DOMINION SECURITIES | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 1959 UPPER WATER ST. | HALIFAX | NOVA SCOTIA | B3J3N2 |  | 2016-05-18 | 2016-06-15 |  | 2016-06-29 |  |  | 00000, 9486, 90270, 90272, 90936, 90958, 90959 |  | Unisys |  |  | 2016-03-30 | 2016-06-24 |  |  | Stewart Robinson | Emily Hynes; Barbara Alward | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 47 | 119 |  |  | 166 | IP |  | done | 58 |  | 7 |  | 902893 | ALIANT TELECOM (NS) | NS | Truro | HLFXNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e90270vr1 | 10M | 10000 | 10.32.27.2/25
P&CB | 800708 | 2016-05-17 | 2204 | SUSSEX BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 664 MAIN ST | SUSSEX | NEW BRUNSWICK | E4E7H9 |  | 2016-05-19 | 2016-06-16 |  | 2016-06-30 | DS 90282 664 Main St Sussex, NB. (NOTE: Sept 17 Cutover date changed to TBD from January 08. No SIP available. Replacement site needed .ph) |  | 00000, 2204, 4435, 8014, 9404, 14582, 16932, 90282 |  | Unisys |  |  | 2016-03-31 | 2016-06-27 | [5 empty] | Melissa Astle | 5064321632 | Gerri Sernick | 5064321626 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 23 | 4 |  |  | 27 | Centrex |  | done | 11 |  | 8 |  | 506432 | ALIANT TELECOM (NB) | NB | Sussex | SUSXNBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-25 | 2014-09-11 | 3 | N | N/A | no | [9 empty] | e02204cr1 | 5M | 5000 | 10.137.51.129/25
P&CB | 801476 | 2016-05-17 | 5503 | PICTOU BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 25 WATER ST | PICTOU | NOVA SCOTIA | B0K1H0 |  | 2016-05-19 | 2016-06-16 |  | 2016-06-30 |  |  | 00000, 5503, 9843 |  | Unisys |  |  | 2016-03-31 | 2016-06-27 | [5 empty] | Leslie Otter | 9024854355 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 15 | 2 |  |  | 17 | Centrex |  | done | 8 |  |  |  | 902485 | ALIANT TELECOM (NS) | NS | Pictou | PCTUNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-25 | 2014-12-09 | 1 | N | N/A | no | [9 empty] | e05503br1 | T1 | 1500 | 10.138.73.1/25
P&CB | 801577 | Yes/Oui | 6117 | STEINBACH BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 288 MAIN ST | STEINBACH | MANITOBA | R5G1Y8 |  | 2016-04-26 | 2016-05-05 |  | 2016-06-30 |  |  | 00000, 6117, 9940, 13987, 14391, 15572, 17176, 17250 |  | Bell Canada |  |  | 2016-03-31 | 2016-06-27 | [5 empty] | David Wersch | 2043466030 | Karen Labossiere | 2043466010 | MAN/SASK NORTHWEST ONTARIO | Justin Cornett | Rob Loeppky | 28 | 5 |  |  | 33 | Centrex |  | done | 13 |  |  |  | 204346 | MTS Inc. | MB | Steinbach | STNBMB01DS1 | Regulated / Réglementé | 0 | 0 | 2016-06-25 | 2015-05-06 | 4 | N | N/A | no | [9 empty] | w06117br1 | 5M | 5000 | 10.138.122.1/25
DS | 809101 | 2016-05-17 | 90282 | NB RBCDS INC-ST JOHN NEW BR | [7 empty] | 664 MAIN ST | SUSSEX | NEW BRUNSWICK | E4E7H9 |  | 2016-05-19 | 2016-06-16 |  | 2016-06-30 |  |  | 00000, 2204, 4435, 8014, 9404, 14582, 16932, 90282 |  | Unisys |  |  | 2016-03-31 | 2016-06-27 | [9 empty] | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 1 | 0 |  |  | 1 | Centrex |  | done | 5 |  | 8 |  | 506432;506433; | [7 empty] | 2016-06-25 | 2015-09-11 | 3 | N | N/A
P&CB | 800134 | 2016-05-17 | 484 | CHATHAM TOWN CENTRE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 1780 WATER ST | MIRAMICHI | NEW BRUNSWICK | E1N1B6 |  | 2016-05-23 | 2016-06-20 |  | 2016-07-04 |  |  |  |  | Unisys |  |  | 2016-04-04 | 2016-06-29 | [5 empty] | Rob Nowlan | 5067781138 | Mary Allison | 5067781132 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 17 | 2 |  |  | 19 | Centrex |  | done | 9 |  |  |  | 506778 | ALIANT TELECOM (NB) | NB | Miramichi | NWCSNBSC62A | Unregulated / Non Réglementé | 0 | 0 | 2016-06-29 | 2015-08-20 | 1 | N | N/A | Yes |  | Done | 2016-06-29 | Bell | 2016-03-17 | 2016-03-27 | OK | 99 | 2016-03-31 | e00484br1 | DSL | 1500 | 10.138.54.129/25
P&CB | 800387 | 2016-05-17 | 1323 | CHETICAMP BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 15374 CABOT TRAIL RD HWY #19 | CHETICAMP | NOVA SCOTIA | B0E1H0 |  | 2016-05-23 | 2016-06-20 |  | 2016-07-04 |  |  |  |  | Unisys |  |  | 2016-04-04 | 2016-06-29 | [5 empty] | Corinne Doucette | 9022243837 | Adele Cormier-Brett | 9022243217 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902224 | ALIANT TELECOM (NS) | NS | Chéticamp | CCPINS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-06-29 | 2015-01-21 | 0 | N | N/A | no | [9 empty] | e01323br1 | T1 | 1500 | 10.136.162.129/25
P&CB | 800854 | Yes/Oui | 2869 | RIVERBEND | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 8338 18TH ST SE | CALGARY | ALBERTA | T2C4E4 |  | 2016-04-28 | 2016-05-09 |  | 2016-07-04 | Oct 28: MPLS upgrade req'd Changed cutover from Jan 28 to TBD |  | 2699, 2869, 8749, 9955, 16921 |  | Bell Canada |  |  | 2016-04-04 | 2016-06-29 | [7 empty] | Shabnam Saeiarasi | 4032928317 | ALBERTA & TERRITORIES | Blair Munholland | Dan Chipak | 19 | 1 |  |  | 20 | Centrex |  | done | 9 |  | 5 |  | 403292 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-06-29 | 2015-08-06 | 1 | Y | 2014-03-07 | Yes | 2015-08-19 | 2014-05-06 | 2016-06-29 | Completed |  |  | Complete | Complete | July 30 - 24 AB | w02869br1 | 5M | 5000 | 10.136.71.1/25
P&CB | 801710 | Yes/Oui | 7200 | MAIN & KING EDWARD BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 4095 MAIN ST | VANCOUVER | BRITISH COLUMBIA | V5V3P5 |  | 2016-04-29 | 2016-05-09 |  | 2016-07-04 |  |  | 486, 7200, 10698, 10689, 10694, 14965 |  | Bell Canada |  |  | 2016-04-04 | 2016-06-29 | [5 empty] | Robert Lydon | 6046653118 | Ken Chan | 6046653112 | BRITISH COLUMBIA | Wendy Palmer | Timothy Carmack | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  | 6 |  | 604665 | TELUS | BC | Vancouver | VANCBC014XD | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-06-29 | 2014-04-18 |  | Y | 2014-04-18 | Yes | 2015-11-23 | 2014-05-05 | 2016-06-29 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w07200br1 | 5M | 5000 | 10.136.90.1/25
P&CB | 801830 | 2016-05-17 | 7813 | YARMOUTH BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 399 MAIN ST | YARMOUTH | NOVA SCOTIA | B5A1G3 |  | 2016-05-23 | 2016-06-20 |  | 2016-07-04 |  |  | 00000, 7813, 9274, 9843, 14535, 14913, 14931 |  | Unisys |  |  | 2016-04-04 | 2016-06-29 | [5 empty] | Berton Murphy | 9027421447 | Bev Keech | 9027421474 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 21 | 1 |  |  | 22 | Centrex |  | done | 10 |  |  |  | 902742 | ALIANT TELECOM (NS) | NS | Yarmouth | YRMONS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-29 | 2015-05-11 | 2 | Y | 2014-10-19 | no | [9 empty] | e07813br1 | 5M | 5000 | 10.136.227.1/25
P&CB | 800439 | 2016-05-17 | 1433 | CHURCH POINT BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 1729 HIGHWAY 1 | CHURCH POINT | NOVA SCOTIA | B0W1M0 |  | 2016-05-24 | 2016-06-21 |  | 2016-07-05 |  |  |  |  | Unisys |  |  | 2016-04-05 | 2016-06-30 | [5 empty] | Angeline Thimot | 9026452214 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 14 | 3 |  |  | 17 | Centrex |  | done | 8 |  |  |  | 902645 | ALIANT TELECOM (NS) | NS | Meteghan | MTGNNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-06-30 | 2014-12-18 | 1 | N | N/A | no | [9 empty] | e01433br1 | T1 | 1500 | 10.136.163.1/25
P&CB | 801560 | Yes/Oui | 6000 | DENMAN & BARCLAY BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 17:00 | 16:00 | Closed | 945 DENMAN ST | VANCOUVER | BRITISH COLUMBIA | V6G2M3 |  | 2016-05-02 | 2016-05-10 |  | 2016-07-05 |  |  | 00000, 1197, 5600, 6000, 8890, 9687, 14302, 14973 |  | Bell Canada |  |  | 2016-04-05 | 2016-06-30 | [5 empty] | John Webber | 6046655294 | Ayanthi Samarasinghe | 6046658422 | BRITISH COLUMBIA | Elaine Sanderson | Timothy Carmack | 21 | 1 |  |  | 22 | Centrex |  | done | 10 |  | 8 |  | 778785 | GT GROUP TELECOM SERVICES CORP. | BC | Vancouver | VANCBCCN0MD | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-06-30 | 2015-01-05 | 2 | Y | 2015-01-05 | Yes | 2015-08-19 | 2014-05-05 | 2016-06-30 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w06000br1 | 5M | 5000 | 10.136.87.129/25
P&CB | 802100 | 2016-05-17 | 9253 | HEARTS CONTENT BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 230-236 MAIN ROAD | HEARTS CONTENT | NEWFOUNDLAND | A0B1Z0 |  | 2016-05-24 | 2016-06-21 |  | 2016-07-05 |  |  |  |  | Unisys |  |  | 2016-04-05 | 2016-06-30 | [9 empty] | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 8 | 3 |  |  | 11 | Centrex |  | done | 6 |  |  |  | 709583 | ALIANT TELECOM (NF) | NL | Heart's Content | MTPRNF01DS1 | Regulated / Réglementé | 0 | 0 | 2016-06-30 | 2014-07-05 | 7 | Y | 2014-06-07 | no | [9 empty] | e09253br1 | T1 | 1500 | 10.136.186.1/25
P&CB | 802197 | Yes/Oui | 9399 | WESTLOCK BRANCH | 17:00 | 17:00 | 17:00 | 19:00 | 18:00 | Closed | Closed | 10427 100TH AVE | WESTLOCK | ALBERTA | T7P2J2 |  | 2016-04-29 | 2016-05-10 |  | 2016-07-05 |  |  | 9399, 14362 |  | Bell Canada |  |  | 2016-04-05 | 2016-06-30 | [5 empty] | Keri Moffat | 7803493167 |  |  | ALBERTA & TERRITORIES | Chris Buckley | Dan Chipak | 18 | 4 |  |  | 22 | Centrex |  | done | 10 |  | 2 |  | 780349 | TELUS | AB | Westlock | WLOCAB01CG1 | (I) Regulated / Réglementé | 0 | 0 | 2016-06-30 | 2015-07-15 | 4 | Y | 2014-08-31 | Yes |  | 2015-04-21 | 2016-06-30 | Telus - pending conduit install | 2016-03-25 | 2016-04-08 | OK | 88 | July 30 - 24 AB | w09399br1 | DSL | 1500 | 10.136.15.129/25
INS | 802382 | 2016-05-17 | 11176 |  | 17:00 | 17:00 | 19:00 | 19:00 | 17:00 | closed | Closed | 238A BROWNLOW AVE-SUITE 101 | DARTMOUTH | NOVA SCOTIA | B3B2B4 |  | 2016-05-24 | 2016-06-21 |  | 2016-07-05 | N/A | N/A | N/A |  | Unisys |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ATLANTIC PROVINCES | N/A | Mike Wallace | N/A | N/A |  |  | N/A |  | #N/A | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 2016-06-30 | 2014-12-06 | 2 | N | N/A | no | [9 empty] | N/A | N/A | N/A | N/A
P&CB | 800001 | 2016-05-17 | 4 | SAINT JOHN MAIN BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed |  | 100 KING ST | SAINT JOHN | NEW BRUNSWICK | E2L1G4 |  | 2016-05-25 | 2016-06-22 |  | 2016-07-06 |  |  | 00000, 4, 1525, 1617, 1806, 1822, 1826, 2444, 3789, 4202, 4435, 5512, 6503, 7662, 8014, 9102, 9284, 9356, 9404, 10108, 10762, 10768, 13979, 14186, 14582, 15980, 16063, 17226, 17835, 90075, 90084, 90571 |  | Unisys |  |  | 2016-05-18 | 2016-07-01 | [5 empty] | Lisa Loughery | 5066320646 | Stephanie Campbell | 5066320640 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 75 | 16 |  |  | 91 | Centrex |  | done | 28 |  | 32 |  | 506632 | ALIANT TELECOM (NB) | NB | Saint John | STJHNBSU63A | Unregulated / Non Réglementé | 0 | 0 | 2016-07-01 | 2015-01-13 | 2 | N | N/A | no | [9 empty] | e00004br1 | 5M | 5000 | 10.138.11.1/25
P&CB | 800491 | 2016-05-17 | 1543 | CLARKS HARBOUR BRANCH | 16:30 | 16:30 | 16:30 | 17:00 | 16:30 | closed | Closed | 2732 MAIN ST | CLARKS HARBOUR | NOVA SCOTIA | B0W1P0 |  | 2016-05-25 | 2016-06-22 |  | 2016-07-06 |  |  | 1543 |  | Unisys |  |  | 2016-04-06 | 2016-07-01 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 8 | 1 |  |  | 9 | Centrex |  | done | 6 |  |  |  | 902745 | ALIANT TELECOM (NS) | NS | Clarke's Harbour | CKHRNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-01 | 2015-07-13 | 2 | Y | 2014-08-31 | Yes |  | Done | 2016-07-01 | Bell | 2016-03-23 | 2016-04-06 | OK | 91 | 2016-03-31 | e01543br1 | DSL | 1500 | 10.138.60.1/25
P&CB | 800684 | 2016-05-17 | 2125 | UPPER TANTALLON BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 5280 SAINT MARGARETS BAY RD | UPPER TANTALLON | NOVA SCOTIA | B3Z2J1 |  | 2016-05-25 | 2016-06-22 |  | 2016-07-06 |  |  | 1506, 2125, 2985, 9843, 9883, 9903, 15075, 17307 |  | Unisys |  |  | 2016-04-06 | 2016-07-01 | [5 empty] | Karen Corney | 9028265286 | Amanda Aucoin | 9028265288 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 7 | 20 |  |  | 27 | IP |  | done | 11 |  |  |  | 902826 | ALIANT TELECOM (NS) | NS | St Margarets | STMRNS01RS1 | Regulated / Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e02125br1 | 5M | 5000 | 10.32.5.65/26 | Y
P&CB | 800870 | Yes/Oui | 2940 | MERRITT BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 2090 QUILCHENA AVE | MERRITT | BRITISH COLUMBIA | V1K1B8 |  | 2016-05-03 | 2016-05-11 |  | 2016-07-06 | 1/18/2015: SIP available Nov 18, 2014 11/11/2014: Bell validation confirmed ADSL - MPLS upgrade required RBC to Advise david.lu: 7/9: pending MPLS due date - moved to Sep 1st as placeholder tentatively |  | 00000, 1700, 2940 |  | Unisys |  | Unisys - | 2016-04-06 | 2016-07-01 |  | 2015-04-20 |  |  |  | Erin Mcgregor | 2503151255 |  |  | BRITISH COLUMBIA | Dana McCombie | Timothy Carmack | 17 | 1 |  |  | 18 | Centrex |  | done | 9 | N | 3 |  | 250315 | TELUS | BC | Merritt | MRRTBC01RS1 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-01 | 2015-03-04 | 2 | Y | 2015-03-06 | Yes | 2015-10-26 | 2014-11-19 | 2016-07-01 | Telus | done | done | Complete | Complete | Priority - 50 | w02940br1 | 3M | 3000 | 10.136.7.1/25
P&CB | 802214 | Yes/Oui | 9459 | WETASKIWIN BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 4916 50TH AVE | WETASKIWIN | ALBERTA | T9A3P8 |  | 2016-05-02 | 2016-05-11 |  | 2016-07-06 | 1/18/2015: Sip Avail Nov 18 2014 |  | 8749, 9459, 10453, 14149 |  | Bell Canada |  |  | 2016-04-06 | 2016-07-01 | [5 empty] | William Taylor | 7803615269 |  |  | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 20 | 1 |  |  | 21 | Centrex |  | done | 10 |  | 4 |  | 780361 | TELUS | AB | Wetaskiwin | WTKWAB02RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-07-01 | 2015-03-20 | 2 | Y | 2015-03-30 | Yes | 2016-01-21 | 2015-04-21 | 2016-07-01 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w09459br1 | DSL | 1500 | 10.136.27.1/25
P&CB | 800218 | 2016-05-17 | 774 | EDMUNDSTON BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 48 ST FRANCIS ST | EDMUNDSTON | NEW BRUNSWICK | E3V1E3 |  | 2016-05-26 | 2016-06-23 |  | 2016-07-07 |  |  |  |  | Unisys |  |  | 2016-04-07 | 2016-07-04 | [5 empty] | Michel Martin | 5067351400 | Deborah Ouellette | 5067351411 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  |  |  | 506735 | ALIANT TELECOM (NB) | NB | Edmundston | EDMNNBSC73C | Regulated / Réglementé | Need PTN | 0 | 2016-07-02 | 2015-08-13 | 3 | Y | 2014-06-20 | Yes |  | Done | 2016-07-02 | Bell | 2016-03-23 | 2016-03-27 | OK | 102 | 2016-03-31 | e00774br1 | T1 | 1500 | 10.136.159.129/25
P&CB | 800503 | Yes/Oui | 1567 | FLIN FLON BR | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 94 MAIN ST | FLIN FLON | MANITOBA | R8A1K1 |  | 2016-05-03 | 2016-05-12 |  | 2016-07-07 |  |  | 1567, 9207, 13987, 14391, 15572 |  | Unisys |  |  | 2016-04-07 | 2016-07-04 | [5 empty] | Michael Yarowy | 2046871901 | Leah Evans | 2046871920 | MAN/SASK NORTHWEST ONTARIO | Justin Cornett | Rob Loeppky | 24 | 4 |  |  | 28 | Centrex |  | done | 12 |  |  |  | 204687 | MTS Inc. | MB | Flin Flon | FLFNMB01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-02 | 2015-05-05 | 2 | N | N/A | Yes | 2015-06-29 | 2014-06-25 | 2015-09-30 | Completed | 2015-02-06 |  | Complete | Complete | Sep 30 - Per Adam | w01567br1 | 2M | 1500 | 10.136.61.1/25
P&CB | 800673 | 2016-05-17 | 2093 | DIGBY BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | 51 WATER ST | DIGBY | NOVA SCOTIA | B0V1A0 |  | 2016-05-26 | 2016-06-23 |  | 2016-07-07 |  |  | 2093, 7373, 9274, 14535, 14913, 14931 |  | Unisys |  |  | 2016-04-07 | 2016-07-04 | [5 empty] | Fran MacDonald | 9022457224 | Iona Fox | 9022454774 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 25 | 4 |  |  | 29 | Centrex |  | done | 12 |  |  |  | 902245 | ALIANT TELECOM (NS) | NS | Digby | DGBYNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-02 | 2015-05-11 | 3 | Y | 2015-01-15 | Yes |  | Done | 2016-07-02 | Bell | 2016-03-09 | 2016-03-27 | OK | 102 | 2016-03-31 | e02093br1 | DSL | 1500 | 10.138.61.129/25
P&CB | 801583 | 2016-05-17 | 6163 | STELLARTON BRANCH | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | Closed | 254 FOORD ST | STELLARTON | NOVA SCOTIA | B0K1S0 |  | 2016-05-26 | 2016-06-23 |  | 2016-07-07 |  |  | 00000, 6163, 14445, 14535, 14931 |  | Unisys |  |  | 2016-04-07 | 2016-07-04 | [5 empty] | Corinnea McGuire | 9027557739 | Yeni Maclean | 9027557751 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 22 | 2 |  |  | 24 | Centrex |  | done | 10 |  |  |  | 902755 | ALIANT TELECOM (NS) | NS | New Glasgow | NWGLNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-02 | 2015-07-13 | 1 | Y | 2014-04-13 | no | [9 empty] | e06163br1 | 5M | 5000 | 10.137.34.1/25
P&CB | 800309 | Yes/Oui | 1109 | CROWSNEST PASS BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 12713 20TH AVE | BLAIRMORE | ALBERTA | T0K0E0 |  | 2016-05-05 | 2016-05-16 |  | 2016-07-11 | 1/18/2015 SIP Available Nov 2014 |  | 1109, 9955 |  | Unisys |  |  | 2016-04-11 | 2016-07-06 | [5 empty] | Ron Hiebert | 4035623361 |  |  | ALBERTA & TERRITORIES | Odell Sinclair | Dan Chipak | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  | 2 |  | 403562 | TELUS | AB | Crowsnest Pass | CTPSAB04RS0 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-06 | 2015-11-19 | 4 | Y | 2014-11-09 | Yes | 2015-12-02 | 2014-05-05 | 2016-07-06 |  | done | done | Complete | Complete | July 30 - 24 AB | w01109br1 | 5M | 5000 | 10.136.58.129/25
P&CB | 800707 | 2016-05-17 | 2203 | ELMSDALE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 178 HWY #214 | ELMSDALE | NOVA SCOTIA | B2S1H7 |  | 2016-05-30 | 2016-06-27 |  | 2016-07-11 |  |  |  |  | Unisys |  |  | 2016-04-11 | 2016-07-06 | [5 empty] | Susan Fitzgerald | 9028838215 | Amy Parker | 9028833425 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 24 | 1 |  |  | 25 | Centrex |  | done | 11 |  |  |  | 902883 | ALIANT TELECOM (NS) | NS | Elmsdale | EMDLNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-06 | 2015-07-14 | 4 | N | N/A | Yes | 2015-05-14 | 2015-02-17 | 2015-05-31 | Completed | 2015-04-22 |  | Complete | Complete | May 31 - per Adam | e02203br1 | 3M | 3000 | 10.138.63.1/25
P&CB | 800728 | 2016-05-17 | 2313 | GLACE BAY BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | 41 UNION ST | GLACE BAY | NOVA SCOTIA | B1A2P6 |  | 2016-05-30 | 2016-06-27 |  | 2016-07-11 |  |  | 00000, 2313, 9883, 14535 |  | Unisys |  |  | 2016-04-11 | 2016-07-06 | [5 empty] | Colleen Doyle | 9027946704 | Michelle Wilton | 9028423106 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 8 | 1 |  |  | 9 | Centrex |  | done | 6 |  | 4 |  | 902849 | ALIANT TELECOM (NS) | NS | Glace Bay | GLBANS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-06 | 2015-08-25 | 3 | N | N/A | Yes |  | Done | 2016-07-06 | Bell | 2016-04-08 | 2016-04-22 | OK | 80 | 2016-03-31 | e02313br1 | DSL | 1500 | 10.137.249.1/25
P&CB | 801571 | Yes/Oui | 6080 | DUNBAR & 26TH AVENUE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 17:00 | 16:00 | Closed | 4205 DUNBAR ST | VANCOUVER | BRITISH COLUMBIA | V6S2G1 |  | 2016-05-06 | 2016-05-16 |  | 2016-07-11 |  |  | 6080, 8890 9687, 14302, 14973 |  | Bell Canada |  |  | 2016-04-11 | 2016-07-06 | [5 empty] | Mark Johnston | 6042226812 | Juliet Lasher | 6042226804 | BRITISH COLUMBIA | Elaine Sanderson | Timothy Carmack | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  | 4 |  | 604222 | TELUS | BC | Vancouver | VANCBC02DS2 | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-07-06 | 2015-04-20 | 3 | Y | 2014-03-28 | Yes | 2015-04-23 | 2014-05-05 | 2015-08-01 | Telus - pending Contract |  |  | Complete | Complete | Aug 1 - 27 BC | w06080br1 | 5M | 5000 | 10.136.88.1/25
P&CB | 802192 | 2016-05-17 | 9353 | KELLIGREW BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 91 CONCEPTION BAY SOUTH HWY | CONCEPTION BAY SOUTH | NEWFOUNDLAND | A1W3A3 |  | 2016-05-30 | 2016-06-27 |  | 2016-07-11 |  |  | 9063, 9275, 9353, 14583, 15630 |  | Unisys |  |  | 2016-04-11 | 2016-07-06 | [5 empty] | Celia Brennan | 7098347823 | Pamela House | 7098346158 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 21 | 4 |  |  | 25 | Centrex |  | done | 11 |  |  |  | 709834 | ALIANT TELECOM (NF) | NL | Long Pond | MTPRNF01DS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-06 | 2015-08-15 | 2 | N | N/A | no | [9 empty] | e09353br1 | 3M | 3000 | 10.136.107.129/25
P&CB | 800625 | Yes/Oui | 1879 | GLAMORGAN SHOPPING CENTRE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 3919A RICHMOND RD SW | CALGARY | ALBERTA | T3E4P2 |  | 2016-05-06 | 2016-05-17 |  | 2016-07-12 |  |  | 0, 1218, 1879, 9955, 10448, 10449, 10450, 11632, 13349, 17182 |  | Bell Canada |  |  | 2016-04-12 | 2016-07-07 | [5 empty] | Brad Sterling | 4032922498 | Eva Cheung | 4032923804 | ALBERTA & TERRITORIES | Kathy Marrinan | Dan Chipak | 23 | 2 |  |  | 25 | Centrex |  | done | 11 |  | 10 |  | 403292 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-07-07 | 2015-08-04 | 1 | N | N/A | Yes | 2016-01-05 | 2014-05-05 | 2016-07-07 |  | done | done | Complete | Complete | July 30 - 24 AB | w01879br5 | Other | 1500 | 10.136.64.1/25
P&CB | 800846 | Yes/Oui | 2830 | WALNUT GROVE | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | Closed | 8843 204TH ST | LANGLEY | BRITISH COLUMBIA | V1M2K4 |  | 2016-05-09 | 2016-05-17 |  | 2016-07-12 |  |  | 00000, 80, 1830, 2830, 3316, 12069, 14415, 148929, 15398, 16953 |  | Bell Canada |  |  | 2016-04-12 | 2016-07-07 | [5 empty] | Bikram Gill | 6048822240 | Ashley Morrison | 6048822206 | BRITISH COLUMBIA | Michele Curley | Timothy Carmack | 26 | 3 |  |  | 29 | Centrex |  | done | 12 |  | 10 |  | 604882 | TELUS | BC | Fort Langley | FTLYBC01DS2 | (C) Regulated / Réglementé | 0 | 0 | 2016-07-07 | 2015-08-14 |  | Y | 2014-08-15 | Yes | 2015-11-25 | 2014-05-06 | 2016-07-07 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w02830br1 | 5M | 5000 | 10.136.70.1/25
P&CB | 800957 | 2016-05-17 | 3303 | QUINPOOL & OXFORD BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 6390 QUINPOOL RD | HALIFAX | NOVA SCOTIA | B3L4N2 |  | 2016-05-31 | 2016-06-28 |  | 2016-07-12 |  |  | 3303, 7666 |  | Unisys |  |  | 2016-04-12 | 2016-07-07 | [5 empty] | Paula Power | 9024214661 | Jen Kogon | 9024214658 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 5 | 32 |  |  | 37 | IP |  | done | 14 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no | [9 empty] | e03303br1 | 5M | 5000 | 10.199.49.1/25 | Y
P&CB | 801020 | 2016-05-17 | 3523 | INVERNESS BRANCH | 16:00 | 16:00 | 16:00 | 17:00 | 16:00 | Closed | Closed | 15794 CENTRAL AVE | INVERNESS | NOVA SCOTIA | B0E1N0 |  | 2016-05-31 | 2016-06-28 |  | 2016-07-12 |  |  |  |  | Unisys |  |  | 2016-04-12 | 2016-07-07 | [5 empty] | Robyn Morgan | 9022583916 |  |  | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902258 | ALIANT TELECOM (NS) | NS | Inverness | INVRNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-07 | 2015-07-13 | 2 | Y | 2014-12-12 | Yes |  | Done | 2016-07-07 | Bell | 2016-04-14 | 2016-04-28 | OK | 75 | 2016-03-31 | e03523br1 | DSL | 1500 | 10.138.64.129/25
P&CB | 801434 | 2016-05-17 | 5204 | SUMMERSIDE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 222 WATER ST | SUMMERSIDE | PRINCE EDWARD ISLAND | C1N2V5 |  | 2016-05-31 | 2016-06-28 |  | 2016-07-12 |  |  | 00000, 5064, 5204, 9044, 9278, 14187 |  | Unisys |  |  | 2016-04-12 | 2016-07-07 | [5 empty] | Boyce Murphy | 9024361121 | Shirley Dyment | 9024361140 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 22 | 3 |  |  | 25 | Centrex |  | done | 11 |  |  |  | 902436 | ALIANT TELECOM (PEI) | PE | Summerside | SMSDPE01RS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-07 | 2014-11-06 | 3 | N | N/A | no | [9 empty] | e05204br1 | 5M | 5000 | 10.137.32.1/25
P&CB | 800440 | 2016-05-17 | 1434 | MOUNTAIN ROAD BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 719 MOUNTAIN RD | MONCTON | NEW BRUNSWICK | E1C2P4 |  | 2016-06-01 | 2016-06-29 |  | 2016-07-13 |  |  | 1426, 1434, 8014, 9279, 10108, 14582, 16932 |  | Unisys |  |  | 2016-04-13 | 2016-07-08 | [5 empty] | Christopher Lorde | 5068564832 | Devin Mazerolle | 5068703721 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 45 | 5 |  |  | 50 | Centrex |  | done | 18 |  |  |  | 506856 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | 2016-07-08 | 2014-12-18 | 2 | N | N/A | no | [9 empty] | e01434br1 | 5M | 5000 | 10.137.23.1/25
P&CB | 800751 | 2016-05-17 | 2423 | GUYSBOROUGH BRANCH | 15:00 | 15:00 | 15:00 | 15:00 | 15:00 | Closed | Closed | 110 MAIN ST | GUYSBOROUGH | NOVA SCOTIA | B0H1N0 |  | 2016-06-01 | 2016-06-29 |  | 2016-07-13 |  |  | 2423 |  | Unisys |  |  | 2016-04-13 | 2016-07-08 | [9 empty] | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 10 | 1 |  |  | 11 | Centrex |  | done | 6 |  |  |  | 902533 | ALIANT TELECOM (NS) | NS | Guysborough | GYBONS03RS2 | Regulated / Réglementé | 0 | 0 | 2016-07-08 | 2014-12-09 | 1 | N | N/A | no | [9 empty] | e02423br1 | T1 | 1500 | 10.136.167.129/25
P&CB | 800980 | 2016-05-17 | 3353 | HALIFAX SHOPPING CENTRE | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 7001 MUMFORD RD | HALIFAX | NOVA SCOTIA | B3L2H8 |  | 2016-06-01 | 2016-06-29 |  | 2016-07-13 |  |  | 3, 1506, 3353, 7666, 9593 |  | Unisys |  |  | 2016-04-13 | 2016-07-08 | [5 empty] | Darlene Ashley | 9024218965 | Jeannine Vautour | 9024218451 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 40 | 6 |  |  | 46 | Centrex |  | done | 17 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-08 | 2015-07-14 | 4 | Y | 2014-03-30 | Yes | 2015-05-04 | 2015-02-18 | 2015-05-31 | Completed | Completed |  | Complete | Complete | May 31 - per Adam | e03353br1 | 3M | 3000 | 10.136.107.1/25
P&CB | 801389 | Yes/Oui | 5000 | PLAZA 33 BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 301 HWY 33 WEST | KELOWNA | BRITISH COLUMBIA | V1X1X8 |  | 2016-05-10 | 2016-05-18 |  | 2016-07-13 | Oct 21: Cutover chg fr Jan 12, 2015 to TBD pending cabling and switch upgrade. Feb 2nd 2015: 'site requires recabling due to ATM room not large enough to accommodate necessary equipment |  | 5000, 8120, 8890, 10695, 13054, 14969, 15881, 16875 |  | Unisys |  |  | 2016-04-13 | 2016-07-08 |  | 2014-10-09 |  |  |  | Kathy Reeves | 2504260309 | Natasha Sazonova | 2504912888 | BRITISH COLUMBIA | Jerry Goncalves | Timothy Carmack | 26 | 2 |  |  | 28 | Centrex |  | done | 12 |  | 8 |  | 250491 | TELUS | BC | Rutland | RTLDBC01RS1 | (W) Unregulated / Non Réglementé | 250-451-0517 | rutland_01_2504510517 | 2016-07-08 | 2015-03-20 |  | Y | 2015-03-20 | Yes |  | 2014-05-05 | 2016-07-08 | Telus - damaged mall conduit | TBD - June forecast |  | LATE | -99999 | Aug 1 - 27 BC | w05000br5 | Other | 1500 | 10.136.83.1/25
P&CB | 801695 | Yes/Oui | 7049 | LACOMBE BRANCH | 17:00 | 17:00 | 17:00 | 18:00 | 18:00 | 16:00 | Closed | 5022 50TH AVE | LACOMBE | ALBERTA | T4L2L1 |  | 2016-05-09 | 2016-05-18 |  | 2016-07-13 | 1/18/2015: Sip avial Nov 3 2014 |  | 00000, 7049, 9882, 13998, 14578 |  | Bell Canada |  |  | 2016-04-13 | 2016-07-08 | [7 empty] | Marcia Varley | 4037821167 | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 15 | 1 |  |  | 16 | Centrex |  | done | 8 |  | 5 |  | 403782 | TELUS | AB | Lacombe | LCMBAB02RS0 | (W) Regulated / Réglementé | 0 | 0 | 2016-07-08 | 2015-07-15 | 3 | Y | 2014-05-31 | Yes | 2016-01-11 | 2015-04-21 | 2016-07-08 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w07049br1 | DSL | 1500 | 10.136.25.1/25
P&CB | 800997 | 2016-05-17 | 3413 | SPRING GARDEN & SUMMER BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 5855 SPRING GARDEN RD | HALIFAX | NOVA SCOTIA | B3H4S2 |  | 2016-06-02 | 2016-06-30 |  | 2016-07-14 |  |  | 00000, 1506, 3413, 7666, 9593, 9883, 12056, 15933, 15977 |  | Unisys |  |  | 2016-04-14 | 2016-07-11 | [5 empty] | Harry Grant | 9024218460 | Stephanie West | 9024218133 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 32 | 3 |  |  | 35 | Centrex |  | done | 14 |  |  |  | 902425 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-09 | 2015-04-29 | 5 | N | N/A | Yes | 2015-06-15 | 2015-04-21 | 2015-08-01 | Completed | 2015-06-03 |  | Complete | Complete | Aug 1 - per Adam | e03413br1 | T1 | 1500 | 10.136.48.1/25
P&CB | 801443 | 2016-05-17 | 5283 | NORTH SYDNEY BRANCH | 18:00 | 18:00 | 18:00 | 20:00 | 18:00 | 16:00 | Closed | 291 COMMERCIAL ST | NORTH SYDNEY | NOVA SCOTIA | B2A1B9 |  | 2016-06-02 | 2016-06-30 |  | 2016-07-14 | 11/11/2014: Bell validation confirmed ADSL - MPLS upgrade required RBC to Advise |  | 00000, 5283, 9076, 9593, 9883, 14535 |  | Unisys |  |  | 2016-04-14 | 2016-07-11 | [7 empty] | Lynette Sampson | 9027945047 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 19 | 3 |  |  | 22 | Centrex |  | done | 10 |  |  |  | 902794 | ALIANT TELECOM (NS) | NS | North Sydney | NSYDNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-09 | 2015-01-19 | 2 | N | N/A | Yes | 2015-01-14 | 2014-11-19 |  |  |  |  | Complete | Complete |  | e05283br1 | T1 | 1500 | 10.138.72.1/25
P&CB | 801596 | Yes/Oui | 6247 | THE PAS BRANCH | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | 16:00 | 301 EDWARDS AVE-PO BOX 1080 | THE PAS | MANITOBA | R9A1L1 |  | 2016-05-10 | 2016-05-19 |  | 2016-07-14 | 1/18/2015: SIP availabe Jan 12, 2015 david.lu: 7/14: updated to April 2016 as per Linda's update 7/8: RBC advised pre-requisit upgrades can be done on time. Bell tentatively put new date on Aug 12. 7/2: postponed to april 1/ 2016 due to pending MPLS upgrade (elaine's note on 6/30) 5/28: moved from 6/4 to sept 1 pending MPLS upgrade updates |  | 6247, 9940 |  | Unisys |  | Unisys aware | 2016-04-14 | 2016-07-11 |  | 2015-03-25 | Jim Pelletier |  |  |  | 204-627-3454 |  |  | MAN/SASK NORTHWEST ONTARIO | Justin Cornett | Rob Loeppky | 19 | 1 |  |  | 20 | Centrex |  | done | 9 | Y | 2 |  | 204627 | MTS Inc. | MB | The Pas | TPASMB01RS1 | (W) Regulated / Réglementé | 0 | 0 | 2016-07-09 | 2015-05-04 | 2 | N | N/A | Yes | 2015-08-13 | 2014-06-11 | 2016-07-09 | Completed | 2015-07-03 |  | Complete | Complete | Priority - 50 | w06247br1 | 5M | 5000 | 10.136.89.1/25
P&CB | 802150 | 2016-05-17 | 9303 | HOLYROOD BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 396 CONCEPTION BAY HWY-ROUTE 60 | HOLYROOD | NEWFOUNDLAND | A0A2R0 |  | 2016-06-02 | 2016-06-30 |  | 2016-07-14 |  |  | 00000, 9303 |  | Unisys |  |  | 2016-04-14 | 2016-07-11 | [5 empty] | Lena Phillips | 7092291233 |  |  | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 8 | 1 |  |  | 9 | Centrex |  | done | 6 |  |  |  | 709229 | ALIANT TELECOM (NF) | NL | Harbour Main | HRMNNF01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-09 | 2015-08-17 | 1 | N | N/A | no | [9 empty] | e09303br1 | T1 | 1500 | 10.136.114.1/25
P&CB | 800405 | 2016-05-17 | 1374 | MAIN BR - MONCTON BLUE CROSS CTR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 644 MAIN ST | MONCTON | NEW BRUNSWICK | E1C1E2 |  | 2016-06-06 | 2016-07-04 |  | 2016-07-18 |  |  | 1374, 1426, 4435, 7474, 8014, 9279, 9314, 10047, 14163, 14582, 15997, 16551, 16972, 17387 |  | Unisys |  |  | 2016-04-18 | 2016-07-13 | [7 empty] | Antonio Mekary | 5068596208 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 41 | 9 |  |  | 50 | Centrex |  | done | 18 |  |  |  | 506856 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | 2016-07-13 | 2015-09-03 | 3 | N | N/A | no | [9 empty] | e01374br1 | 5M | 5000 | 10.137.112.129/25
P&CB | 800496 | 2016-05-17 | 1554 | HEMLOCK SQ BR - RBD | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 9 PEAKVIEW WAY | HALIFAX | NOVA SCOTIA | B3M0G2 |  | 2016-06-06 | 2016-07-04 |  | 2016-07-18 |  |  | 1506, 1554, 9593, 9843, 14163, 15977, 17165 |  | Unisys |  |  | 2016-04-18 | 2016-07-13 | [7 empty] | Negin Hamed | 9028325778 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 8 | 29 |  |  | 37 | IP |  | done | 14 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | N/A | N/A | N/A | N | N/A | no |  |  | 2016-03-31 | [6 empty] | e01554br1 | 5M | 5000 | 10.199.50.129/25 | Y
P&CB | 800899 | Yes/Oui | 3040 | MISSION BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 33114 1ST AVE | MISSION | BRITISH COLUMBIA | V2V1G4 |  | 2016-05-13 | 2016-05-23 |  | 2016-07-18 | 1/18/2015: Sip avial Nov 3 2014 |  | 00000, 3040, 3316, 7700, 8890, 14829, 14971 |  | Bell Canada |  |  | 2016-04-18 | 2016-07-13 | [5 empty] | Kamaljit Bhatti | 6048204722 |  |  | BRITISH COLUMBIA | Michele Curley | Timothy Carmack | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  | 7 |  | 604820 | TELUS | BC | Mission | MSSNBC01DS2 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-13 | 2014-12-04 |  | Y | 2014-12-04 | Yes | 2015-11-26 | 2015-06-26 | 2016-07-13 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w03040br1 | 5M | 5000 | 10.136.21.1/25
P&CB | 801318 | 2016-05-17 | 4513 | METEGHAN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 8249 HIGHWAY 1/ROUTE #1 | METEGHAN | NOVA SCOTIA | B0W2J0 |  | 2016-06-06 | 2016-07-04 |  | 2016-07-18 |  |  | 4513 |  | Unisys |  |  | 2016-04-18 | 2016-07-13 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902645 | ALIANT TELECOM (NS) | NS | Meteghan | MTGNNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-13 | 2015-05-11 | 2 | Y | 2015-01-29 | no | [9 empty] | e04513br1 | T1 | 1500 | 10.136.172.1/25
P&CB | 801989 | Yes/Oui | 8589 | SLAVE LAKE BRANCH | 17:00 | 17:00 | 17:00 | 19:00 | 18:00 | closed | Closed | 204 MAIN ST N | SLAVE LAKE | ALBERTA | T0G2A0 |  | 2016-05-12 | 2016-05-23 |  | 2016-07-18 |  |  | 00000, 1625, 8589, 9955, 13994 |  | Unisys |  |  | 2016-04-18 | 2016-07-13 | [5 empty] | Bill Plowright | 7808498140 | Judy Yaro | 7808498120 | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 19 | 4 |  |  | 23 | Centrex |  | done | 10 |  | 5 |  | 780849 | TELUS | AB | Slave Lake | SELKAB01RS0 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-13 | 2014-09-21 |  | Y | 2014-09-21 | Yes | 2016-01-06 | 2015-04-21 | 2016-07-13 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w08589br1 | DSL | 1500 | 10.136.1.129/25
P&CB | 800935 | Yes/Oui | 3199 | COCHRANE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 130 1ST AVE W-PO BOX 190 | COCHRANE | ALBERTA | T4C1A5 |  | 2016-05-13 | 2016-05-24 |  | 2016-07-19 | david.lu: 7/2: postponed to april 1/ 2016 due to pending MPLS upgrade (elaine's note on 6/30) 5/28: moved from 6/4 to sept 1 pending MPLS upgrade updates |  | 00000, 1231, 3199, 4013, 9878, 9955, 10449, 13936, 14255, 16376, 16921 |  | Bell Canada |  | Valerie Tobler 403-585-8670 | 2016-04-19 | 2016-07-14 |  | 2015-03-25 |  |  |  | Lindsay Doiron | 4038512182 | Ryan Sowtis | 4038512198 | ALBERTA & TERRITORIES | Rhonda Graham | Dan Chipak | 32 | 2 |  |  | 34 | Centrex |  | done | 13 | Y | 11 |  | 403851 | TELUS | AB | Cochrane | CCHRAB01RS3 | (I) Unregulated / Non Réglementé | 0 | 0 | 2016-07-14 | 2015-05-07 | 2 | N | N/A | Yes | 2015-10-21 | 2015-02-18 | 2016-07-14 | Bell | done | done | Complete | Complete | Priority - 50 | w03199br1 | 3M | 3000 | 10.136.19.1/25
P&CB | 801138 | Yes/Oui | 3880 | NO 3 & ACKROYD | 19:00 | 19:00 | 19:00 | 19:00 | 18:00 | 16:00 | Closed | 8171 ACKROYD RD | RICHMOND | BRITISH COLUMBIA | V6X3K1 |  | 2016-05-16 | 2016-05-24 |  | 2016-07-19 |  |  | 1660, 1830, 3880, 10690, 12071, 14966, 14989 |  | Bell Canada |  |  | 2016-04-19 | 2016-07-14 | [5 empty] | Danny Tseng | 6046688888 | Thomas Chung | 6046655800 | BRITISH COLUMBIA | Wendy Palmer | Timothy Carmack | 34 | 3 |  |  | 37 | Centrex |  | done | 14 |  | 7 |  | 604665 | TELUS | BC | Vancouver | VANCBC014XD | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-07-14 | 2015-09-10 | 3 | N | N/A | Yes | 2015-06-23 | 2014-05-06 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w03880br1 | 5M | 5000 | 10.136.78.129/25
P&CB | 801163 | 2016-05-17 | 3963 | LIVERPOOL BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 209 MAIN ST | LIVERPOOL | NOVA SCOTIA | B0T1K0 |  | 2016-06-07 | 2016-07-05 |  | 2016-07-19 |  |  | 00000, 3963, 9843, 14931 |  | Unisys |  |  | 2016-04-19 | 2016-07-14 | [5 empty] | Peter Dimmell | 9023546113 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  |  |  | 902354 | ALIANT TELECOM (NS) | NS | Liverpool | LVPLNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-14 | 2015-05-06 | 2 | N | N/A | Yes |  | Done | 2016-07-14 | Bell | 2016-03-11 | 2016-03-27 | OK | 114 | 2016-03-31 | e03963br1 | DSL | 1500 | 10.138.67.1/25
P&CB | 801203 | 2016-05-17 | 4183 | LOUISBOURG BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 7509 MAIN ST | LOUISBOURG | NOVA SCOTIA | B1C1H8 |  | 2016-06-07 | 2016-07-05 |  | 2016-07-19 | 11/11/2014: Bell validation confirmed ADSL - MPLS upgrade required RBC to Advise |  | 4183 |  | Unisys |  |  | 2016-04-19 | 2016-07-14 | [9 empty] | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902733 | ALIANT TELECOM (NS) | NS | Louisbourg | LSBGNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-14 | 2015-01-20 | 2 | N | N/A | Yes | 2015-01-13 | 2014-11-19 |  |  |  |  | Complete | Complete |  | e04183br1 | T1 | 1500 | 10.138.69.1/25
P&CB | 802224 | 2016-05-17 | 9573 | FRESHWATER & CROSBIE BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 337 FRESHWATER RD-PO BOX 8277 | ST JOHNS | NEWFOUNDLAND | A1B3N4 |  | 2016-06-07 | 2016-07-05 |  | 2016-07-19 |  |  | 00000, 8133, 9063, 9275, 9503, 9573, 14583 |  | Unisys |  |  | 2016-04-19 | 2016-07-14 | [5 empty] | Jodi Pritchard | 7095764263 | Catherine Estabrooks | 7097588622 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 18 | 2 |  |  | 20 | Centrex |  | done | 9 |  |  |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-07-14 | 2015-08-25 | 0 | Y | 2014-04-20 | no | [9 empty] | e09573br1 | 5M | 5000 | 10.137.119.1/25
P&CB | 801184 | 2016-05-17 | 4073 | LOCKEPORT BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 25A BEECH ST | LOCKEPORT | NOVA SCOTIA | B0T1L0 |  | 2016-06-08 | 2016-07-06 |  | 2016-07-20 |  |  | 4073 |  | Unisys |  |  | 2016-04-20 | 2016-07-15 | [9 empty] | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 9 | 1 |  |  | 10 | Centrex |  | done | 6 |  |  |  | 902656 | ALIANT TELECOM (NS) | NS | Lockeport | LCPTNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-15 | 2015-07-17 | 0 | Y | 2014-08-31 | no | [9 empty] | e04073br1 | T1 | 1500 | 10.136.171.129/25
P&CB | 801227 | 2016-05-17 | 4293 | LUNENBURG BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | 84 PELHAM ST | LUNENBURG | NOVA SCOTIA | B0J2C0 |  | 2016-06-08 | 2016-07-06 |  | 2016-07-20 |  |  | 00000, 4293 |  | Unisys |  |  | 2016-04-20 | 2016-07-15 | [5 empty] | Kristine Vidito | 9026347601 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 18 | 3 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 902634 | ALIANT TELECOM (NS) | NS | Lunenburg | LNBGNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-15 | 2015-05-06 | 3 | N | N/A | Yes |  | Done | 2016-07-15 | Bell | 2016-03-14 | 2016-03-27 | OK | 115 | 2016-03-31 | e04293br1 | DSL | 1500 | 10.138.69.129/25
P&CB | 801271 | Yes/Oui | 4400 | PORT MOODY BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 218 NEWPORT DR | PORT MOODY | BRITISH COLUMBIA | V3H5B9 |  | 2016-05-17 | 2016-05-25 |  | 2016-07-20 |  |  | 00000, 1653, 4400, 11687, 17440, 17488 |  | Bell Canada |  |  | 2016-04-20 | 2016-07-15 | [5 empty] | George Bountalas | 6045525020 | Janet Phillips | 6045525013 | BRITISH COLUMBIA | Mauro Susi | Timothy Carmack | 19 | 3 |  |  | 22 | Centrex |  | done | 10 |  | 6 |  | 604552 | TELUS | BC | Port Coquitlam | PTCMBC02DS2 | (C) Regulated / Réglementé | 778-284-6985 | portco_01_7782846985 | 2016-07-15 |  |  | N | N/A | Yes | 2015-12-09 | 2014-05-05 | 2016-07-15 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w04400br5 | Other | 1500 | 10.136.81.1/25
P&CB | 801734 | Yes/Oui | 7379 | 1139 MAYOR MAGRATH DRIVE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 1139 MAYOR MAGRATH DR | LETHBRIDGE | ALBERTA | T1K2P9 |  | 2016-05-16 | 2016-05-25 |  | 2016-07-20 |  |  | 00000, 285, 7379, 10450, 13349, 13486, 17182 |  | Unisys |  |  | 2016-04-20 | 2016-07-15 | [5 empty] | Brian Bradley | 4033823950 | Heather Harris | 4033823805 | ALBERTA & TERRITORIES | Odell Sinclair | Dan Chipak | 24 | 1 |  |  | 25 | Centrex |  | done | 11 |  | 7 |  | 403382 | TELUS | AB | Lethbridge | LTBRAB02CG2 | (I) Regulated / Réglementé | 403-388-3723 | lethbridge_01_4033883723 | 2016-07-15 | 2014-07-07 | 2 | Y | 2014-09-21 | Yes | 2015-07-28 | 2014-05-05 | 2016-07-15 | Completed |  |  | Complete | Complete | July 30 - 24 AB | w07379br1 | 5M | 5000 | 10.136.91.1/25
DS | 803028 | 2016-05-17 | 90288 | CONFEDERATION MALL | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 134 KENT ST SUITE #602 PO BOX #276 | CHARLOTTETOWN | PRINCE EDWARD ISLAND | C1A7K4 |  | 2016-06-08 | 2016-07-06 |  | 2016-07-20 |  |  | 90288 |  | Unisys |  |  | 2016-04-20 | 2016-07-15 |  |  | Wade Gregory | Karen Sheidow | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 26 | 3 |  |  | 29 | Centrex |  | done | 15 |  | 1 |  | 902628 | ALIANT TELECOM (PEI) | PE | Charlottetown | CHTWPE01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-15 | 2014-12-04 | 1 | N | N/A | no | [9 empty] | e90288vr1 | 5M | 5000 | 10.137.177.129/25
P&CB | 800367 | 2016-05-17 | 1264 | WESTWIND PLACE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 800 FAIRVILLE BLVD | SAINT JOHN | NEW BRUNSWICK | E2M5T4 |  | 2016-06-09 | 2016-07-07 |  | 2016-07-21 |  |  | 1264, 8014, 9404 |  | Unisys |  |  | 2016-04-21 | 2016-07-18 | [5 empty] | Craig Allison | 5066313410 | Pam Allen | 5066313442 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 22 | 1 |  |  | 23 | Centrex |  | done | 10 |  |  |  | 506632 | ALIANT TELECOM (NB) | NB | Saint John | STJHNBSU63A | Unregulated / Non Réglementé | 0 | 0 | 2016-07-16 | 2015-08-11 | 2 | N | N/A | no | [9 empty] | e01264br1 | 5M | 5000 | 10.137.246.1/25
P&CB | 801052 | 2016-05-17 | 3633 | KENTVILLE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 63 WEBSTER ST | KENTVILLE | NOVA SCOTIA | B4N1H4 |  | 2016-06-09 | 2016-07-07 |  | 2016-07-21 |  |  | 3633, 9883, 14445, 14535, 14913, 16665 |  | Unisys |  |  | 2016-04-21 | 2016-07-18 | [5 empty] | John Lawrence | 9026793896 | Linda Affleck | 9026793857 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 28 | 4 |  |  | 32 | Centrex |  | done | 13 |  |  |  | 902798 | ALIANT TELECOM (NS) | NS | Windsor | WNDSNS01RS1 | Unregulated / Non Réglementé | 519-255-9607 | windsor_on_01_5192559607 | 2016-07-16 | 2015-05-01 | 2 | N | N/A | Yes | 2014-12-01 | Done | 2016-07-16 | Bell | done | done | Complete | Complete | 2016-03-31 | e03633br1 | T1 | 1500 | 10.137.27.129/25
P&CB | 801524 | 2016-05-17 | 5833 | ST PETERS BRANCH | 16:00 | 16:00 | 16:00 | 17:00 | 17:00 | closed | Closed | 9955 GRENVILLE ST | ST PETERS | NOVA SCOTIA | B0E3B0 |  | 2016-06-09 | 2016-07-07 |  | 2016-07-21 |  |  | 5833 |  | Unisys |  |  | 2016-04-21 | 2016-07-18 | [5 empty] | Joan Burke | 9025352018 |  |  | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902535 | ALIANT TELECOM (NS) | NS | St Peters | NWGLNS01CG0 | Regulated / Réglementé | 0 | 0 | 2016-07-16 | 2015-07-13 | 2 | Y | 2014-11-14 | Yes |  | Done | 2016-07-16 | Bell | 2016-04-20 | 2016-05-04 | OK | 78 | 2016-03-31 | e05833br1 | DSL | 1500 | 10.138.73.129/25
P&CB | 801611 | Yes/Oui | 6397 | VIRDEN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 229 7TH AVE S-PO BOX 1750 | VIRDEN | MANITOBA | R0M2C0 |  | 2016-05-17 | 2016-05-26 |  | 2016-07-21 |  |  | 3349, 5811, 6397, 15572 |  | Unisys |  |  | 2016-04-21 | 2016-07-18 | [5 empty] | Glen Grieve | 2047484060 |  |  | MAN/SASK NORTHWEST ONTARIO | Justin Cornett | Rob Loeppky | 12 | 1 |  |  | 13 | Centrex |  | done | 7 |  |  |  | 204748 | MTS Inc. | MB | Virden | VRDNMB01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-16 | 2015-04-28 | 3 | N | N/A | no | [9 empty] | w06397br1 | 5M | 5000 | 10.138.123.1/25
P&CB | 800806 | Yes/Oui | 2649 | BRITANNIA BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 807 49TH AVE SW | CALGARY | ALBERTA | T2S1G8 |  | 2016-05-19 | 2016-05-30 |  | 2016-07-25 |  |  | 2649, 9955, 10448, 10450, 14256, 17182 |  | Bell Canada |  |  | 2016-04-25 | 2016-07-20 | [5 empty] | Selma Franko | 4032922387 | Lynn Harman | 4032922372 | ALBERTA & TERRITORIES | Kathy Marrinan | Dan Chipak | 17 | 3 |  |  | 20 | Centrex |  | done | 9 |  | 6 |  | 403292 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-07-20 | 2015-01-15 | 3 | N | N/A | Yes | 2015-10-20 | 2014-05-06 | 2016-07-20 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w02649br1 | 5M | 5000 | 10.136.53.129/25
P&CB | 801341 | Yes/Oui | 4670 | QUALICUM BEACH BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 133 WEST 2ND AVE | QUALICUM BEACH | BRITISH COLUMBIA | V9K1T1 |  | 2016-05-20 | 2016-05-30 |  | 2016-07-25 | 1/18/2015: Sip avial Nov 3 2014 |  | 4670 |  | Bell Canada |  |  | 2016-04-25 | 2016-07-20 | [7 empty] | Kaajal Manhas | 2507524016 | BRITISH COLUMBIA | Heather Marshak | Timothy Carmack | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  | 1 |  | 250752 | TELUS | BC | Qualicum | QLCMBC01RS1 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-20 | 2014-09-25 |  | Y | 2014-09-25 | Yes | 2015-11-12 | Done | 2016-07-20 | Telus | done | done | Complete | Complete | Aug 1 - 27 BC | w04670br1 | 5M | 5000 | 10.136.113.129/25
P&CB | 801456 | 2016-05-17 | 5393 | PARRSBORO BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 188 MAIN ST | PARRSBORO | NOVA SCOTIA | B0M1S0 |  | 2016-06-13 | 2016-07-11 |  | 2016-07-25 |  |  |  |  | Unisys |  |  | 2016-04-25 | 2016-07-20 | [5 empty] | Cindy Roberts | 9022543900 |  |  | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 8 | 1 |  |  | 9 | Centrex |  | done | 6 |  |  |  | 902254 | ALIANT TELECOM (NS) | NS | Parrsboro | PRBONS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-20 | 2014-08-15 | 2 | Y | 2014-07-06 | Yes |  | Done | 2016-07-20 | Bell | 2016-04-11 | 2016-04-25 | OK | 91 | 2016-03-31 | e05393br1 | DSL | 1500 | 10.138.72.129/25
P&CB | 801549 | 2016-05-17 | 5943 | SHERBROOKE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 6 MAIN ST | SHERBROOKE | NOVA SCOTIA | B0J3C0 |  | 2016-06-13 | 2016-07-11 |  | 2016-07-25 |  |  |  |  | Unisys |  |  | 2016-04-25 | 2016-07-20 | [9 empty] | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 10 |  |  |  | 10 | Centrex |  | done | 6 |  |  |  | 902522 | ALIANT TELECOM (NS) | NS | Sherbrooke | SHBKNS03RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-20 | 2014-12-08 | 2 | N | N/A | no | [9 empty] | e05943br1 | T1 | 1500 | 10.136.174.129/25
P&CB | 802198 | 2016-05-17 | 9403 | PLACENTIA MALL BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 61 BLOCKHOUSE ROAD | PLACENTIA | NEWFOUNDLAND | A0B2Y0 |  | 2016-06-13 | 2016-07-11 |  | 2016-07-25 |  |  | 9403 |  | Unisys |  |  | 2016-04-25 | 2016-07-20 | [5 empty] | Kay Smith | 7092270062 | Michelle Healey | 7092270063 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 19 | 1 |  |  | 20 | Centrex |  | done | 9 |  |  |  | 709227 | ALIANT TELECOM (NF) | NL | Freshwater | FHWRNF01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-20 | 2015-08-12 | 1 | N | N/A | no | [9 empty] | e09403br1 | T1 | 1500 | 10.136.186.129/25
P&CB | 800543 | 2016-05-17 | 1654 | PLASTER ROCK BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 199 MAIN ST | PLASTER ROCK | NEW BRUNSWICK | E0J1W0 |  | 2016-06-14 | 2016-07-12 |  | 2016-07-26 |  |  |  |  | Unisys |  |  | 2016-04-26 | 2016-07-21 | [9 empty] | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 7 | 1 |  |  | 8 | Centrex |  | done | 5 |  |  |  | 506356 | ALIANT TELECOM (NB) | NB | Plaster Rock | PLRKNBSCRS0 | Regulated / Réglementé | 0 | 0 | 2016-07-21 | 2015-01-14 | 0 | Y | 2014-05-04 | no | [9 empty] | e01654br1 | T1 | 1500 | 10.136.164.1/25
P&CB | 801803 | 2016-05-17 | 7703 | WOLFVILLE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 437 MAIN STREET | WOLFVILLE | NOVA SCOTIA | B4P1E1 |  | 2016-06-14 | 2016-07-12 |  | 2016-07-26 |  |  | 00000, 7703, 9843, 14445, 14535, 14931 |  | Unisys |  |  | 2016-04-26 | 2016-07-21 | [5 empty] | Annette Leblanc | 9025426100 | Charlotte Dorey | 9025426106 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  | 6 |  | 902542 | ALIANT TELECOM (NS) | NS | Wolfville | WFVLNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-21 | 2015-04-30 | 2 | N | N/A | Yes |  | Done | 2016-07-21 | Bell -- pending circuit install | 2016-03-14 | 2016-03-28 | OK | 120 | 2016-03-31 | e07703br1 | DSL | 1500 | 10.138.76.129/25
P&CB | 801837 | Yes/Oui | 7840 | VANDERHOOF BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 2517 BURRARD AVE | VANDERHOOF | BRITISH COLUMBIA | V0J3A0 |  | 2016-05-23 | 2016-05-31 |  | 2016-07-26 | 1/18/2015: SIP available Nov 18, 2014 |  | 7700, 7840, 13055 |  | Unisys |  |  | 2016-04-26 | 2016-07-21 | [5 empty] | Lonny Wiebe | 2505677206 | Candace Klassen | 2505677211 | BRITISH COLUMBIA | Dana McCombie | Timothy Carmack | 21 | 3 |  |  | 24 | Centrex |  | done | 10 |  | 3 |  | 250567 | TELUS | BC | Vanderhoof | VRHFBC01RS2 | (W) Regulated / Réglementé | 0 | 0 | 2016-07-21 | 2015-07-17 | 1 | N | N/A | Yes | 2015-05-21 | 2014-08-25 | 2015-08-01 | Completed | 2015-04-24 |  | Complete | Complete | Aug 1 - 27 BC | w07840br1 | 5M | 5000 | 10.136.224.1/25
P&CB | 802099 | Yes/Oui | 9249 | THREE HILLS BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 501 MAIN ST | THREE HILLS | ALBERTA | T0M2A0 |  | 2016-05-20 | 2016-05-31 |  | 2016-07-26 |  |  | 9249 |  | Bell Canada |  |  | 2016-04-26 | 2016-07-21 | [5 empty] | Marnie Graham | 4034438900 |  |  | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 12 | 1 |  |  | 13 | Centrex |  | done | 7 |  |  |  | 403443 | TELUS | AB | Three Hills | THHLAB01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-21 | 2015-08-05 | 2 | Y | 2014-02-14 | Yes |  | 2014-08-25 | 2015-09-30 | Telus -- Permits pending, CRE Involved | TBD - June forecast |  | LATE | -99999 | Sep 30 - Per Adam | w09249br1 | DSL | 1500 | 10.136.13.129/25
DS | 803020 | 2016-05-17 | 90270 | INC-HALIFAX | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 410 MAIN STREET | WOLFVILLE | NOVA SCOTIA | B4P1C9 |  | 2016-06-14 | 2016-07-12 |  | 2016-07-26 |  |  | 90270 |  | Unisys |  |  | 2016-04-26 | 2016-07-21 |  |  | Stewart Robinson | Emily Hynes; Barbara Alward | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 6 | 5 |  |  | 11 | Centrex |  | done | 8 |  | 1 |  | 902893 | ALIANT TELECOM (NS) | NS | Truro | HLFXNS01CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-21 | 2014-12-16 | 2 | N | N/A | no | [9 empty] | e90270vr3 | 5M | 5000 | 10.138.110.1/25 | Y | 4
P&CB | 800166 | Yes/Oui | 560 | BURNS LAKE BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 354 YELLOWHEAD HWY 16-PO BOX 2 | BURNS LAKE | BRITISH COLUMBIA | V0J1E0 |  | 2016-05-24 | 2016-06-01 |  | 2016-07-27 | 1/18/2015: Sip Avail Nov 18 2014 |  | 00000, 560, 4640 |  | Unisys |  |  | 2016-04-27 | 2016-07-22 | [5 empty] | Alice Harris | 2506925758 | Joyce Ashford | 2506925750 | BRITISH COLUMBIA | Jerry Goncalves | Timothy Carmack | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  | 3 |  | 250692 | TELUS | BC | Burns Lake | BULKBC01RS1 | (I) Regulated / Réglementé | Need PTN | 0 | 2016-07-22 | 2015-07-02 | 3 | Y | 2015-05-15 | Yes |  | 2015-06-25 | 2016-07-22 | Telus - Pending | TBD - June forecast |  | LATE | -99999 | Aug 1 - 27 BC | w00560br1 | DSL | 1500 | 10.136.234.1/25
P&CB | 800492 | 2016-05-17 | 1544 | MIRAMICHI MAIN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 335 PLEASANT ST | MIRAMICHI | NEW BRUNSWICK | E1V3M5 |  | 2016-06-15 | 2016-07-13 |  | 2016-07-27 |  |  | 00000, 1426, 1544, 7474, 10108, 14446 |  | Unisys |  |  | 2016-04-27 | 2016-07-22 | [5 empty] | Kevin Crowder | 5066270839 | Sherri Blakely | 5066270855 | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 26 | 2 |  |  | 28 | Centrex |  | done | 12 |  |  |  | 506627 | ALIANT TELECOM (NB) | NB | Miramichi | NWCSNBSC62A | Unregulated / Non Réglementé | 0 | 0 | 2016-07-22 | 2015-08-20 | 1 | N | N/A | no | [9 empty] | e01544br1 | 5M | 5000 | 10.137.23.129/25
P&CB | 800536 | 2016-05-17 | 1644 | OROMOCTO PERSONAL BANKING CENTRE | 17:00 | 17:00 | 18:00 | 18:00 | 17:00 | closed | Closed | 287 RESTIGOUCHE RD | OROMOCTO | NEW BRUNSWICK | E2V2H2 |  | 2016-06-15 | 2016-07-13 |  | 2016-07-27 |  |  | 1644, 9404 |  | Unisys |  |  | 2016-04-27 | 2016-07-22 | [9 empty] | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 12 | 1 |  |  | 13 | Centrex |  | done | 7 |  |  |  | 506446 | ALIANT TELECOM (NB) | NB | Oromocto | ORMONBSCRS0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-22 | 2015-08-11 | 1 | N | N/A | no | [9 empty] | e01644br1 | T1 | 1500 | 10.136.163.129/25
P&CB | 801484 | 2016-05-17 | 5563 | PORTER`S LAKE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 5228 HWY 7 | PORTER'S LAKE | NOVA SCOTIA | B3E1J8 |  | 2016-06-15 | 2016-07-13 |  | 2016-07-27 |  |  | 5563, 14535 |  | Unisys |  |  | 2016-04-27 | 2016-07-22 | [5 empty] | Shirley Curley | 9028275609 | Donna Baker | 9028275602 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902827 | ALIANT TELECOM (NS) | NS | Chezzetcook | CZCKNS03RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-22 | 2015-05-01 | 2 | Y | 2014-03-09 | Yes |  | 2016-02-23 | 2016-07-22 | Bell - Order placed, dates pending | TBD - June forecast |  | LATE | -99999 | June 1 New Requ | e05563br5 | Other | 1500 | 10.136.49.1/25
P&CB | 801934 | Yes/Oui | 8189 | PONOKA BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 5031 51ST AVE | PONOKA | ALBERTA | T4J1R7 |  | 2016-05-23 | 2016-06-01 |  | 2016-07-27 | 1/18/2015: Sip Avail Nov 18 2014 |  | 8189, 8749 |  | Bell Canada |  |  | 2016-04-27 | 2016-07-22 | [5 empty] | Lorraine Kaip | 4037839113 |  |  | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 14 | 1 |  |  | 15 | Centrex |  | done | 8 |  | 2 |  | 403783 | TELUS | AB | Ponoka | PNKAAB01RS0 | (I) Regulated / Réglementé | 0 | 0 | 2016-07-22 | 2015-07-15 | 4 | Y | 2014-05-24 | Yes |  | 2015-04-21 | 2016-07-22 | Telus - pending JLL for conduit install | TBD - June forecast |  | LATE | -99999 | July 30 - 24 AB | w08189br1 | DSL | 1500 | 10.136.22.129/25
P&CB | 801495 | 2016-05-17 | 5613 | PORT HAWKESBURY BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 327 GRANVILLE ST | PORT HAWKESBURY | NOVA SCOTIA | B9A2M5 |  | 2016-06-16 | 2016-07-14 |  | 2016-07-28 |  |  | 5613, 9076, 9593, 9843, 9883, 14535 |  | Unisys |  |  | 2016-04-28 | 2016-07-25 | [5 empty] | Peter Clow | 9026254875 |  |  | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 26 | 3 |  |  | 29 | Centrex |  | done | 12 |  |  |  | 902625 | ALIANT TELECOM (NS) | NS | Port Hawkesbury | PHBYNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-23 | 2015-01-19 | 2 | N | N/A | no | [9 empty] | e05613br1 | 5M | 5000 | 10.138.15.1/25
P&CB | 801515 | 2016-05-17 | 5783 | CLAYTON PARK BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 271 LACEWOOD DR | HALIFAX | NOVA SCOTIA | B3M4K3 |  | 2016-06-16 | 2016-07-14 |  | 2016-07-28 |  |  | 00000, 1506, 4039, 5783, 7479, 9443, 9593, 9843, 12056, 15961, 18036 |  | Unisys |  |  | 2016-04-28 | 2016-07-25 | [5 empty] | Michelle Allison | 9024218999 | Deborah Brown | 9024218436 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 37 | 5 |  |  | 42 | Centrex |  | done | 16 |  |  |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-23 | 2014-12-09 | 4 | N | N/A | no | [9 empty] | e05783br1 | 10M | 10000 | 10.137.33.129/25
P&CB | 802221 | 2016-05-17 | 9503 | ELIZABETH AVE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 65 ELIZABETH AVE | ST. JOHN'S | NEWFOUNDLAND | A1A1W8 |  | 2016-06-16 | 2016-07-14 |  | 2016-07-28 |  |  | 00000, 8133, 8963, 9063, 9275, 9503, 14583 |  | Unisys |  |  | 2016-04-28 | 2016-07-25 | [5 empty] | Ursula Hann | 7095764571 | Joanne Stevenson | 7095764645 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 31 | 4 |  |  | 35 | Centrex |  | done | 14 |  |  |  | 709576 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-07-23 | 2015-08-06 | 1 | N | N/A | no | [9 empty] | e09503br1 | 5M | 5000 | 10.137.41.129/25
P&CB | 800596 | 2016-05-17 | 1763 | DARTMOUTH BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 44 PORTLAND ST | DARTMOUTH | NOVA SCOTIA | B2Y1H3 |  | 2016-06-21 | 2016-07-19 |  | 2016-08-02 |  |  | 00000, 1506, 1763, 4039, 9593, 12056 |  | Unisys |  |  | 2016-05-03 | 2016-07-28 | [5 empty] | Kathleen Reynolds | 9024214376 | Tracey Connolly | 9024214281 | ATLANTIC PROVINCES | Wendy Wagner | Michael Wallace | 22 | 2 |  |  | 24 | Centrex |  | done | 10 |  | 6 |  | 902421 | ALIANT TELECOM (NS) | NS | Halifax | HLFXNS06CG0 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-28 | 2015-04-29 | 3 | Y | 2014-07-27 | no | [9 empty] | e01763br1 | T1 | 1500 | 10.136.105.129/25
P&CB | 800647 | 2016-05-17 | 1984 | LANSDOWNE & WELLESLEY BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 111 LANSDOWNE AVE | SAINT JOHN | NEW BRUNSWICK | E2K2Z9 |  | 2016-06-21 | 2016-07-19 |  | 2016-08-02 |  |  | 00000, 1464, 1984, 4435, 8014, 14582, 14944, 16978 |  | Unisys |  |  | 2016-05-03 | 2016-07-28 | [5 empty] | Theresa Keane-Gormley | 5066320634 | Michelle Vienneau | 5066320784 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 23 | 2 |  |  | 25 | Centrex |  | done | 11 |  |  |  | 506634 | ALIANT TELECOM (NB) | NB | Saint John | STJHNBSU63A | Unregulated / Non Réglementé | 0 | 0 | 2016-07-28 | 2015-08-11 | 3 | N | N/A | Yes |  | 2016-02-23 | 2016-07-28 | Bell - Order placed, dates pending | TBD - June forecast |  | LATE | -99999 | 2016-03-31 | e01984br5 | Other | 1500 | 10.136.46.1/25
P&CB | 801397 | Yes/Oui | 5029 | KINGSWAY MEWS BRANCH | 16:30 | 16:30 | 16:30 | 16:30 | 17:30 | closed | Closed | 10567 KINGSWAY AVE | EDMONTON | ALBERTA | T5H4K1 |  | 2016-05-27 | 2016-06-07 |  | 2016-08-02 | Oct 28 :MPLS upgrade req'd Change cutover fr Jan 8 to TBD david.lu: 6/24: moved back into schedule as per Leslie's request 6/8: moved to TBD as per Linda's 1pm call - pending MPLS upgrade MPLS delay -- move to 2016 |  | 5029, 8749, 9333, 9955, 9960, 10452, 14259, 14578 |  | Bell Canada |  | James Van Dyke @ 780-982-0815 | 2016-05-03 | 2016-07-28 | delayed | 2015-06-26 |  |  |  | Davide Mazzotta | 7804486448 | Amy Phung | 7804486455 | ALBERTA & TERRITORIES | Chris Buckley | Dan Chipak | 24 | 1 |  |  | 25 | Centrex |  | done | 11 | N | 8 |  | 780448 | TELUS | AB | Edmonton | EDTNABXMCG5 | (C) Regulated / Réglementé | 780-670-2348 | edmonton_01_7806702348 | 2016-07-28 | 2014-07-14 | 1 | N | N/A | Yes |  | 2014-05-05 | 2016-07-28 | Telus - pending conduit install, mall complications | TBD - June forecast |  | LATE | -99999 | Recovered - AB | w05029br5 | Other | 1500 | 10.136.83.129/25
P&CB | 802223 | 2016-05-17 | 9563 | TORBAY BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 1296 TORBAY RD | TORBAY | NEWFOUNDLAND | A1K1K5 |  | 2016-06-21 | 2016-07-19 |  | 2016-08-02 |  |  | 9063 |  | Unisys |  |  | 2016-05-03 | 2016-07-28 | [9 empty] | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 709437 | ALIANT TELECOM (NF) | NL | Torbay | STJHNF01CG1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-28 | 2015-01-14 | 1 | Y | 2014-03-23 | Yes |  | Done | 2016-07-28 | Bell | 2016-03-07 | 2016-03-27 | OK | 128 | 2016-03-31 | e09563br1 | DSL | 1500 | 10.138.79.129/25
DS | 803161 | Yes/Oui | 90862 | RBC INVESTMENTS | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 650 WEST 41ST AVE-SUITE 638 | VANCOUVER | BRITISH COLUMBIA | V5Z2M9 |  | 2016-05-27 | 2016-06-07 |  | 2016-08-02 | 2/1/2015 3 LOB this location (TR 7360 90862 10776) RBC to advise if all 3 cutting over on same day - Will have to move out to April / May time frame david.lu: 6/24: moved back into schedule as per Leslie's request 6/8: moved to TBD as per Linda's 1pm call - pending MPLS upgrade Call quality risk mitigation, move to 2016 |  | 00000, 1660, 3650, 4712, 4960, 5700, 7360, 8890, 10690, 10694, 10776, 12071, 14143, 14966, 14973, 14989, 90862 |  | Bell Canada | 2015-08-28 | Purwanto Hadi @ 604-679-8618 | 2016-05-03 | 2016-07-28 | 2015-08-24 | 2015-05-26 | Mark Husken | Kelly Ha |  |  | 604-718-3126 |  |  | BRITISH COLUMBIA | Elaine Sanderson | Timothy Carmack | 115 | 2 |  |  | 117 | Centrex |  | done | 13 | Y | 17 |  | 604665 | TELUS | BC | Vancouver | VANCBC014XD | (I) Unregulated / Non Réglementé | 604-678-1180 | vanc_01_6046781180 | 2016-07-28 | 2015-07-30 | 2 | N | N/A | no | [9 empty] | w90862vr1 | 5M | 5000 | 10.137.181.1/25
PB | 809080 | Yes/Oui | 10776 | HO PRIVATE BANKING OAKRIDGE | [7 empty] | 650 WEST 41ST AVE-SUITE 328/N TWR | VANCOUVER | BRITISH COLUMBIA | V5Z2M9 |  | 2016-05-27 | 2016-06-07 |  | 2016-08-02 | 2/1/2015 3 LOB this location (TR 7360 90862 10776)RBC to advise if all 3 cutting over on same day - Will have to move out to April / May time frame david.lu: 6/24: moved back into schedule as per Leslie's request 6/8: moved to TBD as per Linda's 1pm call - pending MPLS upgrade Call quality risk mitigation, move to 2016 |  | 00000, 1660, 3650, 4712, 5700, 7360, 8890, 10690, 10694, 10776, 12043, 12071, 14143, 14966, 14989, 17943, 90862 |  | Bell Canada | 2015-08-28 | Jamie Lodge @ 778-837-8775 | 2016-05-03 | 2016-07-28 | 2015-08-24 | 2015-05-26 | [7 empty] | BRITISH COLUMBIA | Elaine Sanderson | Timothy Carmack | 16 | 2 |  |  | 18 | Centrex |  | done | 11 | Y | 17 |  | 604665 | [5 empty] | 604-678-1180 | vanc_01_6046781180 | 2016-07-28 | shared checklist with TR 7360 |  | N | N/A
P&CB | 800650 | Yes/Oui | 2000 | GIBSONS BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 900 GIBSONS WAY SUITE #33 | GIBSONS | BRITISH COLUMBIA | V0N1V7 |  | 2016-05-31 | 2016-06-08 |  | 2016-08-03 |  |  | 00000, 2000, 15529 |  | Bell Canada |  |  | 2016-05-04 | 2016-07-29 | [5 empty] | Sue Gibson | 6048865406 | Anita Bullen | 6048865401 | BRITISH COLUMBIA | Beth Compton | Timothy Carmack | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  | 3 |  | 604886 | TELUS | BC | Gibsons | GBSNBC01DS1 | (C) Regulated / Réglementé | 0 | 0 | 2016-07-29 | 2014-10-16 | 2 | Y | 2014-10-17 | Yes |  | 2015-06-26 | 2016-07-29 | Telus - Pending circuit migration | 2015-12-09 | 2016-03-08 | OK | 148 | Aug 1 - 27 BC | w02000br1 | DSL | 1500 | 10.136.20.129/25
P&CB | 800651 | 2016-05-17 | 2014 | RBC RETAIL MCALLISTER BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 515 WESTMORLAND RD | SAINT JOHN | NEW BRUNSWICK | E2J3W9 |  | 2016-06-22 | 2016-07-20 |  | 2016-08-03 | Ins 15420 515 WESTMORELAND RD-UNIT C009B , ST JOHN , NB |  | 00000, 2014, 4435, 9404, 13280, 14582, 15420 |  | Unisys |  |  | 2016-05-04 | 2016-07-29 | [5 empty] | Jane Bradbrook | 5066320683 | Jennifer Everett | 5066320792 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 28 | 3 |  |  | 31 | Centrex |  | done | 13 |  |  |  | 506631 | ALIANT TELECOM (NB) | NB | Saint John | STJHNBSU63A | Unregulated / Non Réglementé | 0 | 0 | 2016-07-29 | 2015-08-13 | 5 | N | N/A | no | [9 empty] | e02014cr1 | 5M | 5000 | 10.137.51.1/25
P&CB | 801256 | Yes/Oui | 4359 | SOUTHGATE SHOPPING CENTRE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 5015 111TH ST | EDMONTON | ALBERTA | T6H4M6 |  | 2016-05-30 | 2016-06-08 |  | 2016-08-03 | Oct 22nd : removed the T-65 Actual Comms Date (no comm has been - JW) |  | 3306, 4219, 4359, 9955, 9960, 10451, 13487, 14258, 14578, 17316 |  | Bell Canada |  |  | 2016-05-04 | 2016-07-29 |  | 2015-06-26 | [5 empty] | Jenna Galbraith | 7804486122 | ALBERTA & TERRITORIES | Chris Buckley | Dan Chipak | 43 | 5 |  |  | 48 | Centrex |  | done | 17 | N | 10 |  | 780448 | TELUS | AB | Edmonton | EDTNABXMCG5 | (C) Regulated / Réglementé | 780-670-2348 | edmonton_01_7806702348 | 2016-07-29 | 2015-07-03 | 2 | Y | 2015-02-02 | Yes |  | 2014-05-05 | 2016-07-29 | Telus - pending conduit install, mall complications | TBD - June forecast |  | LATE | -99999 | Recovered - AB | w04359br5 | Other | 1500 | 10.136.80.129/25
P&CB | 801374 | 2016-05-17 | 4903 | MUSQUODOBOIT HARBOUR BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 7907 HIGHWAY 7 | MUSQUODOBOIT HARBOUR | NOVA SCOTIA | B0J2L0 |  | 2016-06-22 | 2016-07-20 |  | 2016-08-03 |  |  | 00000, 4903 |  | Unisys |  |  | 2016-05-04 | 2016-07-29 | [5 empty] | Jackie Slaunwhite | 9028892935 |  |  | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902889 | ALIANT TELECOM (NS) | NS | Musquodoboit Harbour | MQHRNS01RS1 | Regulated / Réglementé | 0 | 0 | 2016-07-29 | 2014-12-10 | 1 | N | N/A | Yes |  | 2016-02-23 | 2016-07-29 | Bell - Order placed, dates pending | TBD - June forecast |  | LATE | -99999 | June 1 New Requ | e04903br5 | Other | 1500 | 10.136.48.129/25
P&CB | 801566 | 2016-05-17 | 6053 | SHUBENACADIE BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 16:00 | Closed | 2824 MAIN ST | SHUBENACADIE | NOVA SCOTIA | B0N2H0 |  | 2016-06-22 | 2016-07-20 |  | 2016-08-03 |  |  |  |  | Unisys |  |  | 2016-05-04 | 2016-07-29 | [5 empty] | Robert Mcgee | 9027584402 | Krista MacRae | 9027584420 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 902758 | ALIANT TELECOM (NS) | NS | Shubenacadie | SBNCNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-29 | 2015-05-01 | 2 | Y | 2014-03-23 | no | [9 empty] | e06053br1 | T1 | 1500 | 10.136.175.129/25
P&CB | 800193 | 2016-05-17 | 663 | BARRINGTON PASSAGE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 3525 ROUTE 3 | BARRINGTON PASSAGE | NOVA SCOTIA | B0W1G0 |  | 2016-06-23 | 2016-07-21 |  | 2016-08-04 |  |  | 00000, 663, 14913 |  | Unisys |  |  | 2016-05-05 | 2016-08-01 | [5 empty] | Jody Breen | 9026373901 | Angela Nickerson | 9026373915 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 902637 | ALIANT TELECOM (NS) | NS | Barrington | BNTONS02RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-30 | 2015-07-20 | 2 | N | N/A | Yes |  | Done | 2016-07-30 | Bell - Pending | 2016-05-13 | 2016-05-27 | OK | 69 | 2016-03-31 | e00663br1 | DSL | 1500 | 10.138.55.1/25
P&CB | 800898 | Yes/Oui | 3032 | MISSISSAUGA-WESTWOOD SHOPPING MALL BR | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 7205 GOREWAY DR | MISSISSAUGA | ONTARIO | L4T2T9 |  | 2016-07-12 | 2016-07-18 |  | 2016-08-04 | RBC advised this to move to 4/2016 (7/8 update) July 2015 per jackie -- Mall is under renovation and no fibre installs will happen until the mall is fully renovated Renovations should be completed close to end of the year |  | 1571, 3032, 13940, 13959, 13976, 13977, 17434 |  | Bell Canada |  |  | 2016-06-16 | 2016-08-01 |  | 2015-05-01 |  |  |  | Anil Dhawan | 9056716512 | Silva Suzic | 9056716352 | GREATER TORONTO REGION | Sue Fantini | Dawn Adams-Cheung | 21 | 4 |  |  | 25 | Centrex |  | done | 11 | N | 7 |  | 905671 | BELL CANADA - ON | ON | Malton | MALTON22CG1 | (W) Unregulated / Non Réglementé | 0 | 0 | 2016-07-30 | 2015-03-17 | 3 | Y | 2015-03-27 | Yes |  | 2015-04-15 | 2016-07-30 | Bell -- Mall reno target? | TBD - June forecast |  | LATE | -99999 | Priority - 50 | c03032br5 | Other | 1500 | 10.136.40.1/25
P&CB | 801418 | 2016-05-17 | 5104 | HUNTER RIVER BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | ROUTE #2 | HUNTER RIVER | PRINCE EDWARD ISLAND | C0A1N0 |  | 2016-06-23 | 2016-07-21 |  | 2016-08-04 |  |  |  |  | Unisys |  |  | 2016-05-05 | 2016-08-01 | [5 empty] | Jason Ahern | 9029644310 |  |  | ATLANTIC PROVINCES | Daniel Doucet | Michael Wallace | 11 | 1 |  |  | 12 | Centrex |  | done | 7 |  |  |  | 902964 | ALIANT TELECOM (PEI) | PE | Hunter River | HNRVPE01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-07-30 | 2015-01-14 | 1 | Y | 2014-05-30 | Yes |  | Done | 2016-07-30 | Bell | 2016-04-25 | 2016-05-09 | OK | 87 | 2016-03-31 | e05104br1 | DSL | 1500 | 10.137.250.1/25
P&CB | 801585 | Yes/Oui | 6169 | HANNA BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 301 CENTRE ST | HANNA | ALBERTA | T0J1P0 |  | 2016-05-31 | 2016-06-09 |  | 2016-08-04 |  |  | 6169, 9882 |  | Unisys |  |  | 2016-05-05 | 2016-08-01 | [5 empty] | Randene Graumann | 4038546003 |  |  | ALBERTA & TERRITORIES | Monique Turcotte | Dan Chipak | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  | 2 |  | 403854 | TELUS | AB | Hanna | HANNAB01RS0 | Regulated / Réglementé | 0 | 0 | 2016-07-30 | 2015-05-30 | 1 | Y | 2014-05-16 | Yes | 2015-06-25 | 2015-05-05 | 2015-08-01 | Completed | 2015-06-17 |  | Complete | Complete | Aug 1 - per Adam | w06169br1 | T1 | 1500 | 10.136.12.1/25
INS | 809030 | 2016-05-17 | 15420 | MCALLISTER PLACE, NB | 17:00 | 17:00 | 20:00 | 20:00 | 17:00 | Closed | Closed | 515 WESTMORLAND RD, C009B | SAINT JOHN | NEW BRUNSWICK | E2J3W9 |  | 2016-06-23 | 2016-07-21 |  | 2016-08-04 | Nov. 4: Reno Collision** Inserted a row for INS, the cutover date is TDB until the Renos are completed. |  | 00000, 00004, 2014, 4435, 9404, 13280, 14582, 15420 |  | Unisys |  |  | 2016-06-16 | 2016-08-01 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 7 | 0 |  |  | 7 | Centrex |  | done | 5 |  | 8 |  | 506631;506632; | [5 empty] | #N/A | #N/A | 2016-07-30 | 2015-08-23 | 5 | N | N/A | [13 empty] | #N/A
P&CB | 800280 | 2016-05-17 | 993 | BERWICK BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 195 COMMERCIAL ST | BERWICK | NOVA SCOTIA | B0P1E0 |  | 2016-06-27 | 2016-07-25 |  | 2016-08-08 |  |  |  |  | Unisys |  |  | 2016-05-09 | 2016-08-03 | [5 empty] | Jody Coyle | 9025382807 | Brenda Melanson | 9025382803 | ATLANTIC PROVINCES | Bill Reed | Michael Wallace | 17 | 1 |  |  | 18 | Centrex |  | done | 9 |  |  |  | 902538 | ALIANT TELECOM (NS) | NS | Berwick | BEWKNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-08-03 | 2015-05-01 | 2 | Y | 2014-03-16 | Yes |  | Done | 2016-08-03 | Bell | 2016-06-20 | 2016-07-04 | OK | 35 | 2016-03-31 | e00993br1 | DSL | 1500 | 10.138.57.1/25
P&CB | 801155 | Yes/Oui | 3920 | N VAN-DOLLARTON VILLAGE BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 477 NORTH DOLLARTON HWY | NORTH VANCOUVER | BRITISH COLUMBIA | V7G1MP |  | 2016-06-03 | 2016-06-13 |  | 2016-08-08 |  |  | 1655, 3920, 14975, 15529 |  | Bell Canada |  |  | 2016-05-09 | 2016-08-03 | [5 empty] | Leslie VanderRoest | 6049242755 | Mitra Saffari | 6049242756 | BRITISH COLUMBIA | Beth Compton | Timothy Carmack | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  | 4 |  | 604929 | TELUS | BC | North Vancouver | NVCRBC02RS1 | (C) Regulated / Réglementé | 778-338-6092 | north_vancouver_01_7783386092 | 2016-08-03 | 2014-02-07 |  | Y | 2014-02-07 | Yes |  | 2014-05-06 | 2015-08-01 | Telus -- damaged conduit | TBD - June forecast |  | LATE | -99999 | Aug 1 - 27 BC | w03920br5 | Other | 1500 | 10.136.79.1/25
P&CB | 801636 | Yes/Oui | 6609 | YELLOWHEAD HWY BRANCH | 17:00 | 17:00 | 17:00 | 19:00 | 17:00 | closed | Closed | 874 CARMICHAEL LANE | HINTON | ALBERTA | T7V1Y6 |  | 2016-06-02 | 2016-06-13 |  | 2016-08-08 |  |  | 1625, 6280, 6609, 9892, 10451, 14362 |  | Unisys |  |  | 2016-05-09 | 2016-08-03 | [5 empty] | Charlene Stamp | 7808658444 | Dorothy Hiitola | 7808658439 | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 26 | 3 |  |  | 29 | Centrex |  | done | 12 |  | 6 |  | 780865 | TELUS | AB | Hinton | HITNAB02RS0 | Regulated / Réglementé | 0 | 0 | 2016-08-03 | 2015-05-04 |  | Y | 2015-05-04 | no | [9 empty] | w06609br1 | T1 | 1500 | 10.136.3.1/25
P&CB | 801909 | Yes/Oui | 8059 | PEACE RIVER BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | closed | Closed | 10036 100 ST | PEACE RIVER | ALBERTA | T8S1S8 |  | 2016-06-02 | 2016-06-13 |  | 2016-08-08 |  |  | 0 |  | Unisys |  |  | 2016-05-09 | 2016-08-03 | [5 empty] | Annette Friesen | 7806247615 | Chantal Closs | 7806247618 | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 17 | 3 |  |  | 20 | Centrex |  | done | 0 |  | 1 |  | 780624 | TELUS | AB | Peace River | PCRVAB01DS0 | (I) Regulated / Réglementé | 0 | 0 | 2016-08-03 | 2015-05-14 | 2 | Y | 2015-05-18 | Yes |  | 2015-04-21 | 2016-08-03 | Telus - pending conduit install | TBD - June forecast |  | LATE | -99999 | July 30 - 24 AB | w08059br1 | DSL | 1500 | 10.136.10.1/25
P&CB | 802232 | 2016-05-17 | 9703 | STEPHENVILLE BRN | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 73 MAIN ST | STEPHENVILLE | NEWFOUNDLAND | A2N1H9 |  | 2016-06-27 | 2016-07-25 |  | 2016-08-08 |  |  | 000000, 1622, 7044, 8332, 9063, 9313, 9703, 16760 |  | Unisys |  |  | 2016-05-09 | 2016-08-03 | [5 empty] | Phyllis Hapgood | 7096438303 | Michelle Cochrane | 7096438307 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 18 | 1 |  |  | 19 | Centrex |  | done | 9 |  |  |  | 709643 | ALIANT TELECOM (NF) | NL | Stephenville | STVLNF01RSC | Unregulated / Non Réglementé | 0 | 0 | 2016-08-03 | 2015-08-12 | 2 | N | N/A | Yes |  | Done | 2016-08-03 | Bell | 2016-03-10 | 2016-03-27 | OK | 134 | 2016-03-31 | e09703br1 | DSL | 1500 | 10.138.80.1/25
PB | 809067 | 2016-05-17 | 10754 | HO PRIVATE BANKING HALIFAX | [7 empty] | 1871 HOLLIS ST-SUITE 800 | HALIFAX | NOVA SCOTIA | B3J0C3 |  | 2016-06-27 | 2016-07-25 |  | 2016-08-08 |  |  | 3, 209, 1178, 1443, 2593, 3237, 3333, 4813, 5499, 6250, 6821, 7666, 7785, 8333, 8515, 8566, 9043, 9083, 9363, 9393, 9483, 9543, 9593, 9623, 9723, 9744, 9803, 9843, 9883, 10158, 10754, 13986, 14163, 14912, 14931, 14944, 15027, 15790. 15977, 16880, 17165, 17746 |  | Aliant |  |  | 2016-06-20 | 2016-08-03 | [9 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 6 | 51 |  |  | 57 | IP |  | done | 25 |  | 41 |  | 902420;902421; | [7 empty] | 2016-08-03 | 2015-05-15 | 0 | N | N/A
P&CB | 800101 | 2016-05-17 | 333 | ANTIGONISH BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 236 MAIN ST | ANTIGONISH | NOVA SCOTIA | B2G2C2 |  | 2016-06-28 | 2016-07-26 |  | 2016-08-09 |  |  | 00000, 333, 9593, 9883, 14535 |  | Unisys |  |  | 2016-05-10 | 2016-08-04 | [5 empty] | Kate D'Ettore | 9028675816 | Kim Pelrine | 9028675819 | ATLANTIC PROVINCES | Denise Macleod | Michael Wallace | 22 | 2 |  |  | 24 | Centrex |  | done | 10 |  |  |  | 902867 | ALIANT TELECOM (NS) | NS | Antigonish | AGSHNS01RS1 | Unregulated / Non Réglementé | 0 | 0 | 2016-08-04 | 2014-12-18 | 1 | N | N/A | no | [9 empty] | e00333br1 | 5M | 5000 | 10.138.11.129/25
P&CB | 800763 | Yes/Oui | 2450 | PANDOSY & CEDAR BR | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 3036 PANDOSY ST | KELOWNA | BRITISH COLUMBIA | V1Y1W2 |  | 2016-06-06 | 2016-06-14 |  | 2016-08-09 |  |  | 00000, 2450, 7953, 8820, 10695, 13054, 14969, 16875 |  | Unisys |  |  | 2016-05-10 | 2016-08-04 | [5 empty] | Bridget McKitrick-Gillberg | 2508684227 |  |  | BRITISH COLUMBIA | Jerry Goncalves | Timothy Carmack | 38 | 8 |  |  | 46 | Centrex |  | done | 17 |  | 8 |  | 250717 | TELUS | BC | Kelowna | KLWNBC02DS3 | (W) Regulated / Réglementé | 250-448-4318 | kelowna_01_2504484318 | 2016-08-04 | 2014-08-07 | 2 | N | N/A | Yes | 2015-09-24 | 2014-05-06 | 2016-08-04 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w02450br1 | 5M | 5000 | 10.136.67.129/25
P&CB | 802086 | Yes/Oui | 9179 | TABER BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 4818 53RD ST | TABER | ALBERTA | T1G1W4 |  | 2016-06-03 | 2016-06-14 |  | 2016-08-09 | 1/18/2015: Sip avial Nov 3 2014 |  | 00000, 1120, 9179, 13486 |  | Unisys |  |  | 2016-05-10 | 2016-08-04 | [5 empty] | Pat McCorkle | 4032235656 | Carol Florchinger | 4032235647 | ALBERTA & TERRITORIES | Odell Sinclair | Dan Chipak | 13 | 1 |  |  | 14 | Centrex |  | done | 7 |  | 4 |  | 403223 | TELUS | AB | Taber | TABRAB01RS2 | (W) Regulated / Réglementé | 0 | 0 | 2016-08-04 | 2015-08-07 | 5 | N | N/A | Yes | 2015-10-19 | 2014-04-21 | 2016-08-04 | Telus | done | done | Complete | Complete | July 30 - 24 AB | w09179br1 | 5M | 5000 | 10.136.9.129/25
P&CB | 802227 | 2016-05-17 | 9603 | TOPSAIL RD BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | closed | Closed | 664 TOPSAIL RD | ST. JOHN'S | NEWFOUNDLAND | A1E2E2 |  | 2016-06-28 | 2016-07-26 |  | 2016-08-09 |  |  | 00000, 444, 8963, 9063, 9275, 9603, 14583 |  | Unisys |  |  | 2016-05-10 | 2016-08-04 | [5 empty] | Trudy Tobin | 7095764207 |  |  | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 22 | 4 |  |  | 26 | Centrex |  | done | 11 |  |  |  | 709758 | ALIANT TELECOM (NF) | NL | St John's | STJHNF01CG1 | Regulated / Réglementé | 0 | 0 | 2016-08-04 | 2015-08-14 | 1 | N | N/A | no | [9 empty] | e09603br1 | T1 | 1500 | 10.137.216.129/25
DS | 803026 | 2016-05-17 | 90286 | RBC INVESTMENTS | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 633 MAIN ST. | MONCTON | NEW BRUNSWICK | E1C9X9 |  | 2016-06-28 | 2016-07-26 |  | 2016-08-09 |  |  | 00000, 998, 2258, 5288, 13990, 90277, 90286, 90287 |  | Unisys |  |  | 2016-05-10 | 2016-08-04 |  |  | Bob Cormier | Judy Blakney | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 33 | 5 |  |  | 38 | Centrex |  | done | 19 |  | 8 |  | 506869 | ALIANT TELECOM (NB) | NB | Moncton | MCTNNBSA85C | Unregulated / Non Réglementé | 0 | 0 | 2016-08-04 | 2014-12-22 | 1 | N | N/A | no | [9 empty] | e90286vr1 | 5M | 5000 | 10.137.58.129/25
P&CB | 800674 | 2016-05-17 | 2094 | ST STEPHEN BRANCH | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | Closed | Closed | 26 MILLTOWN BLVD | ST STEPHEN | NEW BRUNSWICK | E3L1G3 |  | 2016-06-29 | 2016-07-27 |  | 2016-08-10 |  |  | 2094, 4435, 9404, 14582 |  | Unisys |  |  | 2016-05-11 | 2016-08-05 | [5 empty] | Barbara Christie | 5064669151 | Leslie Bernardini | 5064669171 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 20 | 1 |  |  | 21 | Centrex |  | done | 10 |  |  |  | 506466 | ALIANT TELECOM (NB) | NB | St Stephen | STJHNBSU63A | Regulated / Réglementé | 0 | 0 | 2016-08-05 | 2015-08-11 | 2 | Y | 2014-06-20 | Yes |  | Done | 2016-08-05 | Bell | 2016-03-08 | 2016-03-27 | OK | 136 | 2016-03-31 | e02094br1 | DSL | 1500 | 10.138.62.1/25
P&CB | 800936 | Yes/Oui | 3200 | NELSON BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 16:00 | Closed | 401 BAKER ST | NELSON | BRITISH COLUMBIA | V1L4H7 |  | 2016-06-07 | 2016-06-15 |  | 2016-08-10 | Oct 21: Cutover chg fr Jan 6, 2015 to TBD pending cabling and switch upgrade |  | 00000, 3200, 8820, 10695, 11920, 13053 |  | Unisys |  |  | 2016-05-11 | 2016-08-05 |  | 2014-10-09 |  |  |  | Scott Fraser | 2503545029 | Julia Mallette | 2503545004 | BRITISH COLUMBIA | Dana McCombie | Timothy Carmack | 25 | 3 |  |  | 28 | Centrex |  | done | 12 |  | 6 |  | 250371 | TELUS | BC | South Kamloops | KMLPBC01DS2 | (W) Regulated / Réglementé | 250-434-1228 | southkamloops_01_2504341228 | 2016-08-05 | 2015-03-27 |  | Y | 2015-03-27 | Yes |  | 2014-05-06 | 2016-08-05 | Telus - Pending circuit migration | 2016-01-12 | 2016-03-17 | OK | 146 | Aug 1 - 27 BC | w03200br5 | Other | 1500 | 10.136.73.129/25
P&CB | 801971 | Yes/Oui | 8479 | SEXSMITH BRANCH | 16:00 | 16:00 | 16:00 | 16:00 | 17:00 | closed | Closed | 9921 100TH ST | SEXSMITH | ALBERTA | T0H3C0 |  | 2016-06-06 | 2016-06-15 |  | 2016-08-10 |  |  | 8479, 19451 |  | Unisys |  |  | 2016-05-11 | 2016-08-05 | [9 empty] | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 10 | 1 |  |  | 11 | Centrex |  | done | 6 |  | 2 |  | 780568 | TELUS | AB | Sexsmith | SXSMAB01RS2 | Regulated / Réglementé | 0 | 0 | 2016-08-05 | 2015-03-15 | 2 | Y | 2015-02-20 | no | [9 empty] | w08479br1 | T1 | 1500 | 10.136.213.129/25
P&CB | 802234 | 2016-05-17 | 9801 | HAPPY VALLEY BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 36 GRENFELL ST | HAPPY VALLEY GOOSE BAY | NEWFOUNDLAND | A0P1E0 |  | 2016-06-29 | 2016-07-27 |  | 2016-08-10 |  |  | 00000, 123, 9063, 9801, 13937, 14583 |  | Unisys |  |  | 2016-05-11 | 2016-08-05 | [5 empty] | Jay Fawcett | 7098966543 | Sandra Hann | 7098966544 | ATLANTIC PROVINCES | Dean Harris | Michael Wallace | 22 | 3 |  |  | 25 | Centrex |  | done | 11 |  |  |  | 709896 | ALIANT TELECOM (NF) | NL | Happy Valley-Goose Bay (Labrador) | GSBANF05DS1 | Regulated / Réglementé | 0 | 0 | 2016-08-05 | 2014-08-25 | 2 | Y | 2014-08-15 | Yes |  | 2016-02-25 | 2016-08-05 | Bell - Order placed, dates pending | TBD - June forecast |  | LATE | -99999 | 2016-03-31 | e09801br1 | T1 | 1500 | 10.136.187.129/25
DS | 803025 | 2016-05-17 | 90283 | FREDERICTON RBC INVESTMENTS | 17:30 | 17:30 | 17:30 | 17:30 | 17:30 | closed | Closed | 371 QUEEN ST | FREDERICTON | NEW BRUNSWICK | E3B4Y9 |  | 2016-06-29 | 2016-07-27 |  | 2016-08-10 |  |  | 90283 |  | Unisys |  |  | 2016-05-11 | 2016-08-05 |  |  | Craig Maguire | Debbie Devereaux Comfort | [5 empty] | ATLANTIC PROVINCES |  | Mike Wallace | 36 | 11 |  |  | 47 | Centrex |  | done | 22 |  | 1 |  | 506458 | ALIANT TELECOM (NB) | NB | Fredericton | FCTNNBSC45C | Unregulated / Non Réglementé | 0 | 0 | 2016-08-05 | 2015-08-10 | 0 | N | N/A | no | [9 empty] | e90283vr1 | 10M | 10000 | 10.136.229.1/25
P&CB | 800729 | 2016-05-17 | 2314 | WOODSTOCK BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | Closed | Closed | 540 MAIN ST | WOODSTOCK | NEW BRUNSWICK | E7M2C3 |  | 2016-06-30 | 2016-07-28 |  | 2016-08-11 |  |  |  |  | Unisys |  |  | 2016-05-12 | 2016-08-08 | [5 empty] | Nancy Knox | 5063257631 | Margaret Findlater | 5063257639 | ATLANTIC PROVINCES | Bob MacKay | Michael Wallace | 26 | 6 |  |  | 32 | Centrex |  | done | 13 |  |  |  | 506325 | ALIANT TELECOM (NB) | NB | Woodstock | WDSTNBSCRS0 | Unregulated / Non Réglementé | 519-537-8997 | woodstock_5195378997 | 2016-08-06 | 2015-08-14 | 2 | Y | 2014-04-25 | Yes |  | Done | 2016-08-06 | Bell | 2016-03-10 | 2016-03-27 | OK | 137 | 2016-03-31 | e02314br1 | DSL | 1500 | 10.137.249.129/25
P&CB | 801185 | Yes/Oui | 4080 | OLIVER BRANCH | 15:00 | 15:00 | 15:00 | 17:00 | 15:00 | Closed | Closed | 36024 97TH ST | OLIVER | BRITISH COLUMBIA | V0H1T0 |  | 2016-06-08 | 2016-06-16 |  | 2016-08-11 | 1/18/2015: SIP available Nov 18, 2014 do not schedule due to cabling CR |  |  |  | Unisys |  |  | 2016-05-12 | 2016-08-08 | [5 empty] | Ryan E.D. Sirianni | 2504985202 | Daylene Bennett | 2504985209 | BRITISH COLUMBIA | Jerry Goncalves | Timothy Carmack | 12 | 1 |  |  | 13 | Centrex |  | done | 7 |  |  |  | 250498 | TELUS | BC | Oliver | OLVRBC01RS1 | (I) Regulated / Réglementé | Need PTN | 0 | 2016-08-06 |  |  | Y | PND RENO | Yes | 2015-05-26 | 2014-08-25 | 2015-08-01 | Completed |  |  | Complete | Complete | Aug 1 - 27 BC | w04080br1 | 5M | 5000 | 10.136.3.129/25
P&CB | 801600 | Yes/Oui | 6279 | HIGH PRAIRIE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 5117 49TH ST | HIGH PRAIRIE | ALBERTA | T0G1E0 |  | 2016-06-07 | 2016-06-16 |  | 2016-08-11 |  |  | 1625, 6279, 8749, 9893 |  | Unisys |  |  | 2016-05-12 | 2016-08-08 | [5 empty] | Simon Tremblay | 7805236152 |  |  | ALBERTA & TERRITORIES | Karen McNamee | Dan Chipak | 16 | 1 |  |  | 17 | Centrex |  | done | 8 |  |  |  | 780523 | TELUS | AB | High Prairie | HIPRAB01RS0 | Regulated / Réglementé | 0 | 0 | 2016-08-06 | 2015-04-06 | 1 | Y | 2015-04-20 | Yes |  | 2015-06-29 | 2016-08-06 | Telus - pending conduit install& ISW JLL | TBD - June forecast |  | LATE | -99999 | 2016-03-31 | w06279br1 | DSL | 1500 | 10.136.7.129/25
P&CB | 801463 | Yes/Oui | 5440 | TERRACE BRANCH | 17:00 | 17:00 | 17:00 | 19:00 | 17:00 | closed | Closed | 4640 LAKELSE AVE | TERRACE | BRITISH COLUMBIA | V8G1R2 |  | 2016-06-10 | 2016-06-20 |  | 2016-08-15 |  |  | 2144, 4610, 5440, 7700, 8890, 10695, 13055, 15883 |  | Unisys |  |  | 2016-05-16 | 2016-08-10 | [5 empty] | Dianne Rooker | 2506358006 | Albertina Vicente | 2506358022 | BRITISH COLUMBIA | Jerry Goncalves | Timothy Carmack | 36 | 9 |  |  | 45 | Centrex |  | done | 16 |  | 8 |  | 250635 | TELUS | BC | Terrace | TRRCBC02DS1 | (C) Unregulated / Non Réglementé | 0 | 0 | 2016-08-10 | 2015-06-05 |  | Y | 2015-06-05 | Yes |  | 2015-06-25 | 2015-08-01 | Telus - pending conduit install | TBD - June forecast |  | LATE | -99999 | Aug 1 - 27 BC | w05440br1 | T1 | 1500 | 10.136.19.129/25
P&CB | 802319 | Yes/Oui | 9974 | BEACON HILL CENTRE BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 11492 SARCEE TRAIL NW 0R 11792 SARCEE? | CALGARY | ALBERTA | T3R0A1 |  | 2016-06-09 | 2016-06-20 |  | 2016-08-15 | Nov. 26: Updated column A from Phase 2 Pilot to Roll out. NOTE**PH Oct. 14**Added to Master for 2016 migration. Reference: Unable to rescue the migrations in time for the Pilot cutoff of July 31st. Dropped from the Pilot based on a decision from Ernie/John that we could assess our processes with the number of pilot migrations we had from ON, PQ, BC, and AB. MB was declared a risk going into Rollout. Previous cutover date - July 31/2014 |  | 00000, 4013, 9974, 10449 |  | Bell Canada |  |  | 2016-05-16 | 2016-08-10 | [5 empty] | Jolene Wilde | 4032998403 |  |  | ALBERTA & TERRITORIES | Rhonda Graham | Dan Chipak | [8 empty] | 10 |  | 4 |  | 403299 | TELUS | AB | Calgary | CLGRAB01CG2 | (I) Regulated / Réglementé | 403-366-3024 | calg_01_4033552310 | 2016-08-10 | 2014-06-26 | 2 | N | N/A | no | [9 empty] | w09974br1 | 5M | 5000 | 10.137.158.1/25
[68 empty] | 1 |  |  |  | 3 | 2
Formulas:
Preaudits due date/ T17/T47 = WORKDAY([Cutover Date], -30, HOLIDAY)
Branch Audit Due Date = WORKDAY([Cutover Date],-10, IF([Province]="Quebec", HolidayQC, IF([Province]="British Columbia", HolidayBC,HOLIDAY)))
Branch Audit Due Date = WORKDAY([Cutover Date],-13, IF([Province]="Quebec", HolidayQC, HOLIDAY))
T35/T65 = WORKDAY([Cutover Date], -65, HOLIDAY)
T35/T65 = WORKDAY([Cutover Date], -65, HolidayBC)
T3 Communication = WORKDAY([Cutover Date],-3,HOLIDAY)
MPLS Upgrade Required Date = [Cutover Date]-5
MPLS Upgrade Target Date = [MPLS Circuit Install Date]+14

## Deleted Sites
Phase | Branch Category | RBVP ID | Field Prime | SIP Availability Date | Site Treatment | Transit | PC&B Branch Prime Contact Name & Number | DS Branch Prime Contact Name & Number | INS Branch Prime Contact Name & Number | Site Name | Hours of Op Monday | Hours of Op Tuesday | Hours of Op Wednesday | Hours of OP Thursday | Hours of Op Friday | Hours of Op Saturday | Hours of Op Sunday | Site address | Site city | Site province/state | Site postal/zip | Site country | Non-Emergency Stand Alone Phones Target Date | Non-Emergency Stand Alone Phones Completion Date | Number of Non-Emergency Stand Alone Phones Completed | Re-Cabling Required Y/N | Re-Cabling Target Completion Date | QOS Switch Upgrade Date | Require POE Switch Y/N | POE Switch Install Target Completion Date | MPLS Upgrade Required? | MPLS upgrade date | MPLS Order Submission Date | Critical Path date | Earliest Scheduled cutover date | Branch Audit Date | Cutover Date | On-site Training Date | Tech Prime | ADA Prime | Total Branch Centrex | CountOfPrimary_Number | IPT Today (1=Yes) | Concurrent Calls | Access Type | Device | Current Service Speed | Speed Kbps | IPT VLAN | Assigned IPT | Data | Data Other | NS Recommended Access | CostCentre_Name | NPA NNX | Bell SIP Avail | OCN of NPANXX/ OCN du IR/NXX | Prov. | Rate Centre/ Circonscription | PSTN CLLI (if known/s'il est connu) | Available/ Disponible | Regulated/Unregulated Réglementé/ Non Réglementé | Bell NPANXX (example only/ exemple seulement) | Broadsoft CLLI (ON/QC) | LIR | LRN | Change Request Number | Communication T-30 Date | Communication T-20 Date | Communication T-2 Date | Trunk Group Number | Description & PTN if Available | Service Extension Yes or No | Customer SBC Yes or No | Telephone Numbers Needed Total Quantity | Toll Free Total Quantity | Number of Concurrent Calls | Inbound,Outbound or Bi-directional | Overflow to Trunk Group provide Trunk | Destination Unreachable to PSTN | Destination Unreachable to Trunk Group | Outgoing Name Display | Outgoing Num ber Display | Number of CLID | Comments
|  |  | 801158 | Bell Canada | Available | [5 empty] | 0 | 1900-01-12 | 2014-08-14 | [5 empty] | 3932 | 1 | 12 |  | LANSDOWNE & ASHBURNHAM BRANCH | No | Info | [5 empty] | 198 LANSDOWNE ST E Part of Tr #3752 806 Chemong | PETERBOROUGH | Ontario | K9J 7N9 | Canada |  |  |  | #N/A |  | #N/A | #N/A | T1 | LANSDOWNE & ASHBURNHAM BR | 705743 | Yes/Oui |  |  | #REF! | [22 empty] | Part of Transit 3732 - 806 Chemog - no data. Site removed.
| CB |  | 800704 | Bell Canada | #N/A | [13 empty] | 2186 |  |  |  | 0 |  |  |  | Branch | Not | Opened |  | 1970 St Clair Avenue West - Suite 101 | Toronto | Ontario | M6N 0A3 | Canada | 0 | c02186br1 |  | 0 | TBD | 0 | 0 | #N/A | #N/A | T1 |  | This is a new location, scheduled to open Fall 2014 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A |  |  | #REF! | [22 empty] | This is a new location, scheduled to open Fall 2014 | VLOOKUPFIELDS FROM OLD MASTER ------->>>>>>>>> | 801471 | 9 | 800488 | 955 WESTNEY RD S-UNIT 2 | [24 empty] | Yes/Oui
| CB | 800748 | Bell Canada | #N/A | [12 empty] | 2413 |  |  |  | 0 |  |  |  | Branch | Not | Opened |  |  |  |  | 7955 Financial Dr | Brampton | Ontario | L6Y 0J8 | Canada | 0 | c02413br1 |  | 0 | TBD | 0 | 0 | #N/A | #N/A | T1 |  | This is a new location, scheduled to open July 2014 | #N/A |  |  |  |  | #N/A | #N/A |  | #N/A | #N/A | #N/A |  |  | #REF! | [22 empty] | This is a new location, scheduled to open July 2014 | VLOOKUPFIELDS FROM OLD MASTER ------->>>>>>>>> | 801204 | 7 | 800524 | 33 DOWNIE ST | [24 empty] | Yes/Oui
Branch Closing | PC&B | 801118 | Bell Aliant | Yes/Oui | 3822 |  | 6 |  |  | PLANTAGENET BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | Closed | Closed | 295 WATER ST | Plantagenet | Ontario | K0B1L0 | Canada | ADSL 1.5M/512Kbps | e03822br1 | 1 | DSL | 1500 | 0 | 10.138.66.128/25 | 10.191.13.129/26 | 0 | T1 | PLANTAGENET BRANCH | 613673 | Yes/Oui | BELL CANADA - ON | ON | Plantagenet | PTGTON68RS0 | Yes/Oui | (W) Unregulated / Non Réglementé | 613673 | ORLNON06CG0 | LIR-ON05 | 613-244-0016
Phase 2 Pilot | PC&B | 801700 | Bell Canada | Yes/Oui | PC&B | 7111 | Gail Lorde 514-624-8283 |  |  | GOUIN & MONK BRANCH | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 16:00 | Closed | 13135 BOUL GOUIN O | PIERRE FONDS | Quebec | H8Z1X1 | Canada |  |  | Y | TBD | #VALUE! | [7 empty] | #VALUE! | TBD |  |  |  | 22 | 20 |  | 9 | T1 1.544Mbps | e07111br1 | T1 | 1500 | 0 | 10.136.178.128/25 | 10.219.45.1/25 | 0 | T1 | GOUIN & MONK BRANCH | 514624 | Yes/Oui | BELL CANADA - QC | QC | Sainte-Geneviève | MTRLPQ54CG0 | Yes/Oui | (I) Unregulated / Non Réglementé | 514620 | MTRLPQ54CG0 | LIR-PQ09 | 514-342-9064 | [18 empty] | June 4 - Branch under renovations. DD moved to TBD. ***July 03 note: This site was migrated as part of the RBD project moving this location to the deleted sites tab
Rollout | site moving | 800515 | Bell Canada | Yes/Oui |  | 1616 |  |  |  | CAMBRIDGE BUSINESS CENTRE | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | closed | 15 SHELDON DR | CAMBRIDGE | Ontario | N1R 6R8 | Canada | #VALUE! |  |  | N | N/A | #VALUE! | [7 empty] | #VALUE! | CANCELLED - SITE CLOSING |  |  |  | 25 | 5 |  | 4 |  | c01616br1 | 5M | 5000 | 0 | 10.138.8.128/25 | 10.123.4.1/25 | 0 | T1 | CAMBRIDGE BUSINESS CENTRE | 519740 | Yes/Oui | BELL CANADA - ON | ON | Galt | GALTON04DS0 | Yes/Oui | (I) Unregulated / Non Réglementé | 519620 | GALTON04DS0 | LIR-ON43 | 519-570-0028
Rollout | P&CB | 801562 | Bell Canada | Yes/Oui |  | 6012 |  |  |  |  | 17:00 | 17:00 | 17:00 | 18:00 | 18:00 | 0.66667 | closed | 65 QUEEN ST. W. | TORONTO | Ontario | M5H2M5 | Canada | 2014-11-07 |  |  | N | N/A | 2014-10-29 | [7 empty] | 2014-10-29 | 2014-11-12 |  |  |  | 0 |  |  | error | T1 1.544Mbps | c06012br1 | T1 | 1500 | 0 | 10.138.104.128/25 | 10.135.2.129/26 | 0 | ERROR |  | 514874 | Yes/Oui | BELL CANADA - QC | QC | Montréal | MTRLPQ02CG4 | Yes/Oui | (W) Unregulated / Non Réglementé | 514201 | MTRLPQ43CG2 | LIR-PQ09 | 514-342-9064 |  |  | 41905 | 41950 |  | 5148743103 | montreal_01_5148743103 | [11 empty] | (514) 874, 340, 762 | Canadian Banking | 20 King St W - Concourse | Toronto | ON | M5H 1C4 | M5H1C4 |  | #N/A | #N/A | #N/A |  | #N/A | 14 | #N/A | #N/A | 41934
Rollout | P&CB | 800010 | Bell Canada | Yes/Oui |  | 59 |  |  |  | QUEENS QUAY BR | 17:00 | 17:00 | 17:00 | 20:00 | 18:00 | 0.66667 | closed | 207 Queen's Quay West | TORONTO | Ontario | M5J 1A7 | Canada | 2014-12-04 |  |  | N | N/A | 2014-11-25 | [7 empty] | 2014-11-25 | 2014-12-09 |  |  |  | 21 | 15 |  | 8 | Optical Ethernet | c00059cr1 | 5M | 5000 | 10.137.45.1/25 | 10.137.45.0/25 | 10.157.42.1/25 | 0 | T1 | TOR-QUEENS QUAY BR | 416955 | Yes/Oui | BELL CANADA - ON | ON | Toronto | TOROON01DS0 | Yes/Oui | (C) Unregulated / Non Réglementé | 416201 | TOROON27DS0 | LIR-ON06 | 416-360-0021 |  |  | 41933 | 41977 |  | 4163481342 | toronto_01_4163481342 | [12 empty] | Canadian Banking | 155 Wellington St W - 14th Flr | Toronto | ON | M5J 1A7 | M5J1A7 |  | 207 QUEENS QUAY W-UNIT 120 | TORONTO | ON |  | 17 | 1 | 18 | F | 41961
Rollout | P&CB | 801466 | Bell Canada | Yes/Oui |  | 5462 |  |  |  | Personal bankers | 17:00 | 17:00 | 17:00 | 17:00 | 18:00 | 0.66667 | closed | 831 COLLEGE ST MAIN FL | Toronto | Ontario | M6H1A1 | Canada | 2014-11-01 |  |  | N | N/A | 2014-10-23 | [7 empty] | 2014-10-23 | 2014-11-06 |  |  |  | 1 | 20 |  | 9 | T1 1.544Mbps | c05462br1 | T1 | 1500 | 10.138.103.1/25 | 10.136.216.0/25 | 10.143.4.129/25 | 0 | T1 | COLLEGE & OSSINGTON BRANCH | 416534 | Yes/Oui | BELL CANADA - ON | ON | Toronto | TOROON09CG1 | Yes/Oui | (C) Unregulated / Non Réglementé | 416201 | TOROON27DS0 | LIR-ON06 | 416-360-0021 |  |  | 41899 | 41946 |  | 4163481342 | toronto_01_4163481342 | [12 empty] | Canadian Banking | 833 College St | Toronto | ON | M6H 1A1 | M6H1A1 |  | 833 COLLEGE ST | TORONTO | ON |  | 16 |  | 16 | T | 41928
Rollout | P&CB | 800364 | Bell Canada | Yes/Oui |  | 1259 |  |  |  |  | 17:00 | 17:00 | 20:00 | 20:00 | 18:00 | 0.66667 | closed | 2500 UNIVERSITY DR NW | CALGARY | Alberta | T2N1N4 | Canada | -5 |  |  | CLOSED | N/A | #NUM! |  |  | Yes |  | no order |  |  | #NUM! |  |  |  |  | 0 | 54 |  | 19 | T1 1.544Mbps | w01259br6 | T1 | 1500 | 10.138.98.129/25 | 10.138.98.128/25 | 10.31.6.129/26 | 0 | 3M | Northland Plaza | 403292 | Yes/Oui | TELUS | AB | Calgary | CLGRAB01CG2 | Yes/Oui | (I) Regulated / Réglementé | 403355 | 0 | WR | 403-355-0001 |  |  | #NUM! | #NUM! | 0 | 41911 | [10 empty] | Transit 1259 (800364) 2500 University, AB. This row was removed from the Scheduled Tab and placed in the Deleted sit tab. There is no staff at this location, there is only 1 telephone line assocaited with student banking at the University of Calgary. | Canadian Banking | 107-383 Aspen Glen Landing SW | Calgary | AB | T2L 2L3 | T2L2L3 |  | 4820 NORTHLAND DR NW-SUITE 220 | CALGARY | AB |  | 63 | 1 | 64 | T | #NUM! | 59 |  | 59 | T | T | 1
Rollout | INS | 802896 | Bell Canada | Yes/Oui |  | 16110 |  |  |  | RBC Insurance | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 3960 Quadra St. | VICTORIA | British Columbia | V8X4A3 | Canada | 2014-12-03 |  |  | N | N/A | 2014-11-24 | [7 empty] | 2014-10-10 | 2014-12-08 |  |  |  | 5 | 10 |  | 6 | T1 1.544Mbps | Not found! C02186br1 | 5M | TBD | #N/A | 0 | #N/A | #N/A | T1 | RBC LIC SALES-VICTORIA | 250953 | Yes/Oui | TELUS | BC | Victoria | VCTABC011XD | Yes/Oui | (W) Regulated / Réglementé | 250220 | 0 | WR | 250-220-0002 |  |  | 41887 | 41976 | 0 | 41887 | [10 empty] | Transit 16110 (802896) 3960 Quadra St. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. This location was closed and was never re-opened. The cutover date was December 08th. Email was sent previouly to James for site replacement for December. | Insurance | 2985 Virtual Way - 3rd Flr Sui | Victoria | BC | V8X 4A3 | V8X4A3 |  | #N/A | #N/A | #N/A |  | 1 |  | 1 | F | 41915 | 1 |  | 1 | F | F |  | T
Rollout | P&CB | 802372 | Bell Canada | Yes/Oui |  | 10773 |  |  |  |  | 16:30 | 16:30 | 16:30 | 16:30 | 16:30 | Closed | Closed | 10117 JASPER AVE | EDMONTON | Alberta | T5J1W8 | Canada | 2014-12-05 |  |  | N | N/A | 2014-11-26 | [7 empty] | 2014-10-15 | 2014-12-10 |  |  |  | 82 | 15 |  | 8 | Optical Ethernet | w10773br1 | 10M | 10000 | 10.138.96.1/25 | 10.138.96.0/25 | 10.11.69.1/25 | 0 | T1 | HO PRIVATE BANKING EDMONTON | 780448 | Yes/Oui | TELUS | AB | Edmonton | EDTNABXMCG5 | Yes/Oui | (C) Regulated / Réglementé | 780409 | 0 | WR | 780-637-0002 |  |  | 41891 | 41978 | 0 | 0 | [10 empty] | Oct. 08: Transit 10773 (802372) P&CB 10117 Jasper Ave. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. The cutover date was scheduled for December 10. The staff has moved to the GU/Campus and are no longer part of the branch network. Email was sent previously to James for site replacement for December. | Canadian Banking | 10117 Jasper Ave | Edmonton | AB | T5J 1W8 | T5J1W8 | 10117 Jasper Ave | #N/A | #N/A | #N/A |  | 17 | 1 | 18 | F | 41919 | 15 | 2 | 17 | T | F |  | T
Rollout | P&CB/PH&N | 801103 | Bell Canada | Yes/Oui |  | 3779 |  |  |  | EDMONTON BUSINESS SALES & SERVICE | 16:30 | 16:30 | 16:30 | 16:30 | 16:30 | Closed | Closed | 10117 JASPER AVE | Edmonton | Alberta | T5J1W9 | Canada | -5 |  |  | N | N/A | #NUM! | [12 empty] | 59 | 14 |  | 7 | Optical Ethernet | w03779cr1 | 10M | 10000 | 10.136.31.129/25 | 10.136.31.128/25 | 10.19.43.1/24 | 0 | T1 | EDM-REAL ESTATE & CONSTRUCTION SERVS | 780448 | Yes/Oui | TELUS | AB | Edmonton | EDTNABXMCG5 | Yes/Oui | (C) Regulated / Réglementé | 780409 | 0 | WR | 780-637-0002 |  |  | #NUM! |  | 0 | 0 | [10 empty] | Oct 08: Transit 3779 (801103) P&CB /PH&N. 10117 Jasper Ave. This entry was taken off of the Scheduled Tab and placed in the Deleted Sites tab. The cutover date was a blank entry. The staff has moved to the GU/Campus and are no longer part of the branch network. Email was sent previously to James for site replacement for December. | Canadian Banking | 10117 Jasper Ave - 13th floor | Edmonton | AB | T5J 1W8 | T5J1W8 |  | #N/A | #N/A | #N/A |  | 14 | 20 | 34 | F | #NUM! |  | 10 | 10 | F | F |  | F | IP
Rollout | P&CB | 801529 | Bell Canada | Yes/Oui |  | 5855 |  |  |  |  | 17:00 | 17:00 | 17:00 | 20:00 | 20:00 | 0.66667 | closed | 4370 WELLINGTON ST | VERDUN | Quebec | H4G1W4 | Canada | 2014-10-31 |  |  | N | N/A | 2014-10-22 | [7 empty] | 2014-10-22 | 2014-11-05 |  |  |  | 0 |  |  | error | Optical Ethernet | e05855br1 | 5M | 5000 | 10.138.104.1/25 | 10.138.104.0/25 | 10.197.0.1/23 | 0 | ERROR |  | 514762 | Yes/Oui | BELL CANADA - QC | QC | Montréal | MTRLPQ48CG0 | Yes/Oui | (W) Unregulated / Non Réglementé | 514201 | MTRLPQ43CG2 | LIR-PQ09 | 514-342-9064 |  |  | 41898 | 41943 |  | 41918 | [10 empty] | (514) 762, 368 | Canadian Banking | 1 PVM - Mezzanine 2 | Montreal | QC | H3C 3A9 | H3C3A9 |  | #N/A | #N/A | #N/A |  | #N/A | 4 | #N/A | #N/A | 41927 |  | 3 | 3 | T | F |  | F | IP | 5855 | 4370 WELLINGTON ST | VERDUN | ON | H4G1W4 | 41948 | #N/A | #N/A | #N/A | #N/A | 4370 WELLINGTON ST VERDUN ON H4G1W4 | 4370WELLINGTONSTVERDUNONH4G1W4
Rollout | P&CB/PH&N | 801096 | Bell Canada | Yes/Oui |  | 3749 |  |  |  | MAIN BR - EDMONTON | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | 10107 JASPER AVE NW | EDMONTON | Alberta | T5J 1W9 | Canada | 2015-01-30 |  |  | N | N/A | 2015-01-21 | no |  | no |  |  |  |  | 2014-12-05 | 2015-02-04 |  |  |  | 41 | 38 |  | 14 | Bonded-T1 | w03749br1 | 5M | 5000 | #N/A | 10.137.133.128/25 | #N/A | #N/A | 3M | MAIN BR - EDMONTON | 780448 | Yes/Oui | TELUS | AB | Edmonton | EDTNABXMCG5 | Yes/Oui | (C) Regulated / Réglementé | 780409 | 0 | WR | 780-637-0002 |  |  | 41943 | 42034 | [12 empty] | Sept. 21 cutover date changed to TBD from Nov. 27. Site replacement required | Canadian Banking | 10107 Jasper Ave | Edmonton | AB | T6H 4M6 | T6H4M6 |  | 10107 JASPER AVE NW | EDMONTON | AB |  | 45 |  | 45 | T | 41971 | 39 |  | 39 | T | F | 10 | T |  | 3749 | 10107 JASPER AVE NW | EDMONTON | Alberta | T5J1W9 | 42039 | Ryan Guenette | 7809926449 | David Gallant | 7804486411 | 10107 JASPER AVE NW EDMONTON Alberta T5J1W9 | 10107JASPERAVENWEDMONTONAlbertaT5J1W9
Rollout | INS | 802442 | Bell Canada | Yes/Oui |  | 12113 |  |  |  | Rbc Insurance | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 1220 Lebourgneuf Street | Quebec City | Quebec | G2K2G4 | Canada | -5 | 2014-11-20 | 0 | N | N/A | #NUM! | no |  | no |  |  |  |  | #NUM! |  |  |  |  | 14 | 13 |  | 7 | T1 1.544Mbps | e12113sr1 | T1 | 1500 | 10.136.110.1/25 | 10.136.110.0/25 | 10.195.54.1/25 | 0 | T1 | RBC LIC-SALES QUE-QUEBEC CITY | 418654 | Yes/Oui | BELL CANADA - QC | QC | Québec | QUBCPQ09CG0 | Yes/Oui | (I) Regulated / Réglementé | 418260 | QUBCPQ03CG0 | LIR-PQ27 | 418-524-5732 |  |  | #NUM! | #NUM! | [12 empty] | Nov 26 LH: Donna advised 12113 office is closing and needs to be removed from schedule. TReplacement site required. *** Dec: 3 (ph) Removed from the Scheduled tab and placed for reference in the Deleted sites tab. This location is closing. | Insurance | 220 Montée Masson | Mascouche | QC | J7K 3B5 | J7K3B5 | 220 Montee Masson | #N/A | #N/A | #N/A |  | 16 |  | 16 | T | #NUM! | 14 |  | 14 | T | F |  | T |  | 12113 | Rbc Insurance | 1220 Lebourgneuf Street | Quebec City | Quebec | G2K2G4 | 1220 Lebourgneuf Street Quebec City Quebec G2K2G4 | 1220LebourgneufStreetQuebecCityQuebecG2K2G4
Rollout | P&CB | 800204 | Bell Canada | Yes/Oui |  | 716 |  |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 7133-7031 120TH ST | DELTA | British Columbia | V4E2A9 | Canada | 2015-03-25 |  |  | N | N/A | 2015-03-16 | no |  | no |  |  |  |  | 2015-01-29 | 2015-03-30 |  |  |  | 4 |  |  | 0 | T1 1.544Mbps | w00716br1 | T1 | 1500 | #N/A | 10.138.129.0/25 | #N/A | #N/A | T1 | Strawberry Hill | 604591 | Yes/Oui | TELUS | BC | Newton | SRRYBC02DS3 | Yes/Oui | (I) Unregulated / Non Réglementé | 604595 | 0 | WR | 604-595-0001 |  |  | 41995 | 42088 | [9 empty] | BRITISH COLUMBIA | Melanie Bird | Timothy Carmack | Dec 11 (ph) Removed from the schedule tab and placed in the Deleted Sites tab. The branch has closed, Donna has already requested site replacement. | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | 42026 |  |  | 0 | F | F |  | F | IP | 716 |  | 7133-7031 120TH ST | DELTA | British Columbia | V4E2A9 | 7133-7031 120TH ST DELTA British Columbia V4E2A9 | 7133-7031120THSTDELTABritishColumbiaV4E2A9
Rollout | P&CB | 801449 | Bell Canada | Yes/Oui |  | 5302 |  |  |  | ROSEDALE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | Closed | Closed | [15 empty] | 2014-12-09 | [7 empty] | 18 | 18 |  | 9 |  | c05302br5 | Other | 1500 | 10.136.42.1/25 | 10.136.42.0/25 | 10.155.5.1/25 | 0 | T1 | ROSEDALE BRANCH | 416313 | [5 empty] | Yes/Oui | (C) Unregulated / Non Réglementé | 416201 | TOROON27DS0 | LIR-ON06 | 416-360-0021
Rollout | P&CB | 803012 | Bell Canada | Yes/Oui |  | 17322 |  |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 6455 Jean Talon , E-Suite 701 | ST LEONARD | QUEBEC | H1S3E8 | CANADA | N/A | N/A | N/A | N | N/A | 2015-04-07 | no |  | no |  |  |  |  | 2015-04-07 | 2015-04-21 |  |  |  | 2 |  | 1 | 4 | 0 | e17322br1 | 5M | 5000 | 10.32.129.1/25 | 0 | 10.22.3.1/24 | 0 | T1 |  | 514899 | Yes/Oui | BELL CANADA - QC | QC | Montréal | MTRLPQ03CG1 | Yes/Oui | (W) Unregulated / Non Réglementé | 514201 | MTRLPQ43CG2 | LIR-PQ09 | 514-342-9064 |  | 17322 | 2015-02-27 | 2015-04-16 | [9 empty] | QUEBEC |  | Sonia Veilleux |  | Capital Markets | 42088 | 2 | 1 | 3 | Centrex |  | done |  | 5148743103 | montreal_01_5148743103 | 1 | 0 | Higher | 5147 | Yes | 2
Rollout | P&CB | 801402 | Bell Canada | Yes/Oui |  | 5050 |  |  |  | SOOKE BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 6660 SOOKE RD | SOOKE | BRITISH COLUMBIA | V9Z1N5 | CANADA | #REF! |  |  | N | N/A | #REF! | no |  | no |  |  |  |  | 42199 | 42257 |  |  |  | 17 | 16 |  | 8 | ADSL 1.5M/512Kbps | w05050br1 | T1 | 1500 | 10.32.145.129/25 | 0 | 10.22.36.1/24 | 0 | T1 | SOOKE BRANCH | 250642 | Yes/Oui | TELUS | BC | Sooke | SOKEBC01RS1 | Yes/Oui | (I) Unregulated / Non Réglementé | 250664 | 0 | WR | 250-664-0001 |  |  | 42163 | 42251 | [5 empty] | Joanne Walsh | 2506421111 | Joanne Kasika | 2506421102 | BRITISH COLUMBIA | Melanie Bird | Timothy Carmack | Dec 10 LH: Per Donna site to be scheduled once construction of new location is confirmed. Currently working out of a trailer. cabling CR | Canadian Banking | 42188 | 13 | 2 | 15 | Centrex |  | done |  | Need PTN | 0 | -2 | 8 | Same |  |  | 17
Rollout | P&CB | 801658 | Bell Canada | Yes/Oui |  | 7473 |  |  |  |  | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | closed | Closed | 260 SPADINA AVE | TORONTO | ONTARIO | M5T2E4 | CANADA | #VALUE! |  |  | N | N/A | #VALUE! | no |  | no |  |  |  |  | #VALUE! |  |  | TBD |  | 0 |  |  | 4 | T1 1.544Mbps | c06776br1 | 5M | 5000 | 10.138.105.1/25 | 10.138.105.0/25 | 10.139.0.129/26 | 0 | ERROR |  | 416974 | Yes/Oui | BELL CANADA - ON | ON | Toronto | TOROON63CG5 | Yes/Oui | (C) Unregulated / Non Réglementé | 416201 | TOROON27DS0 | LIR-ON06 | 416-360-0021 |  | 1491, 5023, 7473 | #VALUE! | #VALUE! |  | 42053 | [7 empty] | GREATER TORONTO REGION | Gail Ruivo | Dawn Adams-Cheung | 2/25/2015 Site will be ready in 2016 Transit being removed from Schedule Sept. 28: The cutover is TBD from a blank entry. Please coordinate the cutover date with 260 Spadina, Transit 7473 (801658). | #N/A | #VALUE! |  |  | 4 |  |  |  |  | 4163481342 | toronto_01_4163481342 | 4 |  | Higher | 5147 | Yes | 0
Rollout | PB | 809094 | Bell Canada | Yes/Oui |  | 10774 | 220 PORTAGE AVE-SUITE 200 | WINNIPEG | MANITOBA | [7 empty] | 42132 | 42192 | 42193 | [5 empty] | 6 | [10 empty] | 204 | [12 empty] | 00000, 7, 248, 367, 588, 767, 1387, 1663, 2553, 2997, 3657, 3667, 3723, 4687, 5727, 6117, 6283, 6907, 7047, 7673, 7907, 7946, 8067, 8197, 8577, 8648, 8987, 9457, 9914, 9940, 10774, 10794, 11265, 12023, 13850, 13967, 14169, 14283, 14947, 15120, 15795, 15911, 15984, 16504, 16547, 17174 | 42139 | 42187 | [9 empty] | MAN/SASK NORTHWEST ONTARIO | Jeff Zacharias | Rob Loeppky | [16 empty] | 42123 | [13 empty] | R3C 0A5 |  |  | 7 |  | 7 |  |  | done |  |  |  | 7 |  | Higher | 5258 | Yes
Rollout | P&CB | 801650 | Bell Canada | Yes/Oui |  | 6752 |  |  |  | DUNDAS & SPADINA BRANCH | 17:00 | 17:00 | 17:00 | 17:00 | 17:00 | 16:00 | Closed | 500 DUNDAS ST W | TORONTO | ONTARIO | M5T1G9 | CANADA | N/A | N/A | N/A | N | N/A | 42243 | no |  | no |  |  |  |  | 42242 | 42257 |  |  |  | 32 | 35 | 1 | 17 | Optical Ethernet | c06752br1 | 5M | 5000 | 10.137.14.129/25 | 10.137.14.128/25 | 10.135.49.1/25 | 0 | 3M | DUNDAS & SPADINA BRANCH | 416313 | Yes/Oui | BELL CANADA - ON | ON | Toronto | TOROON63CG5 | Yes/Oui | (C) Unregulated / Non Réglementé | 416201 | TOROON27DS0 | LIR-ON06 | 416-360-0021 |  | 1491, 4361, 6752, 13977, 16626 | 42206 | 42251 |  | 42045 | [5 empty] | Irene Lew | 4169740060 | GREATER TORONTO REGION | Gail Ruivo | Dawn Adams-Cheung | 2/25/2015 Site will be ready in 2016 Transit being removed from Schedule Sept. 28: The cutover is TBD from a blank entry. Please coordinate the cutover date with 260 Spadina, Transit 7473 (801658). | Canadian Banking | 42233 | 45 | 1 | 46 | Centrex | 1 | done |  | 4163481342 | toronto_01_4163481342 | 14 | 14 | Higher | 5626 | Yes | 32
Rollout | PB | 809077 | Bell Canada | Yes/Oui |  | 10773 |  |  |  | HO PRIVATE BANKING EDMONTON | [7 empty] | 10117 JASPER AVE-SUITE 1400 | EDMONTON | ALBERTA | T5J1W8 | CANADA | 42154 |  |  | N | N/A | [8 empty] | 42102 | 42159 | 42160 | [5 empty] | 18 | [10 empty] | 780944 | [12 empty] | 208, 1489, 2480, 2729, 2829, 3420, 3639, 3697, 3779, 4759, 6125, 6805, 7793, 8019, 8749, 9908, 9955, 10773, 11263, 11837, 14168, 14393, 15986, 17317, 17395 | 42109 | 42156 | [9 empty] | ALBERTA & TERRITORIES |  |  |  |  | 42089 | 27 | 8 | 35 | Centrex |  | done |  |  |  | 35 |  | Higher | 8788 | Yes |  |  | 25
Rollout | DS | 803105 | Bell Canada | Yes/Oui |  | 90701 | [11 empty] | 333 7TH AVE SW - 14TH FLR CALGARY AB CANADA T2P 2Z1 | CALGARY | ALBERTA | T2P2Z1 | CANADA | N/A | N/A | N/A | N | N/A | 42152 | no |  | no |  |  |  |  | 42152 | 42166 | 42167 |  |  | 7 | 12 | 1 | 86 |  | 0 | 0 | TBD | #N/A | 0 | #N/A | #N/A | T1 | ? | 403266 | [11 empty] | ? | ? | 42072 | 42163 |  | 42069 | Cal Malhiot | Tracy Trimming, Carly Blackman | ? |  |  |  |  | ALBERTA & TERRITORIES | Rhonda Graham | Dan Chipak | ? | Wealth Management | 42096 | 31 | 239 | 270 | IP |  | done |  | #N/A | #N/A | 263 |  | Higher | 17436 |  | 7 |  | 1
Rollout | INS | 809106 | Bell Canada | Yes/Oui |  | 15229/11287 |  |  |  | CALGARY MAIN | 16:00 | 16:00 | 16:00 | 16:00 | 16:00 | Closed | Closed | 195-315 8th Ave SW | CALGARY | ALBERTA | T2P4K1 | CANADA | 42158 |  |  | N | N/A | 42149 | [8 empty] | 42163 | [6 empty] | 5 | [23 empty] | 11287, 14694, 15229, 15316 | 42067 | 42158 | [9 empty] | ALBERTA & TERRITORIES |  | Dan Chipak | 4/10/2015 Res from July 16 to June 8 - No sets IPT siet / Marcus to add Co-hab TR 14694 ( 3 users) |  | 42093 | 1 | 7 | 8 | IP |  | done |  |  |  | 8 |  | Higher | 5294 | Yes |  |  | 4
Rollout | PB | 809107 | Bell Canada | Yes/Oui |  | 14694 |  |  |  | LANGLEY HO PB-LANGLEY/FRASER VALLEY | [7 empty] | 195-315 8th Ave SW | CALGARY | ALBERTA | T2P4K1 | CANADA | -5 |  |  |  |  | #NUM! | [39 empty] | 11287, 14694, 15229, 15316 | #NUM! | #NUM! | [9 empty] | ALBERTA & TERRITORIES |  | Dan Chipak |  |  | #NUM! |  |  | 3 | Centrex | [12 empty] | 4
Rollout | PB | 809090 | Bell Canada | Yes/Oui |  | 809 |  |  |  | DOMESTIC PRIVATE BANKING - EXECUTIVE | [7 empty] | 200 BAY ST-14TH FLR/S TWR | TORONTO | ONTARIO | M5J2J5 | CANADA | 42203 |  |  | N | N/A | [9 empty] | 42208 | 42209 | 42210 | 42211 |  |  |  | 47 | [10 empty] | 416 | [13 empty] | 42115 | 42205 | [9 empty] | GREATER TORONTO REGION |  | Dawn Adams-Cheung |  |  | 42179 | 11 | 117 | 128 | IP |  | done |  |  |  | 128 |  | Higher | 12210
Rollout | PB | 809086 | Bell Canada | Yes/Oui |  | 14259 |  |  |  | EDM AB-CSR POOL-EDM NW | [7 empty] | 9499 137TH AVENUE-UNIT 1032 | EDMONTON | ALBERTA | T5E5R8 | CANADA | 42175 |  |  | N | N/A |  | no |  | Yes | 41878 | 41757 |  |  |  | 42180 | 42181 | [5 empty] | 18 |  | w04629br1 | 3M | 3000 | 10.137.228.129/25 | [5 empty] | 780944 |  | TELUS | AB | Edmonton | EDTNABXMCG5 | Yes/Oui | (C) Regulated / Réglementé | 780409 | 0 | WR | 780-637-0002 |  | 1625, 2480, 3223, 4629, 7927, 9679, 9955, 10451, 20452, 14257, 14258, 14259, 14986, 17316, | 42083 | 42177 |  | 42094 | [7 empty] | ALBERTA & TERRITORIES |  | Dan Chipak |  |  | 42111 | 34 | 3 | 37 | Centrex |  | done |  | 780-670-2348 | edmonton_01_7806702348 | 37 |  | Higher | 8862 |  |  | 1 | 15
Rollout | DS | 803068 | Bell Canada | Yes/Oui |  | 90531 |  |  |  | RBC INVESTMENTS | 0.72917 | 0.72917 | 0.72917 | 0.72917 | 0.72917 | closed | Closed | 50 QUEEN ST W SUITE #300 | BRAMPTON | ONTARIO | L6X4H3 | CANADA | 42161 |  |  | N | N/A | 42152 | no |  | no |  |  |  |  | 42152 | 42166 | 42167 |  |  | 56 | 55 |  | 10 | Bonded-T1 | c90531vr1 | 5M | 5000 | 10.137.171.129/25 | 10.137.171.128/25 | #N/A | #N/A | 5M | ON RBCDS INC-BRAMPTON | 905951 | Yes/Oui | BELL CANADA - ON | ON | Bolton | BOTNON12RSA | Yes/Oui | (I) Regulated / Réglementé | 905857 | WDBGON48CG0 | LIR-ON45 | 905-886-0026 |  | 0 | 42116 | 42163 |  |  | Hugh Connor | 0 | 0 |  |  |  |  | GREATER TORONTO REGION |  | Dawn Adams-Cheung |  | Wealth Management | 42143 | 13 | 2 | 15 | Centrex |  |  |  | 905-951-2017 | bolton_01_9059512017 | -41 | 25 | Lower | 5552 | Yes | 56 | 1 | 1
Rollout | P&CB | 801959 | Bell Canada | Yes/Oui |  | 8371 |  |  |  | LA PLAZA BRANCH | 0.70833 | 0.70833 | 0.70833 | 0.83333 | 0.70833 | 0.66667 | Closed |  | SHAWINIGAN | QUEBEC | G9N7C1 | CANADA | 42154 |  |  | N | N/A | 42145 | no |  | Yes | 41864 | 41809 |  |  | 42139 | 42159 |  |  |  | 17 | 18 |  | 9 | ADSL 1.5M/512Kbps | e08371br1 | T1 | 1500 | 10.138.106.1/25 | 10.138.106.0/25 | 10.219.0.129/25 | 0 | T1 | LA PLAZA BRANCH | 819539 | Yes/Oui | BELL CANADA - QC | QC | Shawinigan | SHGNPQ37DS0 | Yes/Oui | (C) Regulated / Réglementé | 819534 | SHGNPQ37DS0 | LIR-PQ21 | 819-537-9321 |  | 1531, 8371, 17224 | 42109 | 42156 |  | 42109 |  |  |  | Theresia Bucher | 8195396689 |  |  | QUEBEC | Annie Roux | Sonia Veilleux | 3/11/2015 June schedule approved by BellA ddress to be reviewed | Canadian Banking | 42135 | 17 | 1 | 18 | Centrex |  | done |  | 0 | 0 | 1 | 9 | Same | 5662 | Yes | 17 | 1 | 3
Rollout | PB (GU) | 809079 | Bell Canada | Yes/Oui |  | 10775 |  |  |  | HO PRIVATE BANKING VANCOUVER | [7 empty] | 1055 W GEORGIA ST-5TH FLR | VANCOUVER | BRITISH COLUMBIA | V6E3P3 | CANADA | 42215 |  |  | N | N/A | [8 empty] | 42160 | 42220 | 42221 | [5 empty] | 16 | [10 empty] | 604665 | [12 empty] | 00000, 10, 1154. 1197, 1553, 1649, 1655, 1661, 1664, 1679, 1739, 1830, 2120, 2810, 2970, 3271, 3290, 3617, 4000, 4098, 4323, 4434, 4712, 4945, 5130, 5560, 5617, 5717, 57777, 5825, 5910, 6160, 6257, 6318, 6654, 6785, 7700, 7753, 7797, 7864, 7940, 7953, 8120, 8390, 8700, 8800, 8850, 8860, 8890, 9340, 9360, 9687, 9770, 9929, 9931, 10261, 10689, 10691, 10692, 10694, 10695, 106096, 10725, 10775, 10776, 11687, 11835, 13826, 14167, 14302, 14415, 14590, 14829, 14950, 14967, 14975, 15539, 15609, 15668, 155669, 15672, 15881, 15883, 15950, 15987, 15993, 16046, 16146, 16160, 16369, 16550, 16733, 17229, 17315, 17316, 17478, 17993, 83617, 90803, 90841, 90842, 90862, 90868, 90933 | 42124 | 42214 |  | 42124 | [7 empty] | BRITISH COLUMBIA | Elaine Sanderson | Timothy Carmack |  |  | 42151 | 4 | 26 | 30 | IP |  | done |  |  |  | 30 |  | Higher | 6104 | Yes |  |  | 103 | [10 empty] | #N/A
Rollout | PB | 809075 | Bell Canada | Yes/Oui |  | 10769 |  |  |  | HO PRIVATE BANKING LONDON | [7 empty] | 383 RICHMOND ST-SUITE 803 | LONDON | ONTARIO | N6A3C4 | CANADA | 42203 |  |  | N | N/A | [8 empty] | 42194 | 42208 | 42209 | [5 empty] | 22 | [10 empty] | 519661 |  | BELL CANADA - ON | ON | London | LONDON14CG0 | Yes/Oui | (I) Regulated / Réglementé | 519430 | LONDON14DS1 | LIR-ON31 | 519-660-0014 |  | 00000, 248, 2444, 2494, 2692, 2722, 2732, 2786, 2796, 3477, 5512, 7045, 7205, 7845, 9317, 10769, 13979, 15980, 16063, 16714, 17392, 17481, 95089 | 42157 | 42205 |  | 42157 | [7 empty] | ONTARIO SOUTH WEST REGION |  |  |  |  | 42184 | 22 | 26 | 48 | IP |  | done |  | 519-472-2017 | london_01_5194722017 | 48 |  | Higher | 9266 | Yes |  |  | 23
Formulas:
Site Name = IF([DS Branch Prime Contact Name & Number]="YES",WORKDAY([Hours of Op Wednesday],-120),"")
Hours of Op Monday = MAX([Site Treatment]:[PC&B Branch Prime Contact Name & Number])
Hours of Op Tuesday = WORKDAY([Hours of Op Monday],10)
Re-Cabling Target Completion Date = WORKDAY([Branch Audit Date],-10)
Earliest Scheduled cutover date = WORKDAY([Branch Audit Date],-10)
QOS Switch Upgrade Date = WORKDAY([Cutover Date],-10)
Branch Audit Date = WORKDAY([Cutover Date],-10)
Branch Audit Date = WORKDAY([Cutover Date],-40,HOLIDAY)
Communication T-20 Date = WORKDAY([Cutover Date], -35, HOLIDAY)
Communication T-2 Date = WORKDAY([Cutover Date],-3,HOLIDAY)
Note on J1: Maclean, Leslie (CWM-NR): From Telemanager, manually entered
Note on AL16: 540818382: Patricia Hillis Site replacement needed. To be scheduled after March 2015
Note on DJ16: 540818382: Patricia Hillis Site replacement needed. To be scheduled after March 2015

## Removed Data
RBVP ID | Site address | Site city | Site province/state | Site postal/zip | Site country | Device | unknown | Current Service Speed | IPT VLAN | Assigned IPT | Data | Data Other | NS Recommended Access
800001 | 100 KING ST | SAINT JOHN | New Brunswick | E2L1G4 | Canada | e00004br1 |  | 5M | 0 | 10.138.11.0/25 | 10.203.37.1/25 | 0 | T1
800002 | 700 PLACE D`YOUVILLE | QUEBEC | Quebec | G1R3P2 | Canada | e00005br1 |  | 5M | 0 | 10.137.17.0/25 | 10.197.65.1/24 | 0 | T1
800003 | 865 Milner Ave. | SCARBOROUGH | Ontario | M1B5N6 | Canada | c00022br1 |  | T1 | 0 | 10.136.118.0/25 | 10.157.54.1/25 | 0 | T1
800004 | 40 Taunton Rd. E. | Whitby | Ontario | L1R0A1 | Canada | c00024br1 | 1 | T1 | 0 | 10.137.54.128/25 | 10.157.43.1/25 | 0 | 3M
800005 | 9980 Mcvean Dr. | BRAMPTON | Ontario | L6P 2S5 | Canada | c00027br1 |  | T1 | 0 | 10.137.55.0/25 | 10.157.68.1/25 | 0 | T1
800006 | 1005 King St. W. | Toronto | Ontario | M6K3M8 | Canada | c00034br1 | 1 | T1 | 0 | 10.137.56.128/25 | 10.157.41.1/25 | 0 | T1
800007 | 510 RUE SACRE COEUR O | ALMA | Quebec | G8B1L9 | Canada | e00041br1 | 1 | DSL | 0 | 10.137.246.128/25 | 10.207.44.1/25 | 0 | T1
800008 | 2 HARWOOD AV S | AJAX | Ontario | L1S7L8 | Canada | c00042br1 | 1 | DSL | 0 | 10.138.89.0/25 | 10.127.41.1/25 | 0 | 3M
800009 | 715 FISCHER HALLMAN RD | KITCHENER | Ontario | N2E 4E9 | Canada | c00056br1 |  | 5M | 0 | 10.137.4.128/25 | 10.157.61.1/25 | 0 | T1
800010 | 207 Queen's Quay West | TORONTO | Ontario | M5J 1A7 | Canada | c00059cr1 |  | 5M | 0 | 10.137.45.0/25 | 10.157.42.1/25 | 0 | T1
800011 | 440 MAIN ST S | ALEXANDRIA | Ontario | K0C1A0 | Canada | e00062br1 | 1 | DSL | 0 | 10.138.52.0/25 | 10.191.7.1/26 | 0 | T1
800012 | 585 Saint-charles Ave., Suite 30 | Vaudreuil Dorion | Quebec | J7V8P9 | Canada | e00077br1 |  | T1 | 0 | 10.136.154.128/25 | 10.195.46.1/25 | 0 | T1
800013 | 33780 South Fraser Way | Abbotsford | British Columbia | V2S 5M4 | Canada | w00080br1 |  | 5M | 0 | 10.136.52.0/25 | 10.23.59.1/25 | 0 | 3M
800014 | 6680 BOUL JOSEPH RENAUD | ANJOU | Quebec | H1K3V4 | Canada | e00081br1 |  | T1 | 0 | 10.136.255.0/25 | 10.187.6.129/26 | 0 | T1
800016 | 443 OTTAWA ST | ALMONTE | Ontario | K0A 1A0 | Canada | e00082br1 |  | 5M | 0 | 10.137.108.0/25 | 10.179.9.1/26 | 0 | T1
800017 | 117 CENTRE POINTE DR | NEPEAN | Ontario | K2G5X3 | Canada | e00084br1 | 1 | T1 | 0 | 10.137.206.0/25 | 10.187.44.1/25 | 0 | T1
800018 | 438 King St. W.----unit 5 And 6 | Toronto | Ontario | M5V3T9 | Canada | c00085br1 | 1 | T1 | 0 | 10.137.63.0/25 | 10.157.57.1/25 | 0 | T1
800019 | 7675 Markham Rd. | Markham | Ontario | L3S3J9 | Canada | c00086br1 |  | T1 | 0 | 10.137.2.128/25 | 10.135.63.1/25 | 0 | T1
800021 | 839 Rte Jean-gauvin | QUEBEC | Quebec | G1X4V9 | Canada | e00095br1 |  | T1 | 0 | 10.136.103.128/25 | 10.195.9.1/26 | 0 | T1
800023 | 59 WILSON ST W | ANCASTER | Ontario | L9G 1N1 | Canada | c00102br1 |  | 5M | 0 | 10.137.76.0/25 | 10.167.1.129/26 | 0 | T1
800026 | 103 VICTORIA ST E | AMHERST | Nova Scotia | B4H1X9 | Canada | e00113br1 |  | T1 | 0 | 10.136.104.0/25 | 10.215.0.1/26 | 0 | T1
800027 | 230 MAIN ST | BATHURST | New Brunswick | E2A 1A8 | Canada | e00114br1 |  | 5M | 0 | 10.137.17.128/25 | 10.219.36.1/25 | 0 | 3M
800028 | 140 GRANDE ALLEE EAST-SUITE 10 | QUEBEC | Quebec | G1R 5M8 | Canada | e00115cr1 |  | 5M | 0 | 10.137.162.0/25 | 10.219.40.1/25 | 0 | T1
800029 | 745 BANK ST | OTTAWA | Ontario | K1S 3V3 | Canada | e00116br1 | 1 | T1 | 0 | 10.136.112.0/25 | 10.179.38.1/25 | 0 | T1
800030 | 160 MAIN ST | IROQUOIS FALLS | Ontario | P0K 1G0 | Canada | c00122br1 |  | T1 | 0 | 10.136.118.128/25 | 10.131.7.1/26 | 0 | T1
800035 | 2495 Appleby Line | BURLINGTON | Ontario | L7L0B6 | Canada | c00124br1 | 1 | T1 | 0 | 10.136.119.0/25 | 10.157.56.1/25 | 0 | T1
800036 | 12612 Hwy 50 | BOLTON | Ontario | L7E1T6 | Canada | c00126br1 | 1 | T1 | 0 | 10.137.64.0/25 | 10.157.60.1/25 | 0 | 3M
800037 | 16591 Yonge St. | NEWMARKET | Ontario | L3X 2G8 | Canada | c00128br1 |  | T1 | 0 | 10.136.119.128/25 | 10.157.4.129/26 | 0 | T1
800038 | 161 King St. E. | TORONTO | Ontario | M5C 1G9 | Canada | c00131br1 |  | 5M | 0 | 10.137.76.128/25 | 10.157.52.1/25 | 0 | T1
800039 | 473 Eglinton Ave. W. | Toronto | Ontario | M5N1A7 | Canada | c00139br1 |  | T1 | 0 | 10.136.120.0/25 | 10.157.51.1/25 | 0 | T1
800040 | 700 700 Matheson Blvd. W | Mississauga | Ontario | L5R3T2 | Canada | c00143br1 |  | 5M | 0 | 10.137.64.128/25 | 10.157.49.1/25 | 0 | T1
800041 | 2955 Hazelton Place | Mississauga | Ontario | L5M6J3 | Canada | c00144br1 | 1 | T1 | 0 | 10.137.65.128/25 | 10.157.64.1/25 | 0 | T1
800042 | 28 SANDIFORD DRIVE | STOUFFVILLE | Ontario | L4A 7X5 | Canada | c00150br1 | 1 | T1 | 0 | 10.137.66.0/25 | 10.167.14.129/25 | 0 | T1
800043 | 4300 Innes Rd. | Orleans | Ontario | K4A5E6 | Canada | e00155br1 |  | T1 | 0 | 10.136.155.0/25 | 10.157.58.1/25 | 0 | T1
800044 | 1881 Steeles Ave. W. | Toronto | Ontario | M3H5Y4 | Canada | c00157br1 | 1 | T1 | 0 | 10.136.120.128/25 | 10.157.59.1/25 | 0 | T1
800045 | 106 1st Ave W | Assiniboia | Saskatchewan | S0H 0B0 | Canada | w00158br5 |  | Other | 0 | 10.136.52.128/25 | 10.35.3.129/26 | 0 | T1
800046 | 27510 FRASER HWY | Aldergrove | British Columbia | V4W3N5 | Canada | w00160br1 |  | T1 | 0 | 10.138.80.128/25 | 10.63.9.129/26 | 0 | T1
800047 | 135 BURLEIGH ST --HWY #28 | APSLEY | Ontario | K0L1A0 | Canada | c00162br1 |  | T1 | 0 | 10.136.250.0/25 | 10.127.13.1/26 | 0 | T1
800048 | 231 CHAMPLAIN ST | DIEPPE | New Brunswick | E1A 1N9 | Canada | e00170cr1 |  | 10M | 10.32.5.1/26 |  | 10.179.42.1/25 | 0 | T1
800049 | 300 5th Avenue - Suite 620 | CALGARY | Alberta | T2P3C4 | Canada | w00177br1 |  | 10M | 0 | 10.138.95.0/25 | 10.22.21.1/24 | 0 | T1
800050 | 16919 24th St Sw | Calgary | Alberta | T2Y 0J3 | Canada | w00180br5 |  | Other | 0 | 10.136.53.0/25 | 10.75.51.1/25 | 0 | T1
800052 | 91 JOHN ST N | ARNPRIOR | Ontario | K7S2N4 | Canada | e00182br1 | 1 | DSL | 0 | 10.138.52.128/25 | 10.191.48.1/25 | 0 | T1
800053 | 45 Wicksteed Ave--Unit 10 | TORONTO | Ontario | M4G4H9 | Canada | c00189br1 | 1 | T1 | 0 | 10.137.3.0/25 | 10.157.7.129/26 | 0 | 3M
800054 | 3300 HIGHWAY 7-SUITE 100 , CONCORD , ON, L4K 4M3 | Concord | Ontario | L4K4M3 | Canada | c00192cr1 | 1 | 20M | 0 | 10.138.131.128/25 | 10.123.70.1/24 | 10.121.10.1/24 | 3M
800055 | 7188 West Saanich Road | BRENTWOOD BAY | British Columbia | V8M 1P6 | Canada | w00200br1 |  | T1 | 0 | 10.136.226.128/25 | 10.11.16.1/26 | 0 | T1
800056 | 804 Parsons Rd. S.W. | Edmonton | Alberta | T6X0B4 | Canada | w00201br1 | 1 | T1 | 0 | 10.137.217.0/25 | 10.75.48.1/25 | 0 | T1
800057 | 199 GEORGE ST | ARTHUR | Ontario | N0G1A0 | Canada | c00202br1 | 1 | DSL | 0 | 10.137.254.0/25 | 10.131.15.1/26 | 0 | T1
800059 | 1908 38th Ave. N.w. | Edmonton | Alberta | T6T0B9 | Canada | w00212br1 | 1 | T1 | 0 | 10.137.217.128/25 | 10.75.53.1/25 | 0 | T1
800061 | 327a La Salle Blvd | Baie Comeau | Quebec | G4Z 2L5 | Canada | e00221br5 |  | Other | 0 | 10.136.44.128/25 | 10.183.8.1/26 | 0 | T1
800062 | 112 WEST MAIN ST | ATIKOKAN | Ontario | P0T1C0 | Canada | w00222br1 |  | T1 | 0 | 10.138.81.0/25 | 10.19.2.1/26 | 0 | T1
800063 | 248 ST GEORGE ST | ANNAPOLIS ROYAL | Nova Scotia | B0S1A0 | Canada | e00223br1 | 1 | DSL | 0 | 10.138.53.0/25 | 10.191.11.129/26 | 0 | T1
800064 | 15 IRVING BLVD | BOUCTOUCHE | New Brunswick | E4S3J4 | Canada | e00224br1 | 1 | DSL | 0 | 10.138.53.128/25 | 10.183.2.129/26 | 0 | T1
800065 | 1535 BANK ST | Ottawa | Ontario | K1H7Z1 | Canada | e00226br1 | 1 | T1 | 0 | 10.136.155.128/25 | 10.187.49.1/25 | 0 | T1
800067 | 6233 199 St. N.W. | Edmonton | Alberta | T5T2P4 | Canada | w00229br1 | 1 | T1 | 0 | 10.137.218.0/25 | 10.75.45.1/25 | 0 | T1
800068 | 15408 YONGE ST | Aurora | Ontario | L4G1N9 | Canada | c00232br1 | 1 | T1 | 0 | 10.136.121.0/25 | 10.127.35.1/25 | 0 | T1
800069 | 16508 50 St NW | EDMONTON | Alberta | T5Y 0L2 | Canada | w00234cr1 |  | 5M | 0 | 10.138.21.128/25 | 10.75.63.1/25 | 0 | T1
800070 | 99 BANK ST | Ottawa | Ontario | K1P6B9 | Canada | e00236br1 | 1 | T1 | 0 | 10.137.206.128/25 | 10.179.37.1/25 | 0 | T1
800071 | 130 Adelaide St. W. - Unit 105 | Toronto | Ontario | M5H3P5 | Canada | c00238br1 |  | T1 | 0 | 10.136.121.128/25 | 10.157.66.1/25 | 0 | T1
800073 | 7 TALBOT ST W | AYLMER | Ontario | N5H 1J6 | Canada | c00242br1 |  | T1 | 0 | 10.136.122.0/25 | 10.127.18.129/26 | 0 | T1
800078 | 495 Charolais Blvd. | BRAMPTON | Ontario | L6Y0M2 | Canada | c00257br1 |  | T1 | 0 | 10.137.70.128/25 | 10.157.65.1/25 | 0 | T1
800080 | 6140 Highway 7 | WOODBRIDGE | Ontario | L4H0R2 | Canada | c00258br1 | 1 | T1 | 0 | 10.137.71.0/25 | 10.157.27.1/25 | 0 | T1
800081 | 523 Louisa St MAIN COMPUTER ROOM | Ayton | Ontario | N0G 1C0 | Canada | c00262br1 |  | T1 | 0 | 10.138.97.0/25 | 10.127.14.1/26 | 0 | T1
800082 | 650 PRINCIPALE ST | CASSELMAN | Ontario | K0A1M0 | Canada | e00266br1 | 1 | DSL | 0 | 10.138.54.0/25 | 10.191.4.1/26 | 0 | T1
800083 | 602 PARK AVE E-PO BOX 370 | BEAUSEJOUR | Manitoba | R0E 0C0 | Canada | w00267br1 |  | 5M | 0 | 10.138.117.128/25 | 10.79.2.1/25 | 0 | T1
800084 | 1501 Innisfil Beach Road | INNISFIL | Ontario | L9S4B2 | Canada | c00272br1 | 1 | T1 | 0 | 10.136.225.0/25 | 10.139.16.1/25 | 0 | T1
800086 | 892 Heritage Blvd. W. | LETHBRIDGE | Alberta | T1K7V5 | Canada | w00285br1 |  | T1 | 0 |  | 10.75.44.1/25 | 0 | T1
800088 | 2938 Rue De La Faune | Wendake | Quebec | G0A4V0 | Canada | e00288br1 |  | T1 | 0 | 10.136.156.0/25 | 10.179.44.1/25 | 0 | T1
800089 | 99 MAPLEVIEW DR W | BARRIE | Ontario | L4N 9H7 | Canada | c00292br1 |  | 5M | 0 | 10.137.72.128/25 | 10.139.41.1/25 | 0 | 3M
800090 | 53 BAYFIELD ST | BARRIE | Ontario | L4M3A6 | Canada | c00302br1 | 1 | T1 | 0 | 10.137.73.0/25 | 10.131.48.1/25 | 0 | 3M
800091 | 60 Copper Creek Dr. | Markham | Ontario | L6B0P2 | Canada | c00313br1 |  | T1 | 0 | 10.137.73.128/25 | 10.157.21.1/25 | 0 | T1
800092 | 220 MONTEE MASSON | MASCOUCHE | Quebec | J7K 3B5 | Canada | e00314cr1 |  | 5M | 0 | 10.137.50.128/25 | 10.195.50.1/25 | 0 | T1
800093 | 670 KINGSTON RD-UNIT 109 | PICKERING | Ontario | L1V 1A6 | Canada | c00316cr1 |  | 5M | 0 | 10.137.45.128/25 | 10.157.26.1/25 | 0 | T1
800094 | 100 Main St NE | AIRDRIE | Alberta | T4B 0R3 | Canada | w00319br1 |  | 5M | 0 | 10.137.120.0/25 | 10.55.48.1/25 | 0 | 3M
800095 | 4370 KINGSWAY | Burnaby | British Columbia | V5H4G9 | Canada | w00320br1 |  | 5M | 0 | 10.137.120.128/25 | 10.79.68.1/24 | 0 | 3M
800096 | 128 WELLINGTON ST W | BARRIE | Ontario | L4N8J6 | Canada | c00322br1 | 1 | T1 | 0 | 10.137.81.128/25 | 10.131.47.1/25 | 0 | 3M
800097 | 8 GREEN LANE | THORNHILL | Ontario | L3T7P7 | Canada | c00324br1 |  | T1 | 0 | 10.137.90.128/25 | 10.151.6.1/25 | 0 | T1
800099 | 181 CHATHAM ST | BLENHEIM | Ontario | N0P1A0 | Canada | c00332br1 | 1 | DSL | 0 | 10.137.254.128/25 | 10.135.6.1/26 | 0 | T1
800101 | 236 MAIN ST | ANTIGONISH | Nova Scotia | B2G 2C2 | Canada | e00333br1 |  | 5M | 0 | 10.138.11.128/25 | 10.215.0.129/26 | 0 | T1
800102 | 161 ROSEBERRY ST | CAMPBELLTON | New Brunswick | E3N 2H2 | Canada | e00334br1 |  | 5M | 0 | 10.137.18.0/25 | 10.215.3.1/26 | 0 | T1
800103 | 2450 LAURIER BLVD Suite #2 | QUEBEC | Quebec | G1V 2L1 | Canada | e00335br1 |  | 5M | 0 | 10.137.108.128/25 | 10.199.74.1/24 | 0 | 3M
800104 | 375 MAIN ST | BATH | Ontario | K0H 1G0 | Canada | c00342br1 | 1 | DSL | 0 | 10.137.255.0/25 | 10.139.11.129/26 | 0 | T1
800105 | 6040 GLEN ERIN DR | Mississauga | Ontario | L5N3M4 | Canada | c00354br1 | 1 | T1 | 0 | 10.137.95.0/25 | 10.123.0.129/25 | 0 | T1
800106 | 106 Beaurepaire Dr. | BEACONSFIELD | Quebec | H9W0A1 | Canada | e00361br1 | 1 | T1 | 0 | 10.136.156.128/25 | 10.199.48.1/25 | 0 | T1
800107 | 4310 ONTARIO ST | BEAMSVILLE | Ontario | L0R1B0 | Canada | c00362br1 | 1 | DSL | 0 | 10.137.255.128/25 | 10.127.8.1/26 | 0 | T1
800108 | 1240 EGLINTON AVE W-UNIT B4 | MISSISSAUGA | Ontario | L5V 1N3 | Canada | c00364br1 |  | 5M | 0 | 10.137.5.0/25 | 10.151.38.1/25 | 0 | 3M
800109 | 303 MOODIE DR | NEPEAN | Ontario | K2H9R4 | Canada | e00372br1 |  | T1 | 0 | 10.137.207.0/25 | 10.203.48.1/25 | 0 | T1
800110 | 11141 Ellerslie Rd. S.W. | Edmonton | Alberta | T6W0E9 | Canada | w00373br1 |  | T1 | 0 | 10.136.188.0/25 | 10.75.47.1/25 | 0 | T1
800111 | 12 MAIN ST | BEETON | Ontario | L0G1A0 | Canada | c00382br1 | 1 | DSL | 0 | 10.138.0.0/25 | 10.131.23.129/25 | 0 | T1
800112 | 600 Queen's Plate Drive | Etobicoke | Ontario | M9W 0A4 | Canada | c00384br1 |  | T1 | 0 | 10.136.225.128/25 | 10.147.51.1/25 | 0 | T1
800113 | 246 NORTH FRONT ST | BELLEVILLE | Ontario | K8P 3C2 | Canada | c00392br1 |  | 5M | 0 | 10.137.77.0/25 | 10.123.46.1/25 | 0 | T1
800114 | 3715 47 Ave. | SYLVAN LAKE | Alberta | T4S0C8 | Canada | w00394br1 |  | T1 | 0 | 10.136.188.128/25 | 10.75.56.1/25 | 0 | T1
800115 | 4382 East Hastings St | Burnaby | British Columbia | V5C 2J9 | Canada | w00400br5 | 1 | Other | 0 | 10.136.54.0/25 | 10.31.51.1/25 | 0 | T1
800116 | 241 FRONT ST | BELLEVILLE | Ontario | K8N 5B3 | Canada | c00402br1 | 1 | T1 | 0 | 10.136.122.128/25 | 10.131.43.1/25 | 0 | T1
800117 | 365 High Tech Rd | RICHMOND HILL | Ontario | L4B 4V9 | Canada | c00409cr1 |  | 5M | 0 | 10.137.46.0/25 | 10.155.45.1/25 | 0 | T1
800118 | 1015 LAKE SHORE BLVD E-UNIT 2B | TORONTO | Ontario | M4M 1B4 | Canada | c00414cr1 |  | 5M | 0 | 10.138.19.0/25 | 10.157.67.1/25 | 0 | T1
800119 | 1 WOODWARD AVE | BLIND RIVER | Ontario | P0R1B0 | Canada | c00422br1 | 1 | DSL | 0 | 10.138.0.128/25 | 10.127.17.1/26 | 0 | T1
800120 | 10720 80 AVE | GRANDE PRAIRIE | Alberta | T8W 0G9 | Canada | w00424br1 |  | 5M | 0 | 10.137.121.0/25 | 10.75.57.1/25 | 0 | T1
800121 | 385 RUE ELLICE | BEAUHARNOIS | Quebec | J6N1X5 | Canada | e00431br1 | 1 | DSL | 0 | 10.137.247.0/25 | 10.219.4.129/25 | 0 | T1
800122 | 195 King Street East | BOWMANVILLE | Ontario | L1C 1P2 | Canada | c00432br1 |  | 3M | 10.33.4.129/26 |  | 10.11.42.129/25 | 0 | T1
800123 | 301 Wye Road - Unit 31 | SHERWOOD PARK | Alberta | T8B0A4 | Canada | w00434br1 | 1 | T1 | 0 | 10.137.1.0/25 | 10.11.59.1/25 | 0 | T1
800124 | 6570 EAST HASTINGS ST | Burnaby | British Columbia | V5B1S2 | Canada | w00440br1 | 1 | T1 | 0 | 10.136.189.0/25 | 10.55.42.1/25 | 0 | T1
800125 | 37 MANITOBA ST | BRACEBRIDGE | Ontario | P1L1T6 | Canada | c00442br1 | 1 | DSL | 0 | 10.138.87.0/25 | 10.147.8.1/26 | 0 | T1
800126 | 1520 MAJOR MACKENZIE DR-SUITE | VAUGHAN | Ontario | L6A 0A9 | Canada | c00458cr1 |  | 5M | 0 | 10.137.158.128/25 | 10.135.38.129/25 | 0 | T1
800127 | 6801 51st | COLD LAKE | Alberta | T9M1Z9 | Canada | w00459br1 |  | T1 | 0 | 10.136.189.128/25 | 10.75.55.1/25 | 0 | T1
800128 | 26 HOLLAND St East | BRADFORD | Ontario | L3Z 2A9 | Canada | c00462br1 |  | 3M | 0 | 10.138.23.128/25 | 10.127.37.1/25 | 0 | T1
800129 | 50 BRAMALEA RD | BRAMPTON | Ontario | L6T 2W8 | Canada | c00472br1 |  | 5M | 0 | 10.137.77.128/25 | 10.135.44.1/25 | 0 | 3M
800130 | 55A BRYNE DR | BARRIE | Ontario | L4N 8V8 | Canada | c00476cr1 |  | 5M | 0 | 10.138.7.0/25 | 10.157.21.129/25 | 0 | T1
800131 | 5051 HWY 7-UNIT 101 | MARKHAM | Ontario | L3R 1N3 | Canada | c00477cr1 |  | 5M | 0 | 10.137.159.0/25 | 10.157.34.1/25 | 0 | T1
800132 | 7299 KINGSWAY | Burnaby | British Columbia | V5E1G7 | Canada | w00480br1 | 1 | T1 | 0 | 10.137.218.128/25 | 10.55.0.1/26 | 0 | T1
800133 | 1 MAIN ST N | BRAMPTON | Ontario | L6X1M8 | Canada | c00482br1 | 1 | T1 | 0 | 10.137.97.0/25 | 10.123.36.1/25 | 0 | 3M
800134 | 1780 WATER ST | MIRAMICHI | New Brunswick | E1N1B6 | Canada | e00484br1 | 1 | DSL | 0 | 10.138.54.128/25 | 10.183.4.1/26 | 0 | T1
800142 | 5010 Kingsway | Burnaby | British Columbia | V5H 2E4 | Canada | w00490br5 | 1 | Other | 0 | 10.136.54.128/25 | 10.55.35.1/25 | 0 | T1
800143 | 235 QUEEN ST E | BRAMPTON | Ontario | L6W2B5 | Canada | c00492br1 | 1 | T1 | 0 | 10.137.100.128/25 | 10.155.8.1/26 | 0 | T1
800144 | 1330 Baseline Rd | OTTAWA | Ontario | K2C 0A9 | Canada | e00496br1 |  | 5M | 0 | 10.137.109.0/25 | 10.191.61.1/25 | 0 | 3M
800146 | 600 SIR WILFRID LAURIER BLVD | BELOEIL | Quebec | J3G 4J2 | Canada | e00501br1 |  | 5M | 0 | 10.137.18.128/25 | 10.199.46.1/25 | 0 | 3M
800147 | 160 Main St S | Brampton | Ontario | L6W 2E1 | Canada | c00502br5 | 1 | Other | 0 | 10.136.38.0/25 | 10.147.4.129/26 | 0 | 3M
800149 | 2166 Rymal Rd. E. | Hannon | Ontario | L0R1P0 | Canada | c00509br1 |  | T1 | 0 | 10.136.123.0/25 | 10.135.11.1/26 | 0 | T1
800150 | 7 SUNNY MEADOW BLVD | BRAMPTON | Ontario | L6R 1W7 | Canada | c00512br1 |  | 5M | 0 | 10.137.5.128/25 | 10.135.43.1/25 | 0 | 3M
800151 | 40 Aberdeen Ave. | St John's | Newfoundland | A1A5T3 | Canada | e00514br1 |  | T1 | 0 | 10.136.157.0/25 | 10.195.49.1/25 | 0 | T1
800152 | 975 PAISLEY RD-UNIT 975A | GUELPH | Ontario | N1K 1X6 | Canada | c00519cr1 |  | 5M | 0 | 10.138.19.128/25 | 10.127.53.1/25 | 0 | T1
800153 | 650 Mt. Pleasant Road | Toronto | Ontario | M4S2N5 | Canada | c00520br1 |  | T1 | 0 | 10.136.123.128/25 | 10.135.60.1/25 | 0 | T1
800154 | 22 COLBORNE ST | BRANTFORD | Ontario | N3T 2G2 | Canada | c00522cr1 |  | 5M | 0 | 10.138.20.0/25 | 10.143.35.1/25 | 0 | 3M
800155 | 1224 Dundas St. W | Mississauga | Ontario | L5C4G7 | Canada | c00523br1 |  | T1 | 0 | 10.136.124.0/25 | 10.157.69.1/25 | 0 | T1
800156 | 743 Main St | Birtle | Manitoba | R0M 0C0 | Canada | w00527br5 |  | Other | 0 | 10.136.55.0/25 | 10.63.5.129/26 | 0 | T1
800157 | 790 rue Notre-Dame | BERTHIERVILLE | Quebec | J0K 1A0 | Canada | e00531br1 |  | 5M | 10.32.133.129/25 |  | 10.22.12.1/24 | 0 | T1
800158 | 361 Cornwall Rd. --unit 107 | OAKVILLE | Ontario | L6J7Z5 | Canada | c00533cr1 | 1 | T1 | 0 | 10.136.217.0/25 | 10.157.32.1/25 | 0 | T1
800159 | 7250 BOUL TASCHEREAU | Brossard | Quebec | J4W1M9 | Canada | e00541cr1 |  | 5M | 0 | 10.138.21.0/25 | 10.203.49.1/24 | 0 | 3M
800160 | 1610 Kenaston Blvd. | WINNIPEG | Manitoba | R3P0Y4 | Canada | w00543br1 | 1 | T1 | 0 | 10.137.219.0/25 | 10.75.50.1/25 | 0 | T1
800161 | 2035 33rd Ave Sw | Calgary | Alberta | T2T 1Z5 | Canada | w00549br5 | 1 | Other | 0 | 10.136.55.128/25 | 10.11.58.1/25 | 0 | T1
800162 | 496 CHEBUCTO ST | BADDECK | Nova Scotia | B0E1B0 | Canada | e00553br1 |  | T1 | 0 | 10.136.157.128/25 | 10.183.12.129/26 | 0 | T1
800163 | 388 WILLIAM ST | DALHOUSIE | New Brunswick | E8C2X2 | Canada | e00554br1 |  | T1 | 0 | 10.136.158.0/25 | 10.183.2.1/26 | 0 | T1
800164 | 3118 Clarence Ave. S. | SASKATOON | Saskatchewan | S7T0C9 | Canada | w00557br1 | 1 | T1 | 0 | 10.136.190.0/25 | 10.75.58.1/25 | 0 | T1
800165 | 106 Main St | Balcarres | Saskatchewan | S0G 0C0 | Canada | w00558br5 |  | Other | 0 | 10.136.56.0/25 | 10.35.4.1/26 | 0 | T1
800166 | 354 YELLOWHEAD HWY 16-PO BOX 2 | BURNS LAKE | British Columbia | V0J 1E0 | Canada | w00560br1 | 1 | DSL | 0 | 10.136.234.0/25 | 10.23.0.1/26 | 0 | T1
800167 | 5717 SIGNAL HILL CENTRE SW | CALGARY | Alberta | T3H 3P8 | Canada | w00563cr1 |  | 5M | 0 | 10.138.22.0/25 | 10.43.56.1/25 | 0 | T1
800168 | 1287 West Pender St. | VANCOUVER | British Columbia | V6E2V1 | Canada | w00567br1 |  | T1 | 0 | 10.136.190.128/25 | 10.75.10.129/25 | 0 | T1
800169 | 108 E Esplanade (101-88 Lonsdale?) | NORTH VANCOUVER | British Columbia | V7L0A7 | Canada | w00573br1 | 1 | T1 | 0 | 10.136.191.0/25 | 10.75.60.1/25 | 0 | T1
800170 | 200 ELGIN ST-MAIN FLR | OTTAWA | Ontario | K2P 1L5 | Canada | e00576br1 |  | 5M | 0 | 10.137.19.0/25 | 10.179.7.1/26 | 0 | T1
800171 | 370 Queen St. E. | ACTON | Ontario | L7J2N3 | Canada | c00581br1 |  | T1 | 0 | 10.136.124.128/25 | 10.157.28.1/25 | 0 | T1
800172 | 80 KING ST W | BROCKVILLE | Ontario | K6V3P9 | Canada | e00582br1 |  | 5M | 0 | 10.137.207.128/25 | 10.191.47.1/25 | 0 | T1
800174 | 6111 SOUTHRIDGE AVE | PRINCE GEORGE | British Columbia | V2N6Z4 | Canada | w00587br1 | 1 | T1 | 0 | 10.136.191.128/25 | 10.75.59.1/25 | 0 | T1
800175 | 100 JAMIESON PKWY | CAMBRIDGE | Ontario | N3C4B3 | Canada | c00592br1 |  | T1 | 0 | 10.136.125.0/25 | 10.157.3.1/25 | 0 | T1
800176 | 8940 HIGHWAY 50-UNIT 1 | BRAMPTON | Ontario | L6P 3A3 | Canada | c00593cr1 |  | 5M | 0 | 10.137.46.128/25 | 10.135.69.129/25 | 0 | T1
800177 | 16 First Commerce Drive - Unit 16a | Aurora | Ontario | L4G0H5 | Canada | c00597cr1 | 1 | T1 | 0 | 10.137.237.128/25 | 10.143.52.1/25 | 0 | T1
800178 | 22314 FRASER HWY | LANGLEY | British Columbia | V3A 8M6 | Canada | w00608br1 | 1 | T1 | 0 | 10.136.30.128/25 | 10.75.49.1/25 | 0 | T1
800179 | 801 York Mills Road | Toronto | Ontario | M3B1X2 | Canada | c00610br1 | 1 | T1 | 0 | 10.136.125.128/25 | 10.157.30.1/25 | 0 | T1
800180 | 6 Fort York Blvd | TORONTO | Ontario | M5V 3Z2 | Canada | c00616br1 |  | 5M | 0 | 10.136.38.128/25 | 10.157.72.1/24 | 0 | T1
800181 | 654 River Road | Wasaga Beach | Ontario | L9Z2P1 | Canada | c00617br1 | 1 | T1 | 0 | 10.136.126.0/25 | 10.157.31.1/25 | 0 | T1
800182 | 303 Main St | Biggar | Saskatchewan | S0K 0M0 | Canada | w00618br5 |  | Other | 0 | 10.136.34.128/25 | 10.19.14.129/26 | 0 | T1
800183 | 66 TAYLOR ST | BRUCE MINES | Ontario | P0R1C0 | Canada | c00622br1 | 1 | DSL | 0 | 10.138.1.0/25 | 10.127.15.1/26 | 0 | T1
800184 | Deer Valley Centre, 1221 Canyon Meadows Dr SE | CALGARY | Alberta | T2J 6G2 | Canada | w00629br1 |  | 5M | 0 | 10.137.121.128/25 | 10.23.23.1/25 | 0 | 3M
800185 | 1047 TRANS CANADA HWY S | CACHE CREEK | British Columbia | V0K1H0 | Canada | w00640br1 |  | T1 | 0 | 10.136.192.0/25 | 10.23.2.1/26 | 0 | T1
800186 | 201 BOUL DE L`INDUSTRIE | CANDIAC | Quebec | J5R6A6 | Canada | e00641br1 |  | 5M | 0 | 10.137.19.128/25 | 10.191.56.1/25 | 0 | T1
800188 | 189 ONTARIO ST | BURKS FALLS | Ontario | P0A1C0 | Canada | c00642br1 | 1 | DSL | 0 | 10.138.1.128/25 | 10.131.11.1/26 | 0 | T1
800189 | 1260 LEBOURGNEUF BLVD | QUEBEC | Quebec | G2K 2G2 | Canada | e00651cr1 |  | 5M | 10.32.5.193/26 |  | 10.187.38.1/25 | 0 | T1
800190 | 388 SOUTH RAILWAY ST-PO BOX 52 | BOISSEVAIN | Manitoba | R0K 0E0 | Canada | w00657br1 |  | 5M | 0 | 10.138.123.128/25 | 10.63.2.129/26 | 0 | T1
800191 | 360 Pearl St. | BURLINGTON | Ontario | L7R1E1 | Canada | c00662br1 |  | T1 | 0 | 10.136.126.128/25 | 10.143.11.129/25 | 0 | T1
800193 | 3525 ROUTE 3 | BARRINGTON PASSAGE | Nova Scotia | B0W1G0 | Canada | e00663br1 | 1 | DSL | 0 | 10.138.55.0/25 | 10.183.17.129/26 | 0 | T1
800194 | 585 MONTREAL RD-UNIT 15 | OTTAWA | Ontario | K1K 4K4 | Canada | e00666br1 |  | 5M | 0 | 10.137.109.128/25 | 10.187.54.1/25 | 0 | 3M
800195 | 9115 AIRPORT RD | BRAMPTON | Ontario | L6S 0B8 | Canada | c00667br1 |  | 5M | 0 | 10.138.7.128/25 | 10.157.25.1/25 | 0 | T1
800196 | 600 Crowfoot Crescent NW - Unit 1 | CALGARY | Alberta | T3G0B4 | Canada | w00683br1 |  | T1 | 0 | 10.136.239.0/25 | 10.75.52.1/25 | 0 | T1
800199 | 211 Du Plateau Blvd. | GATINEAU | Quebec | J9A0N4 | Canada | e00684br1 |  | T1 | 0 | 10.136.158.128/25 | 10.179.45.1/25 | 0 | T1
800200 | 185 Boulevard Omer-marcil | St Jean Sur Richileau | Quebec | J2W0A3 | Canada | e00697br1 |  | T1 | 0 | 10.136.104.128/25 | 10.215.49.1/25 | 0 | T1
800201 | 15 PLAINS RD E | BURLINGTON | Ontario | L7T2B8 | Canada | c00702br1 |  | T1 | 0 | 10.136.127.0/25 | 10.127.2.1/25 | 0 | T1
800202 | 1540 GREBER BLVD-SUITE 1 | GATINEAU | Quebec | J8R0E1 | Canada | e00706br1 | 1 | T1 | 0 | 10.136.105.0/25 | 10.215.48.1/25 | 0 | T1
800203 | 3030 MAINWAY | BURLINGTON | Ontario | L7M 1A3 | Canada | c00712br1 |  | 5M | 10.127.2.129/26 |  | 10.127.38.1/25 | 0 | T1
800204 | 7133-7031 120TH ST | DELTA | British Columbia | V4E2A9 | Canada | w00716br1 |  | T1 | #N/A | 10.138.129.0/25 | #N/A | #N/A | T1
800205 | 1290 SHOPPERS ROW | CAMPBELL RIVER | British Columbia | V9W 2C8 | Canada | w00720br1 |  | 5M | 0 | 10.138.116.128/25 | 10.79.36.1/25 | 0 | T1
800206 | 300 RUE BARKOFF | TROIS-RIVIERES | Quebec | G8T2A3 | Canada | e00721br1 |  | 5M | 0 | 10.136.159.0/25 | 10.179.5.129/26 | 0 | T1
800207 | 5322 DUNDAS ST W-UNIT 3 | ETOBICOKE | Ontario | M9B 1B3 | Canada | c00724cr1 |  | 5M | 0 | 10.137.47.0/25 | 10.157.23.1/25 | 0 | T1
800208 | 360 MARCH RD | KANATA | Ontario | K2K 2T5 | Canada | e00726br1 |  | 5M | 10.32.132.129/25 |  | 10.179.1.129/26 | 0 | T1
800209 | 400 SANDWICH ST S | AMHERSTBURG | Ontario | N9V3L4 | Canada | c00732br1 | 1 | DSL | 0 | 10.138.2.0/25 | 10.139.9.129/26 | 0 | T1
800210 | 15 PLACE CHAMBLY (known as 1233 Périgny) | CHAMBLY | Quebec | J3L 2Y7 | Canada | e00741br1 |  | 5M | 10.32.143.129/25 |  | 10.22.32.1/24 | 0 | T1
800211 | 3535 NEW ST | BURLINGTON | Ontario | L7L1S8 | Canada | c00742br1 |  | 5M | 0 | 10.137.78.0/25 | 10.143.42.1/25 | 0 | 3M
800212 | 2880 Major Mackenzie East | Markham | Ontario | L6C0G6 | Canada | c00744cr1 |  | 5M | 0 | 10.138.89.128/25 | 10.155.47.1/25 | 0 | T1
800213 | 2840 BAINBRIDGE AVE | Burnaby | British Columbia | V5A3W7 | Canada | w00750br1 | 1 | T1 | 0 | 10.137.219.128/25 | 10.11.0.1/26 | 0 | T1
800214 | 2201 BRANT ST-UNIT 23 | BURLINGTON | Ontario | L7P 3N8 | Canada | c00752br1 |  | T1 | 0 | 10.136.234.128/25 | 10.143.8.129/25 | 0 | T1
800215 | 3601 MAJOR MACKENZIE DR-UNIT 1 | WOODBRIDGE | Ontario | L4H 0A2 | Canada | c00754cr1 |  | 5M | 0 | 10.138.20.128/25 | 10.157.24.1/25 | 0 | T1
800216 | 36 Rene-Levesque Blvd | Chandler | Quebec | G0C 1K0 | Canada | e00761br5 |  | Other | 0 | 10.136.45.0/25 | 10.183.7.129/26 | 0 | T1
800217 | x House 1068-Communications Bldg | CROSS LAKE | Manitoba | R0B 0J0 | Canada | w00767br1 |  | 5M | 0 | 10.138.118.0/25 | 10.55.2.129/26 | 0 | T1
800218 | 48 ST FRANCIS ST | EDMUNDSTON | New Brunswick | E3V1E3 | Canada | e00774br1 | 1 | T1 | 0 | 10.136.159.128/25 | 10.203.1.1/26 | 0 | T1
800220 | Les Galeries Charlesbourg, 4250 1re av | QUÉBEC | Quebec | G1H 2S5 | Canada | e00775br1 |  | 5M | 0 | 10.138.12.0/25 | 10.203.44.1/25 | 0 | T1
800221 | 2269 RIVERSIDE DR | OTTAWA | Ontario | K1H 8K2 | Canada | e00776br1 |  | 5M | 0 | 10.137.110.0/25 | 10.195.42.1/25 | 0 | T1
800222 | 120 Centre St | Cabri | Saskatchewan | S0N 0J0 | Canada | w00778br5 |  | Other | 0 | 10.136.56.128/25 | 10.35.11.129/26 | 0 | T1
800223 | 200 D`ANJOU BLVD-SUITE 455 | CHATEAUGUAY | Quebec | J6K 1C5 | Canada | e00781br1 |  | 5M | 0 | 10.137.20.0/25 | 10.203.50.1/25 | 0 | 3M
800224 | 996 Homer St. | VANCOUVER | British Columbia | V6B2W7 | Canada | w00782br1 | 1 | T1 | 0 | 10.136.211.128/25 | 10.63.49.1/25 | 0 | T1
800225 | 9428 Highway 48 | Markham | Ontario | L6E 0N1 | Canada | c00783br1 |  | 3M | 10.33.0.193/26 |  | 10.147.53.1/25 | 0 | T1
800226 | 740 ROSSER AVE | BRANDON | Manitoba | R7A 0K9 | Canada | w00787cr1 |  | 5M | 0 | 10.137.164.128/25 | 10.79.41.1/25 | 0 | T1
800227 | 25 PEEL CENTRE DR-UNIT 115C | BRAMPTON | Ontario | L6T 3R5 | Canada | c00792br1 |  | 5M | 0 | 10.137.6.0/25 | 10.143.55.1/25 | 0 | 3M
800228 | 661 18 ST | BRANDON | Manitoba | R7A 5B3 | Canada | w00797br1 |  | 5M | 10.34.2.129/26 |  | 10.11.117.129/25 | 0 | T1
800229 | 15 DOXSEE AVE N | CAMPBELLFORD | Ontario | K0L1L0 | Canada | c00802br1 | 1 | DSL | 0 | 10.138.2.128/25 | 10.131.17.1/26 | 0 | T1
800230 | 1050 boul de la Rive-Sud, SS 90 | SAINT-ROMUALD | Quebec | G6W 5M6 | Canada | e00803br1 |  | 5M | 0 | 10.138.12.128/25 | 10.203.53.1/25 | 0 | T1
800231 | 77 MAIN ST | BRIGHTON | Ontario | K0K1H0 | Canada | c00812br1 | 1 | DSL | 0 | 10.138.3.0/25 | 10.139.13.1/26 | 0 | T1
800232 | 5 Clair Road East | Guelph | Ontario | N1L 0J7 | Canada | c00819br1 |  | 3M | 10.33.0.65/26 |  | 10.143.57.1/25 | 0 | T1
800233 | 435 BROOKSIDE DR | FREDERICTON | New Brunswick | E3A8V4 | Canada | e00824br1 | 1 | DSL | 0 | 10.138.55.128/25 | 10.187.2.129/26 | 0 | T1
800234 | 45460 Luckakuck Way | CHILLIWACK | British Columbia | V2R3S9 | Canada | w00834br1 | 1 | T1 | 0 | 10.136.192.128/25 | 10.11.56.1/25 | 0 | T1
800235 | 383 ASPEN GLEN LANDING SW-UNIT 107 | CALGARY | Alberta | T3H 0N6 | Canada | w00836cr1 |  | 5M | 0 | 10.137.165.0/25 | 10.11.60.1/25 | 0 | T1
800236 | 3195 Cliffe Ave. | Courtenay | British Columbia | V9N2L9 | Canada | w00838br1 | 1 | T1 | 0 | 10.136.193.0/25 | 10.75.61.1/25 | 0 | T1
800238 | 93 BRIDGE ST | CARLETON PLACE | Ontario | K7C 2V4 | Canada | e00842br1 | 1 | DSL | 0 | 10.138.56.0/25 | 10.191.43.1/25 | 0 | T1
800239 | 1265 FANSHAWE PARK RD W / 1267 Fanshawe | LONDON | Ontario | N6G 0G4 | Canada | c00844cr1 |  | 5M | 0 | 10.137.47.128/25 | 10.139.44.1/25 | 0 | T1
800240 | 40 Saddletowne Circle NE | CALGARY | Alberta | T3J0H5 | Canada | w00846br1 | 1 | T1 | 0 | 10.137.1.128/25 | 10.43.55.1/25 | 0 | T1
800242 | 489 BROADWAY | ORANGEVILLE | Ontario | L9W 0A4 | Canada | c00847br1 |  | 5M | 0 | 10.137.4.0/25 | 10.157.22.1/25 | 0 | T1
800243 | 2399 PARKDALE BLVD | BROCKVILLE | Ontario | K6V3G9 | Canada | e00852br1 |  | 5M | 0 | 10.137.110.128/25 | 10.191.46.1/25 | 0 | T1
800244 | 101 Middlecote Drive | AJAX | Ontario | L1T0K3 | Canada | c00856br1 |  | T1 | 0 | 10.136.114.128/25 | 10.135.67.1/25 | 0 | T1
800245 | 33 BIRCH ST | CHAPLEAU | Ontario | P0M1K0 | Canada | c00862br1 |  | T1 | 0 | 10.136.115.0/25 | 10.127.5.1/26 | 0 | T1
800246 | 18676 Fraser HWY | Surrey | British Columbia | V3S 7Y4 | Canada | w00863br1 | 1 | T1 | 0 | 10.136.235.0/25 | 10.43.57.1/25 | 0 | T1
800247 | 2275 LAKESHORE BLVD W | ETOBICOKE | Ontario | M8V 3Y3 | Canada | c00864br1 |  | 3M | 0 | 10.138.23.0/25 | 10.155.15.129/26 | 0 | T1
800248 | 879 Marine Drive | NORTH VANCOUVER | British Columbia | V7P1R7 | Canada | w00873br1 | 1 | T1 | 0 | 10.136.108.0/25 | 10.75.65.1/24 | 0 | T1
800249 | 746 SHUSWAP AVE | CHASE | British Columbia | V0E1M0 | Canada | w00880br1 | 1 | DSL | 0 | 10.136.10.128/25 | 10.35.5.129/26 | 0 | T1
800250 | 190 KING ST W (KING W & FOURTH | CHATHAM | Ontario | N7M 1E6 | Canada | c00882br1 |  | 3M | 0 | 10.137.74.0/25 | 10.123.51.1/25 | 0 | T1
800251 | 1597 BEDFORD HWY | BEDFORD | Nova Scotia | B4A 1E7 | Canada | e00883br1 |  | 5M | 0 | 10.137.20.128/25 | 10.199.38.1/25 | 0 | 3M
800252 | 504 QUEEN ST | FREDERICTON | New Brunswick | E3B 5G1 | Canada | e00884br1 |  | 5M | 0 | 10.137.21.0/25 | 10.207.36.1/25 | 0 | T1
800253 | 307 Toronto Street south Unit 10 | UXBRIDGE | Ontario | L9P0B4 | Canada | c00885br1 |  | T1 | 0 | 10.136.115.128/25 | 10.135.61.1/25 | 0 | T1
800254 | 1930 ST LAURENT BLVD | OTTAWA | Ontario | K1G 1A4 | Canada | e00886br1 |  | 5M | 0 | 10.137.111.0/25 | 10.187.51.1/25 | 0 | 3M
800255 | 9300 Bathurst Street | Vaughan | Ontario | L6A4N9 | Canada | c00888br1 | 1 | T1 | 0 | 10.137.36.128/25 | 10.135.41.129/25 | 0 | T1
800256 | 3068 Mayfield Rd. | BRAMPTON | Ontario | L6Z0E3 | Canada | c00890br1 |  | T1 | 0 | 10.136.116.0/25 | 10.135.64.1/25 | 0 | T1
800257 | 8 QUEEN ST N | BOLTON | Ontario | L7E 1C8 | Canada | c00892cr1 |  | 3M | 0 | 10.137.74.128/25 | 10.147.40.1/25 | 0 | T1
800258 | 5905 Berton Ave | VANCOUVER | British Columbia | V6S 0B3 | Canada | w00894br1 | 1 | T1 | 0 | 10.137.241.0/25 | 10.63.50.1/25 | 0 | 3M
800259 | 25 MAIN ST S | CARMAN | Manitoba | R0G0J0 | Canada | w00897br1 |  | T1 | 0 | 10.136.193.128/25 | 10.55.4.1/26 | 0 | T1
800261 | 141 BOUL DE MORTAGNE | BOUCHERVILLE | Quebec | J4B6G4 | Canada | e00901br1 | 1 | DSL | 0 | 10.138.56.128/25 | 10.219.1.1/25 | 0 | T1
800262 | 171 KEIL DR S | CHATHAM | Ontario | N7M3H3 | Canada | c00902br1 |  | T1 | 0 | 10.137.38.0/25 | 10.127.10.129/26 | 0 | T1
800263 | 2212 BANK ST | OTTAWA | Ontario | K1V 1J6 | Canada | e00909cr1 | 1 | 5M | 0 | 10.137.162.128/25 | 10.195.53.1/24 | 0 | T1
800264 | 3420 ERRINGTON ST | CHELMSFORD | Ontario | P0M1L0 | Canada | c00912br1 | 1 | DSL | 0 | 10.137.250.128/25 | 10.131.8.1/26 | 0 | T1
800265 | 539 Holland Street West | Bradford | Ontario | L3Z0C1 | Canada | c00913br1 |  | T1 | 0 | 10.136.111.0/25 | 10.127.21.1/25 | 0 | T1
800266 | 106 RACINE ST E | CHICOUTIMI | Quebec | G7H 1R1 | Canada | e00921br1 |  | 5M | 0 | 10.137.21.128/25 | 10.203.73.1/24 | 0 | 3M
800267 | 8170 CUMMINGTON SQUARE W | NIAGARA FALLS | Ontario | L2G6V9 | Canada | c00922br1 |  | T1 | 0 | 10.136.116.128/25 | 10.155.2.1/26 | 0 | T1
800268 | 2460 WINSTON CHURCHILL BLVD | OAKVILLE | Ontario | L6H 6J5 | Canada | c00932br1 |  | 5M | 0 | 10.137.75.0/25 | 10.143.40.1/25 | 0 | 3M
800269 | 1206 Prospect St | Fredericton | New Brunswick | E3B 3C1 | Canada | e00934cr5 |  | Other | 0 | 10.136.45.128/25 | 10.219.51.1/25 | 0 | T1
800270 | 780 CURE LABELLE | BLAINVILLE | Quebec | J7C 2K5 | Canada | e00941br1 |  | 5M | 0 | 10.137.22.0/25 | 10.203.3.1/26 | 0 | T1
800271 | 1730 LAKESHORE RD W | MISSISSAUGA | Ontario | L5J 1J5 | Canada | c00942br1 |  | 5M | 10.33.6.129/26 |  | 10.123.42.1/25 | 0 | T1
800275 | 9296 MAIN ST | CHILLIWACK | British Columbia | V2P 4M5 | Canada | w00960cr1 |  | 5M | 0 | 10.137.165.128/25 | 10.23.66.1/25 | 0 | T1
800276 | 12 Elora St MAIN COMPUTER ROOM | Clifford | Ontario | N0G 1M0 | Canada | c00962br1 |  | T1 | 0 | 10.138.97.128/25 | 10.127.17.129/26 | 0 | T1
800278 | 68 VICTORIA ST | CLINTON | Ontario | N0M1L0 | Canada | c00982br1 |  | T1 | 0 | 10.137.251.0/25 | 10.147.10.129/26 | 0 | T1
800279 | 965 BOUL CURE LABELLE | LAVAL | Quebec | H7V2V7 | Canada | e00991br1 | 1 | T1 | 0 | 10.137.208.0/25 | 10.207.45.1/25 | 0 | 3M
800280 | 195 COMMERCIAL ST | BERWICK | Nova Scotia | B0P 1E0 | Canada | e00993br1 | 1 | DSL | 0 | 10.138.57.0/25 | 10.191.3.1/26 | 0 | T1
800281 | 131 Main St | Caryle | Saskatchewan | S0C 0R0 | Canada | w00998br5 |  | Other | 0 | 10.136.57.0/25 | 10.35.4.129/26 | 0 | T1
800282 | 66 KING ST W | COBOURG | Ontario | K9A 2L9 | Canada | c01002br1 |  | 5M | 0 | 10.137.251.128/25 | 10.139.12.1/26 | 0 | T1
800283 | 280 HURONTARIO ST | COLLINGWOOD | Ontario | L9Y2M3 | Canada | c01012br1 | 1 | DSL | 0 | 10.137.252.0/25 | 10.131.9.129/25 | 0 | T1
800284 | 125 SUSSEX DR | Ottawa | Ontario | K1A0G2 | Canada | e01016br1 |  | T1 | 0 | 10.136.160.0/25 | 10.179.10.1/26 | 0 | T1
800285 | 6307 MAIN ST | COMBER | Ontario | N0P1J0 | Canada | c01022br1 | 1 | DSL | 0 | 10.138.98.0/25 | 10.131.18.1/26 | 0 | T1
800286 | 31975 SOUTH FRASER WAY | ABBOTSFORD | British Columbia | V2T1V5 | Canada | w01040br1 |  | 5M | 0 | 10.137.122.0/25 | 10.63.78.1/24 | 0 | 3M
800288 | 11 QUEEN ST | COOKSTOWN | Ontario | L0L1L0 | Canada | c01042br1 | 1 | DSL | 0 | 10.137.252.128/25 | 10.139.14.129/25 | 0 | T1
800289 | 213 Broadway St | Crystal City | Manitoba | R0K 0N0 | Canada | w01047br5 |  | Other | 0 | 10.136.57.128/25 | 10.63.3.1/26 | 0 | T1
800290 | 32900 South Fraser Way | Abbotsford | British Columbia | V2S 5A1 | Canada | w01050br5 | 1 | Other | 0 | 10.136.58.0/25 | 10.23.54.1/25 | 0 | 3M
800294 | 77 WELLINGTON ST | COATICOOK | Quebec | J1A2H6 | Canada | e01061br1 |  | T1 | 0 | 10.136.232.128/25 | 10.215.2.1/26 | 0 | T1
800295 | 2 DUNDAS ST W | MISSISSAUGA | Ontario | L5B 1H3 | Canada | c01062br1 |  | 5M | 0 | 10.137.75.128/25 | 10.123.41.1/25 | 0 | 3M
800296 | 300 PITT ST | CORNWALL | Ontario | K6J 3P9 | Canada | e01082br1 | 1 | 5M | 0 | 10.137.111.128/25 | 10.203.47.1/25 | 0 | T1
800297 | 74 YOUNG RD | Clearwater | British Columbia | V0E 1N2 | Canada | w01090br1 | 1 | DSL | 0 | 10.136.5.128/25 | 10.63.10.129/26 | 0 | T1
800298 | 1380 SECOND ST E | CORNWALL | Ontario | K6H2B8 | Canada | e01092br1 |  | T1 | 0 | 10.136.160.128/25 | 10.215.5.129/26 | 0 | T1
800299 | 15795 Croydon Drive | SURREY | British Columbia | V3S2L6 | Canada | w01094br1 | 1 | T1 | 0 | 10.137.241.128/25 | 10.11.61.1/25 | 0 | T1
800300 | 6021 Steeles Ave East | Toronto | Ontario | M1V5P7 | Canada | c01095br1 | 1 | T1 | 0 | 10.137.49.0/25 | 10.135.35.129/25 | 0 | T1
800301 | 4120 Strandherd Drive | NEPEAN | Ontario | K2J0V2 | Canada | e01098br1 |  | T1 | 0 | 10.136.161.0/25 | 10.167.57.1/25 | 0 | T1
800304 | 348 LYNDOCK ST | CORUNNA | Ontario | N0N1G0 | Canada | c01102br1 | 1 | DSL | 0 | 10.137.253.0/25 | 10.139.8.1/26 | 0 | T1
800305 | 3 QUEEN ST | BRIDGETOWN | Nova Scotia | B0S1C0 | Canada | e01103br1 | 1 | DSL | 0 | 10.138.57.128/25 | 10.183.19.129/26 | 0 | T1
800306 | 305 BROADWAY BLVD | GRAND FALLS | New Brunswick | E3Z 2K3 | Canada | e01104br1 |  | 5M | 0 | 10.138.13.0/25 | 10.183.6.1/26 | 0 | T1
800307 | 6204 Currents Drive N.w. | Edmonton | Alberta | T6W0L8 | Canada | w01106cr1 |  | 5M | 0 | 10.136.217.128/25 | 10.75.66.1/25 | 0 | T1
800308 | 475 Bank St. | Ottawa | Ontario | K2P1Z2 | Canada | e01108br1 |  | T1 | 0 | 10.136.161.128/25 | 10.195.52.1/25 | 0 | T1
800309 | 12713 20th Ave | Blairmore | Alberta | T0K 0E0 | Canada | w01109br5 |  | Other | 0 | 10.136.58.128/25 | 10.23.4.1/26 | 0 | T1
800310 | 17931 56TH AVE | SURREY | British Columbia | V3S1E2 | Canada | w01110br1 | 1 | DSL | 0 | 10.138.81.128/25 | 10.11.9.1/26 | 0 | T1
800311 | 1095-1103 Yonge St - Unit 201 | Toronto | Ontario | M4W 2L7 | Canada | c01117br1 |  | 5M | 10.32.140.129/25 |  | 10.22.26.1/24 | 0 | T1
800312 | 5028 50TH AVE SUITE #104 | BONNYVILLE | Alberta | T9N2G8 | Canada | w01119br1 | 1 | DSL | 0 | 10.136.24.128/25 | 10.35.7.1/26 | 0 | T1
800313 | 1905 Sooke Road | VICTORIA | British Columbia | V9B 1V8 | Canada | w01120br1 |  | 5M | 10.34.0.193/26 |  | 10.67.53.1/25 | 0 | T1
800314 | 900 Fairway Crescent--unit 1 | KITCHENER | Ontario | N2A0A1 | Canada | c01123br1 |  | T1 | 0 | 10.136.117.0/25 | 10.135.10.129/25 | 0 | T1
800315 | 300 KING GEORGE RD-UNIT C1 | BRANTFORD | Ontario | N3R 5L8 | Canada | c01124cr1 |  | 5M | 0 | 10.137.48.0/25 | 10.143.54.1/25 | 0 | T1
800316 | 420 DU SUD ST | COWANSVILLE | Quebec | J2K2X7 | Canada | e01131br1 | 1 | DSL | 0 | 10.138.58.0/25 | 10.179.3.129/26 | 0 | T1
800317 | 3075 Sources Blvd. | Dollard Des Ormeaux | Quebec | H9B1Z6 | Canada | e01141br1 | 1 | T1 | 0 | 10.136.162.0/25 | 10.207.4.129/26 | 0 | T1
800318 | 1721 CHIEFS WOOD DRIVE | OHSWEKEN | Ontario | N0A1M0 | Canada | c01144br1 | 1 | DSL | 0 | 10.137.253.128/25 | 10.139.9.1/26 | 0 | T1
800319 | 5 Collier St - 2nd Flr | Barrie | Ontario | L4M 1G4 | Canada | c01146br5 | 1 | Other | 0 | 10.136.39.0/25 | 10.143.47.1/25 | 0 | T1
800322 | 7956 120TH STREET | SURREY | British Columbia | V3W 3N2 | Canada | w01154br1 |  | 5M | 10.11.66.129/25 |  | 10.11.66.1/25 | 0 | T1
800325 | 202 MAIN ST N | DAUPHIN | Manitoba | R7N 1C4 | Canada | w01177br1 |  | 5M | 0 | 10.138.125.0/25 | 10.31.2.129/26 | 0 | T1
800326 | 102 North Railway Ave | Deloraine | Manitoba | R0M 0M0 | Canada | w01187br5 |  | Other | 0 | 10.136.59.0/25 | 10.63.6.1/26 | 0 | T1
800329 | 439 NORTH RD | COQUITLAM | British Columbia | V3K 3V9 | Canada | w01200br1 |  | 5M | 0 |  | 10.23.62.1/25 | 0 | 3M
800330 | 1300 BOUL WALLBERG | DOLBEAU | Quebec | G8L3L8 | Canada | e01201br1 | 1 | DSL | 0 | 10.138.58.128/25 | 10.183.9.129/26 | 0 | T1
800332 | 3610 ST JEAN BLVD | DOLLARD-DES-ORMEAUX | Quebec | H9G 1X1 | Canada | e01211br1 |  | 5M | 10.32.5.129/26 |  | 10.219.44.1/25 | 0 | T1
800333 | 565 King St | BRIDGEWATER | Nova Scotia | B4V 1B3 | Canada | e01213br1 |  | 5M | 0 | 10.137.22.128/25 | 10.199.1.1/26 | 0 | T1
800334 | 1941 ROUTE 3 | HARVEY STATION | New Brunswick | E6K1K3 | Canada | e01214br1 | 1 | DSL | 0 | 10.138.59.0/25 | 10.183.10.1/26 | 0 | T1
800335 | 1145 WELLINGTON ST | Ottawa | Ontario | K1Y2Y9 | Canada | e01216br1 | 1 | T1 | 0 | 10.137.208.128/25 | 10.179.12.129/25 | 0 | T1
800339 | 4 King Street North, Unit #1 | Alliston | Ontario | L9R1L9 | Canada | c01220br1 |  | T1 | 0 | 10.136.117.128/25 | 10.157.40.129/25 | 0 | T1
800341 | 23 MAIN ST | DRAYTON | Ontario | N0G1P0 | Canada | c01222br1 | 1 | DSL | 0 | 10.138.3.128/25 | 10.131.14.1/26 | 0 | T1
800342 | 235 Ira Needles Blvd | Kitchener | Ontario | N2N 0B2 | Canada | c01224br1 |  | T1 | 0 | 10.136.127.128/25 | 10.135.42.129/25 | 0 | T1
800343 | 14785 Yonge Street | Aurora | Ontario | L4G 1N1 | Canada | c01230br1 |  | T1 | 0 | 10.137.240.128/25 | 10.143.56.1/25 | 0 | T1
800356 | 1962 COMO LAKE RD | COQUITLAM | British Columbia | V3J3R3 | Canada | w01240br1 | 1 | DSL | 0 | 10.136.18.0/25 | 10.23.60.1/25 | 0 | T1
800358 | 40 King St | Dryden | Ontario | P8N 2Y7 | Canada | w01242br5 |  | Other | 0 | 10.136.59.128/25 | 10.55.46.1/25 | 0 | T1
800359 | 6911 Derry Rd.--Unit E01 | Milton | Ontario | L9T 7H5 | Canada | c01248br1 | 1 | T1 | 0 | 10.136.128.0/25 | 10.135.57.129/25 | 0 | T1
800360 | 23 PINE ST | DUBREUILVILLE | Ontario | P0S1K0 | Canada | c01252br1 |  | T1 | 0 | 10.136.250.128/25 | 10.131.6.1/26 | 0 | T1
800361 | 405 Bayfield Street | Barrie | Ontario | L4M3C5 | Canada | c01256br1 | 1 | T1 | 0 | 10.137.107.128/25 | 10.157.29.1/25 | 0 | T1
800364 | 2500 UNIVERSITY DR NW | CALGARY | Alberta | T2N1N4 | Canada | w01259br6 | 1 | T1 | 0 | 10.138.98.128/25 | 10.31.6.129/26 | 0 | 3M
800362 | 4820 NORTHLAND DR NW | CALGARY | Alberta | T2L2L3 | Canada | w01259br1 |  | 5M | 0 | 10.136.229.128/25 | 10.43.76.1/24 | 0 | 3M
800365 | 2885 BARNET HWY | COQUITLAM | British Columbia | V3B1C1 | Canada | w01260br1 |  | 5M | 0 | 10.137.122.128/25 | 10.31.52.1/24 | 0 | 3M
800366 | 70 KING ST W | DUNDAS | Ontario | L9H5E7 | Canada | c01262br1 | 1 | DSL | 0 | 10.138.4.0/25 | 10.131.40.1/25 | 0 | T1
800367 | 800 Fairville Blvd | SAINT JOHN | New Brunswick | E2M 5T4 | Canada | e01264br1 |  | 5M | 0 | 10.137.246.0/25 | 10.179.0.129/26 | 0 | T1
800368 | 480 Dundas Street East | Toronto | Ontario | M5A2C4 | Canada | c01265br1 |  | T1 | 0 | 10.136.128.128/25 | 10.135.37.129/25 | 0 | T1
800370 | 316 DORVAL AVENUE | DORVAL | Quebec | H9S 3H7 | Canada | e01271br1 |  | 5M | 0 | 10.137.112.0/25 | 10.219.42.1/25 | 0 | T1
800371 | 2288 WHATCOM RD | ABBOTSFORD | British Columbia | V3G 0C1 | Canada | w01278br1 |  | 5M | 10.63.51.129/25 |  | 10.63.51.1/25 | 0 | T1
800372 | 3711 61ST AVE SE | CALGARY | Alberta | T2C1V5 | Canada | w01279br1 |  | T1 | 0 | 10.138.99.0/25 | 10.63.7.1/25 | 0 | T1
800374 | 1015 RYAN RD | COURTENAY | British Columbia | V9N 3R6 | Canada | w01280br1 |  | 5M | 0 | 10.137.123.0/25 | 10.27.36.1/25 | 0 | 3M
800375 | 163 QUEEN ST | DUNNVILLE | Ontario | N1A 1H6 | Canada | c01282br1 |  | 5M | 0 | 10.137.78.128/25 | 10.147.35.1/25 | 0 | T1
800376 | 6304 50th Street | Beaumount | Alberta | T4X 0B6 | Canada | w01288br1 | 1 | T1 | 0 | 10.136.235.128/25 | 10.11.62.1/25 | 0 | T1
800377 | 27 Rean Dr. | North York | Ontario | M2K0A6 | Canada | c01291br1 |  | T1 | 0 | 10.136.254.0/25 | 10.123.57.1/24 | 0 | T1
800378 | 955 WESTNEY RD S-UNIT 2 | AJAX | Ontario | L1S3K7 | Canada | c01292br1 | 1 | DSL | 0 | 10.138.4.128/25 | 10.155.12.1/26 | 0 | T1
800379 | 1000 RAILWAY AVE | CANMORE | Alberta | T1W 1P4 | Canada | w01297br1 |  | 5M | 0 | 10.137.123.128/25 | 10.75.2.1/25 | 0 | T1
800380 | 108 GARAFRAXA ST S | DURHAM | Ontario | N0G1R0 | Canada | c01302br1 | 1 | DSL | 0 | 10.138.5.0/25 | 10.127.18.1/26 | 0 | T1
800382 | 9495 Mississauga Road, Unit A,& Unit B | Brampton | Ontario | L6X 0Z8 | Canada | c01306cr1 |  | 10M | 10.33.3.65/26 |  | 10.11.37.129/25 | 0 | T1
800383 | 517 London St | Winnipeg | Manitoba | R2K 2Z4 | Canada | w01307br5 |  | Other | 0 | 10.136.60.0/25 | 10.27.0.1/26 | 0 | T1
800384 | 5445 FALSBRIDGE DR NE | CALGARY | Alberta | T3J3C7 | Canada | w01309br1 | 1 | T1 | 0 | 10.137.220.0/25 | 10.67.3.1/26 | 0 | T1
800385 | 95 LYNDEN RD | BRANTFORD | Ontario | N3R 7J9 | Canada | c01312br1 |  | 5M | 0 | 10.136.245.128/25 | 10.151.74.1/24 | 0 | 3M
800386 | 206 CURRIE RD or 206 Main St | DUTTON | Ontario | N0L1J0 | Canada | c01322br1 |  | T1 | 0 | 10.136.129.0/25 | 10.131.19.1/26 | 0 | T1
800387 | 15374 CABOT TRAIL RD HWY #19 | CHETICAMP | Nova Scotia | B0E1H0 | Canada | e01323br1 |  | T1 | 0 | 10.136.162.128/25 | 10.183.11.1/26 | 0 | T1
800388 | 196 Chestermere Station Way | CALGARY | Alberta | T2P 1C9 | Canada | w01325br1 | 1 | T1 | 0 | 10.137.220.128/25 | 10.43.60.1/25 | 0 | T1
800389 | 1309 CARLING AVE | OTTAWA | Ontario | K1Z 7L3 | Canada | e01326br1 |  | 5M | 0 | 10.138.13.128/25 | 10.187.52.1/25 | 0 | 3M
800391 | 9231 WOODBINE AVE | Markham | Ontario | L3R0K1 | Canada | c01334br1 | 1 | T1 | 0 | 10.137.124.128/25 | 10.151.6.129/25 | 0 | T1
800392 | 8835 Macleod Trail SW Unit 515 | CALGARY | Alberta | T2H 0M2 | Canada | w01336br1 | 1 | T1 | 0 | 10.137.221.0/25 | 10.11.64.1/25 | 0 | T1
800394 | 1125 boul Saint-Joseph | DRUMMONDVILLE | Quebec | J2C 2C8 | Canada | e01341br1 |  | 5M | 0 | 10.138.14.0/25 | 10.207.42.1/25 | 0 | T1
800395 | 2 SASKATCHEWAN RD | ELLIOT LAKE | Ontario | P5A2J7 | Canada | c01342br1 | 1 | DSL | 0 | 10.138.5.128/25 | 10.131.9.1/26 | 0 | T1
800398 | 5 MAIN ST N | CALLANDER | Ontario | P0H1H0 | Canada | c01352br1 | 1 | DSL | 0 | 10.138.6.0/25 | 10.131.12.1/26 | 0 | T1
800399 | 963 HENDERSON HWY | WINNIPEG | Manitoba | R2K2M3 | Canada | w01357br1 |  | 5M | 0 | 10.136.194.0/25 | 10.27.39.1/25 | 0 | T1
800400 | 2 CRANBROOK ST | Cranbrook | British Columbia | V1C3P6 | Canada | w01360br1 |  | 5M | 0 | 10.136.16.128/25 | 10.55.41.1/25 | 0 | T1
800402 | 6 CHURCH ST W | ELMIRA | Ontario | N3B 1M3 | Canada | c01362br1 |  | 5M | 0 | 10.137.6.128/25 | 10.139.38.1/25 | 0 | T1
800403 | 209 11TH AVE SE | CALGARY | Alberta | T2G 0X9 | Canada | w01371br1 | 1 | T1 | 0 | 10.136.110.128/25 | 10.43.58.1/25 | 0 | T1
800404 | 1000 Market Street S.E. | Airdrie | Alberta | T4A 0K9 | Canada | w01372br1 | 1 | T1 | 0 | 10.136.25.128/25 | 10.43.61.1/25 | 0 | T1
800405 | 644 MAIN ST | MONCTON | New Brunswick | E1C 1E2 | Canada | e01374br1 |  | 5M | 0 | 10.137.112.128/25 | 10.219.39.129/25 | 0 | T1
800406 | 1800 Sheppard Avenue Unit 2105 | North York | Ontario | M2J5A7 | Canada | c01380br1 |  | 5M | 0 | 10.137.137.0/25 | 10.157.22.129/25 | 0 | T1
800415 | 4640 Gordon Road | Regina | Saskatchewan | S4W 0B7 | Canada | w01388br1 | 1 | T1 | 0 | 10.136.194.128/25 | 10.43.62.1/25 | 0 | T1
800416 | 112 COMMISSIONER ST | EMBRO | Ontario | N0J1J0 | Canada | c01402br1 |  | T1 | 0 | 10.136.129.128/25 | 10.131.20.1/26 | 0 | T1
800420 | 3100 CONCORDE BLVD | DUVERNAY | Quebec | H7E 2B8 | Canada | e01411br1 |  | 5M | 0 | 10.137.113.0/25 | 10.191.57.1/25 | 0 | 3M
800422 | 414 SPADINA RD | Toronto | Ontario | M5P2W2 | Canada | c01412br1 |  | T1 | 0 | 10.137.145.0/25 | 10.135.3.1/26 | 0 | T1
800424 | 6014 VEDDER RD-UNIT 23 | CHILLIWACK | British Columbia | V2R5M4 | Canada | w01420br1 | 1 | DSL | 0 | 10.138.82.0/25 | 10.23.3.129/26 | 0 | T1
800427 | 936 NOTRE DAME ST | EMBRUN | Ontario | K0A1W0 | Canada | e01422br1 |  | 5M | 0 | 10.138.59.128/25 | 10.191.12.129/26 | 0 | T1
800432 | BLDG D, 111 BETTS AVENUE | SASKATOON | Saskatchewan | S7M 1L2 | Canada | w01429br1 | 1 | T1 | 0 | 10.137.243.0/25 | 10.27.53.1/25 | 0 | T1
800433 | 206 Slimmon Road | Saskatoon | Saskatchewan | S7V 0C6 | Canada | w01430br1 |  | 5M | 10.27.54.129/25 |  | 10.27.54.1/25 | 0 | T1
800439 | 1729 HIGHWAY 1 | CHURCH POINT | Nova Scotia | B0W 1M0 | Canada | e01433br1 |  | T1 | 0 | 10.136.163.0/25 | 10.183.12.1/26 | 0 | T1
800440 | 719 MOUNTAIN RD | MONCTON | New Brunswick | E1C2P4 | Canada | e01434br1 |  | 5M | 0 | 10.137.23.0/25 | 10.203.70.1/24 | 0 | 3M
800441 | 151 Walden Gate SE - Unit 600 | CALGARY | Alberta | T2X 0R2 | Canada | w01436br1 |  | 5M | 10.11.68.129/25 |  | 10.11.68.1/25 | 0 | T1
800442 | 34 MAIN ST-PO BOX 10 | ERICKSON | Manitoba | R0J 0P0 | Canada | w01437br1 |  | 5M | 0 | 10.138.118.128/25 | 10.27.2.1/26 | 0 | T1
800444 | 220 2ND ST W | BROOKS | Alberta | T1R1B2 | Canada | w01439br1 | 1 | DSL | 0 | 10.136.26.0/25 | 10.31.5.1/26 | 0 | T1
800445 | 1008 CANYON ST | CRESTON | British Columbia | V0B1G0 | Canada | w01440br1 | 1 | DSL | 0 | 10.136.4.0/25 | 10.35.8.1/26 | 0 | T1
800446 | 152 MAIN ST | ERIN | Ontario | N0B1T0 | Canada | c01442br1 | 1 | DSL | 0 | 10.138.6.128/25 | 10.139.3.1/26 | 0 | T1
800447 | 515 The Queensway | Toronto | Ontario | M8Y 1J6 | Canada | c01453br1 | 1 | T1 | 0 | 10.136.226.0/25 | 10.147.50.1/25 | 0 | T1
800448 | 4000 No 3 Road #110 | Richmond | British Columbia | V6X 0J8 | Canada | w01457br1 |  | 5M | 10.34.4.1/26 |  | 10.11.54.129/25 | 0 | T1
800449 | 871 Village Drive | Port Coquitlam | British Columbia | V3B 0G9 | Canada | w01458br1 |  | 10M | 10.34.1.65/26 |  | 10.11.35.129/25 | 0 | T1
800450 | 3122 Mt Lehman Rd-Unit J100 | Abbotsford | British Columbia | V2T0C5 | Canada | w01460br1 |  | 5M | 10.32.134.129/25 |  | 10.22.14.1/24 | 0 | T1
800451 | 12704 167th Avenue NW | Edmonton | Alberta | T6V 1J6 | Canada | w01461br1 |  | 5M | 10.34.3.129/26 |  | 10.11.113.129/25 | 0 | T1
800454 | 161 TALBOT ST N | ESSEX | Ontario | N8M2C6 | Canada | c01472br1 | 1 | DSL | 0 | 10.138.8.0/25 | 10.139.8.129/26 | 0 | T1
800455 | 115 TUDHOPE ST | ESPANOLA | Ontario | P5E1S6 | Canada | c01482br1 | 1 | DSL | 0 | 10.138.15.128/25 | 10.131.4.1/26 | 0 | T1
800456 | 2929 Sunridge Way N.E | CALGARY | Alberta | T1Y 7K7 | Canada | w01486br1 |  | 5M | 10.34.1.1/26 |  | 10.67.7.1/25 | 0 | T1
800458 | 226 MAIN ST S | EXETER | Ontario | N0M1S3 | Canada | c01492br1 | 1 | DSL | 0 | 10.138.16.128/25 | 10.127.44.1/25 | 0 | T1
800463 | 800 Carnarvon Street Unit 240 | New Westminster | British Columbia | V3M 0G3 | Canada | w01504br1 |  | 5M | 10.34.0.1/26 |  | 10.79.46.1/25 | 0 | T1
800464 | 8220 CENTRE ST NE | CALGARY | Alberta | T3K 1J7 | Canada | w01509br1 |  | 5M | 0 | 10.137.124.0/25 | 10.23.57.1/25 | 0 | T1
800466 | 139 Rideau Street | Ottawa | Ontario | K1N5X4 | Canada | e01517br1 |  | 5M | 10.187.55.129/25 |  | 10.187.55.1/25 | 0 | T1
800470 | 795 CANBORO RD | FENWICK | Ontario | L0S1C0 | Canada | c01522br1 |  | T1 | 0 | 10.136.130.0/25 | 10.155.13.1/26 | 0 | T1
800486 | 309 HAYS BLVD | OAKVILLE | Ontario | L6H 6Z3 | Canada | c01532br1 |  | 5M | 0 | 10.137.79.0/25 | 10.123.1.1/25 | 0 | 3M
800490 | 100 ST ANDREW ST E | FERGUS | Ontario | N1M 1P8 | Canada | c01542br1 |  | 5M | 0 | 10.137.79.128/25 | 10.127.50.1/25 | 0 | T1
800491 | 2732 MAIN ST | CLARKS HARBOUR | Nova Scotia | B0W1P0 | Canada | e01543br1 | 1 | DSL | 0 | 10.138.60.0/25 | 10.191.6.129/26 | 0 | T1
800492 | 335 PLEASANT ST | MIRAMICHI | New Brunswick | E1V 3M5 | Canada | e01544br1 |  | 5M | 0 | 10.137.23.128/25 | 10.191.1.1/26 | 0 | T1
800493 | 201 3rd St | Craik | Saskatchewan | S0G 0V0 | Canada | w01548br5 |  | Other | 0 | 10.136.60.128/25 | 10.35.5.1/26 | 0 | T1
800494 | 3810 BOW TRAIL SW | CALGARY | Alberta | T3C2E7 | Canada | w01549br1 |  | 5M | 10.34.16.1/25 | 10.137.221.128/25 | 10.55.8.1/26 | 0 | T1
800495 | 8 ERIE ST N | FISHERVILLE | Ontario | N0A1G0 | Canada | c01552br1 | 1 | DSL | 0 | 10.138.24.128/25 | 10.131.4.129/26 | 0 | T1
800496 | 9 Peakview Way | Halifax | Nova Scotia | B3M 0G2 | Canada | e01554br1 |  | 5M | 10.199.50.129/25 |  | 10.199.50.1/25 | 0 | T1
800497 | 2164 Montreal Road | Ottawa | Ontario | K1J1G4 | Canada | e01556br1 |  | 5M | 10.187.56.129/25 |  | 10.187.56.1/25 | 0 | T1
800500 | 525 Highway 97 South Suite #200 | Kelowna | British Columbia | V1Z 4C9 | Canada | w01560br1 |  | 5M | 10.32.1.129/26 |  | 10.23.6.129/26 | 0 | T1
800501 | 67 JARVIS ST-PO BOX 278 | FORT ERIE | Ontario | L2A 5M9 | Canada | c01562br1 |  | 5M | 0 | 10.137.80.0/25 | 10.135.54.1/25 | 0 | T1
800502 | 2115 King Road | King City | Ontario | L7B 1K2 | Canada | c01564br1 |  | 5M | 10.32.133.1/25 |  | 10.22.11.1/24 | 0 | T1
800503 | 94 Main St | Flin Flon | Manitoba | R8A 1K1 | Canada | w01567br5 |  | Other | 0 | 10.136.61.0/25 | 10.31.40.1/25 | 0 | T1
800505 | 1910 Fowler Drive | Mississauga | Ontario | L5K0A1 | Canada | c01575br1 |  | 5M | 10.123.61.1/24 |  | 10.123.58.1/24 | 0 | T1
800507 | 1100 MALONEY BLVD W | GATINEAU | Quebec | J8T 6G3 | Canada | e01581br1 |  | 5M | 0 | 10.137.113.128/25 | 10.207.50.1/25 | 0 | 3M
800509 | 343 Scott St | Fort Frances | Ontario | P9A 1H1 | Canada | w01592br5 | 1 | Other | 0 | 10.136.61.128/25 | 10.35.9.1/26 | 0 | T1
800510 | 8005 Emerald Drive- Unit 400 | Sherwood Park | Alberta | T8H 0P1 | Canada | w01594br1 |  | 5M | 10.43.63.129/25 |  | 10.43.63.1/25 | 0 | T1
800512 | 16909 103A AVE NW | Edmonton | Alberta | T5P4Y5 | Canada | w01599br1 |  | 5M | 0 | 10.136.244.0/25 | 10.75.70.1/24 | 0 | 3M
800513 | 5 Woodlawn Road West, Unit D5 | Guelph | Ontario | N1H1G8 | Canada | c01604br1 |  | 5M | 10.33.6.1/26 |  | 10.11.52.129/25 | 0 | T1
800514 | 71 Clearview Market Way | Red Deer | Alberta | T4P 0N1 | Canada | w01614br1 |  | 5M | 10.34.0.129/26 | 10.137.125.0/25 | 10.11.76.1/24 | 0 | T1
800515 | 15 SHELDON DR | CAMBRIDGE | Ontario | N1R 6R8 | Canada | c01616br1 |  | 5M | 0 | 10.138.8.128/25 | 10.123.4.1/25 | 0 | T1
800518 | 73 MAIN ST | CAMBRIDGE | Ontario | N1R5V5 | Canada | c01622br1 | 1 | T1 | 0 | 10.137.149.128/25 | 10.127.45.1/25 | 0 | 3M
800521 | 4462 Limebank Rd | Ottawa | Ontario | K1V 2N8 | Canada | e01626br1 |  | 5M | 10.32.135.1/25 |  | 10.22.15.1/24 | 0 | T1
800528 | 541 HESPELER RD | CAMBRIDGE | Ontario | N1R6J2 | Canada | c01632br1 | 1 | T1 | 10.32.150.1/25 | 10.32.150.0/25 | 10.143.7.1/25 | 0 | T1
800529 | 1625 Hillside Ave | Victoria | British Columbia | V8T 2C3 | Canada | w01635br1 |  | 5M | 10.11.67.129/25 |  | 10.11.67.1/25 | 0 | T1
800532 | 144 4th Ave Sw | Calgary | Alberta | T2P 3N4 | Canada | w01639br5 |  | Other | 0 | 10.136.62.0/25 | 10.67.3.129/26 | 0 | T1
800535 | 83 MAIN ST S | GEORGETOWN | Ontario | L7G3E5 | Canada | c01642br1 |  | T1 | 0 | 10.136.130.128/25 | 10.127.10.1/25 | 0 | T1
800536 | 287 RESTIGOUCHE RD | OROMOCTO | New Brunswick | E2V2H2 | Canada | e01644br1 |  | T1 | 0 | 10.136.163.128/25 | 10.187.3.1/26 | 0 | T1
800537 | 195 PRINCIPALE STREET | GRANBY | Quebec | J2G 2V7 | Canada | e01651br1 |  | 5M | 0 | 10.137.24.0/25 | 10.219.46.1/25 | 0 | T1
800543 | 199 MAIN ST | PLASTER ROCK | New Brunswick | E0J1W0 | Canada | e01654br1 |  | T1 | 0 | 10.136.164.0/25 | 10.183.6.129/26 | 0 | T1
800555 | 728 NORTHMOUNT DR NW | CALGARY | Alberta | T2K3K2 | Canada | w01659br1 | 1 | T1 | 0 | 10.137.222.0/25 | 10.27.47.1/25 | 0 | 3M
800563 | 109 MAIN ST | GERALDTON | Ontario | P0T1M0 | Canada | w01662br1 | 1 | DSL | 0 | 10.138.82.128/25 | 10.19.7.129/26 | 0 | T1
800571 | 232 GUELPH ST | GEORGETOWN | Ontario | L7G4B1 | Canada | c01672br1 |  | 5M | 0 | 10.136.131.0/25 | 10.127.9.1/25 | 0 | T1
800572 | 7020 Saint Barbara Blvd | Mississauga | Ontario | L5W0E6 | Canada | c01678br1 |  | T1 | 10.33.1.65/26 |  | 10.123.60.1/25 | 0 | T1
800573 | 10324 10TH ST | DAWSON CREEK | British Columbia | V1G3T6 | Canada | w01680br1 | 1 | DSL | 0 | 10.136.28.128/25 | 10.35.41.1/25 | 0 | T1
800574 | 158 THE SQUARE | GODERICH | Ontario | N7A3Z2 | Canada | c01682br1 |  | T1 | 0 | 10.138.25.0/25 | 10.127.13.129/26 | 0 | T1
800576 | 203 Laverendrye Ave | Churchill | Manitoba | R0B 0E0 | Canada | w01697br5 |  | Other | 0 | 10.136.62.128/25 | 10.55.2.1/26 | 0 | T1
800580 | 10615 Creditview Road | BRAMPTON | Ontario | L7A0T4 | Canada | c01704br1 |  | 5M | 10.33.4.1/26 |  | 10.11.16.65/26 | 0 | T1
800581 | 2 Gladstone Avenue, Unit 1 | TORONTO | Ontario | M6J3K6 | Canada | c01710br1 |  | 5M | 10.33.13.129/26 | 10.137.80.128/25 | 10.151.16.1/26 | 0 | T1
800582 | 425 BOUL ST JOSEPH | GATINEAU | Quebec | J8Y3Z8 | Canada | e01711br1 | 1 | T1 | 0 | 10.137.209.0/25 | 10.191.37.1/25 | 0 | 3M
800583 | 1 Hurontario Street | Mississauga | Ontario | M5G0A3 | Canada | c01712br1 |  | 5M | 10.123.59.129/25 |  | 10.123.59.1/25 | 0 | T1
800584 | 7163 Yonge Street | Markham | Ontario | L3T 0C8 | Canada | c01718br1 |  | 5M | 10.32.144.129/25 |  | 10.22.34.1/24 | 0 | T1
800585 | 320 Harwood Ave South-Unit #4 | Ajax | Ontario | L1S2J1 | Canada | c01720br1 |  | 5M | 10.135.67.129/25 |  | 10.135.68.129/25 | 0 | T1
800586 | 43 MAIN ST | GRAND VALLEY | Ontario | L0N1G0 | Canada | c01722br1 | 1 | DSL | 0 | 10.138.25.128/25 | 10.131.21.1/26 | 0 | T1
800587 | 9090 Leduc Blvd Suite 110 | BROSSARD | Quebec | J4Y 0E2 | Canada | e01724br1 | 1 | 20M | 10.32.4.129/25 |  | 10.11.48.129/25 | 0 | T1
800588 | 570 Queen St W | TORONTO | Ontario | M5V 2B5 | Canada | c01728br1 |  | 5M | 10.33.2.129/26 |  | 10.11.17.129/25 | 0 | T1
800589 | 11170 84TH AVE | Delta | British Columbia | V4C2L7 | Canada | w01730br1 | 1 | T1 | 0 | 10.137.222.128/25 | 10.67.38.1/25 | 0 | T1
800591 | 398 MUSKOKA RD N | GRAVENHURST | Ontario | P1P1G3 | Canada | c01742br1 | 1 | DSL | 0 | 10.138.26.0/25 | 10.127.19.1/26 | 0 | T1
800592 | 24 LIVINGSTON AVE | GRIMSBY | Ontario | L3M1K7 | Canada | c01752br1 | 1 | DSL | 0 | 10.138.26.128/25 | 10.143.0.129/26 | 0 | T1
800593 | 50 Sage Creek Blvd- Unit 200 | Winnipeg | Manitoba | R3X 0J6 | Canada | w01753br1 |  | 5M | 10.34.2.1/26 |  | 10.11.18.129/25 | 0 | T1
800594 | 395 TRUNK RD | DUNCAN | British Columbia | V9L 2P4 | Canada | w01760br1 |  | 5M | 0 | 10.137.166.0/25 | 10.79.35.1/25 | 10.77.74.1/24 | 3M
800595 | 74 WYNDHAM ST N | GUELPH | Ontario | N1H4E6 | Canada | c01762br1 |  | 5M | 0 | 10.137.81.0/25 | 10.143.72.1/24 | 0 | 3M
800596 | 44 PORTLAND ST | Dartmouth | Nova Scotia | B2Y1H3 | Canada | e01763br1 |  | T1 | 0 | 10.136.105.128/25 | 10.199.45.1/25 | 0 | T1
800597 | 9393 MAIN ST | RICHIBUCTO | New Brunswick | E4W4B6 | Canada | e01764br1 | 1 | DSL | 0 | 10.138.60.128/25 | 10.183.3.1/26 | 0 | T1
800598 | 18273 Yonge Street | East Gwillimbury | Ontario | L9N 0A2 | Canada | c01766br1 |  | 5M | 10.33.1.193/26 |  | 10.147.54.1/25 | 0 | T1
800599 | 114 Broad St | Cut Knife | Saskatchewan | S0M 0N0 | Canada | w01768br5 |  | Other | 0 | 10.136.63.0/25 | 10.35.7.129/26 | 0 | T1
800600 | 117 SILVERCREEK PKWY N | GUELPH | Ontario | N1H3T2 | Canada | c01772br1 |  | 5M | 0 | 10.137.7.0/25 | 10.127.48.1/25 | 0 | 3M
800601 | 1530 Dundas Street East- Unit C4 | Mississauga | Ontario | L4X 1L4 | Canada | c01773br1 |  | 5M | 10.33.2.65/26 |  | 10.11.38.129/25 | 0 | T1
800603 | 5345 Fernbank Rd, RR 1 | Ottawa | Ontario | K2S 0T7 | Canada | e01783br1 |  | 5M | 10.33.6.65/26 |  | 10.11.57.129/25 | 0 | T1
800604 | 121 PINE GLEN RD | RIVERVIEW | New Brunswick | E1B1V5 | Canada | e01784br1 | 1 | DSL | 0 | 10.138.61.0/25 | 10.187.4.129/26 | 0 | T1
800606 | 202 BROWNLOW AVE-STE 100-CAMBR | DARTMOUTH | Nova Scotia | B3B 1T5 | Canada | e01793br1 |  | 5M | 0 | 10.137.24.128/25 | 10.219.43.1/25 | 0 | T1
800607 | 30 Main St South, PO Box 70, RR 3 | HAGERSVILLE | Ontario | N0A 1H0 | Canada | c01802br1 |  | 5M | 0 | 10.138.9.0/25 | 10.139.1.1/26 | 0 | T1
800609 | 1153 Esquimalt Rd. | VICTORIA | British Columbia | V9A3N7 | Canada | w01810br1 | 1 | T1 | 0 | 10.136.195.0/25 | 10.11.55.1/25 | 0 | T1
800610 | 9919 Fairmount Dr Se | Calgary | Alberta | T2J 0S3 | Canada | w01819br5 | 1 | Other | 0 | 10.136.63.128/25 | 10.31.43.1/25 | 0 | 3M
800611 | 100 KING ST W --main floor | HAMILTON | Ontario | L8P1A2 | Canada | c01822br1 | 1 | 5M | 0 | 10.136.241.0/25 | 10.143.70.1/24 | 0 | 3M
800612 | 51 Hanna Ave | TORONTO | Ontario | M6K 3N7 | Canada | c01824br1 | 1 | 5M | 10.33.5.1/26 |  | 10.11.44.129/25 | 0 | T1
800614 | 1300 PEMBINA HWY | WINNIPEG | Manitoba | R3T 2B4 | Canada | w01827br1 |  | 5M | 0 | 10.138.119.0/25 | 10.11.42.1/25 | 0 | T1
800615 | 2068 DE CHAMBLY RD | LONGUEUIL | Quebec | J4J3Y7 | Canada | e01831br1 | 1 | DSL | 0 | 10.137.247.128/25 | 10.187.43.1/25 | 0 | T1
800616 | 1022 COLE HARBOUR RD | DARTMOUTH | Nova Scotia | B2V 1E7 | Canada | e01833br1 |  | 5M | 0 | 10.137.114.0/25 | 10.191.51.1/25 | 0 | T1
800617 | 51 Mountainash Rd, Unit #1 | Brampton | Ontario | L6R 1W4 | Canada | c01834br1 |  | 5M | 10.33.5.65/26 |  | 10.11.45.129/25 | 0 | T1
800618 | 215 Taschereau Blvd | Quebec | Quebec | J5R 4H9 | Canada | e01836br1 |  | 5M | 10.32.0.193/26 |  | 10.11.113.1/25 | 0 | T1
800620 | 825 ST LAURENT W | LONGUEUIL | Quebec | J4K2V1 | Canada | e01851br1 | 1 | DSL | 0 | 10.137.248.0/25 | 10.187.5.1/25 | 0 | T1
800622 | 374 C STUART DR W | FORT ST JAMES | British Columbia | V0J1P0 | Canada | w01860br1 |  | T1 | 0 | 10.136.195.128/25 | 10.35.10.1/26 | 0 | T1
800623 | 103 MAIN ST | SACKVILLE | New Brunswick | E4L4B1 | Canada | e01874br1 | 1 | DSL | 0 | 10.137.248.128/25 | 10.215.3.129/26 | 0 | T1
800624 | 300 FIRST ST W | DELISLE | Saskatchewan | S0L0P0 | Canada | w01878br1 |  | T1 | 0 | 10.136.196.0/25 | 10.35.2.129/26 | 0 | T1
800625 | 3919a Richmond Rd Sw | Calgary | Alberta | T3E 4P2 | Canada | w01879br5 | 1 | Other | 0 | 10.136.64.0/25 | 10.55.47.1/25 | 0 | T1
800626 | 555 CONCESSION ST | HAMILTON | Ontario | L8V1A8 | Canada | c01882br1 |  | T1 | 0 | 10.137.168.128/25 | 10.131.0.129/26 | 0 | T1
800627 | 4977 Jean-Talon St. W | MONTREAL | Quebec | H4P 1W7 | Canada | e01891br1 |  | 10M | 10.32.1.193/26 |  | 10.11.39.129/25 | 0 | T1
800628 | 680 Longworth Ave Unit B1 | Bowmanville | Ontario | L1C 0M9 | Canada | c01894br1 |  | 5M | 10.33.5.129/26 |  | 10.11.47.129/25 | 0 | T1
800629 | 375 BOUL MANSEAU | JOLIETTE | Quebec | J6E3C9 | Canada | e01901br1 |  | T1 | 0 | 10.136.164.128/25 | 10.215.40.1/25 | 0 | T1
800630 | 169 Hampton Rd. | QUISPAMSIS | New Brunswick | E2E2R3 | Canada | e01904br1 |  | 3M | 0 | 10.137.63.128/25 | 10.183.20.129/26 | 0 | 3M
800631 | 10312 100 ST | FORT ST JOHN | British Columbia | V1J 3Z1 | Canada | w01920br1 |  | 5M | 0 | 10.137.125.128/25 | 10.55.39.1/25 | 0 | T1
800632 | 810 UPPER GAGE AVE | HAMILTON | Ontario | L8V 4L8 | Canada | c01922br1 |  | 5M | 0 | 10.137.82.0/25 | 10.131.35.1/25 | 0 | T1
800635 | 100 Riverstone Ridge - Unit 101 | Fort McMurray | Alberta | T9K 1S6 | Canada | w01934br1 |  | 5M | 10.32.143.1/25 |  | 10.22.31.1/24 | 0 | T1
800637 | 1145 BARTON ST E-UNIT 1 | HAMILTON | Ontario | L8H 2V2 | Canada | c01942cr1 |  | 5M | 0 | 10.137.159.128/25 | 10.135.68.1/25 | 0 | 3M
800638 | 40 TACOMA DR | Dartmouth | Nova Scotia | B2W 6E2 | Canada | e01943br1 |  | 5M | 0 | 10.136.165.0/25 | 10.191.53.1/25 | 0 | T1
800639 | 5929 Cousineau Blvd | St-Hubert | Quebec | J3Y7P5 | Canada | e01951br1 |  | 5M | 10.32.139.1/25 |  | 10.22.23.1/24 | 0 | T1
800640 | 2132 KING ST E | HAMILTON | Ontario | L8K1W6 | Canada | c01952br1 |  | T1 | 0 | 10.136.131.128/25 | 10.143.0.1/26 | 0 | T1
800641 | 614 Railway Ave | Glenboro | Manitoba | R0K 0X0 | Canada | w01957br5 |  | Other | 0 | 10.136.64.128/25 | 10.63.3.129/26 | 0 | T1
800642 | 65 Locke St. S. | HAMILTON | Ontario | L8P4A3 | Canada | c01962br1 |  | T1 | 0 | 10.136.132.0/25 | 10.151.0.1/26 | 0 | T1
800643 | 226 WATER ST | ST. JOHN'S | Newfoundland | A1C1A9 | Canada | e01963br1 |  | T1 | 0 | 10.136.236.128/25 | 10.218.49.1/24 | 0 | T1
800645 | 3750 DU ROYAUME BLVD | JONQUIERE | Quebec | G7X 0A4 | Canada | e01971br1 |  | 5M | 0 | 10.137.114.128/25 | 10.215.42.1/25 | 0 | T1
800647 | 111 Lansdowne Ave | Saint John | New Brunswick | E2K 2Z9 | Canada | e01984br5 |  | Other | 0 | 10.136.46.0/25 | 10.179.35.1/25 | 0 | T1
800648 | 3541 Blanshard St | VICTORIA | British Columbia | V8Z 0B9 | Canada | w01988br1 |  | 5M | 10.34.14.129/26 |  | 10.11.10.193/26 | 0 | T1
800649 | 417 10 St NW | CALGARY | Alberta | T2N 1W1 | Canada | w01989br1 |  | 5M | 0 | 10.137.126.0/25 | 10.67.49.1/25 | 0 | T1
800650 | 900 GIBSONS WAY Suite #33 | GIBSONS | British Columbia | V0N 1V7 | Canada | w02000br1 | 1 | DSL | 0 | 10.136.20.128/25 | 10.67.1.129/26 | 0 | T1
800651 | 515 WESTMORLAND RD | SAINT JOHN | New Brunswick | E2J 3W9 | Canada | e02014cr1 |  | 5M | 0 | 10.137.51.0/25 | 10.179.46.1/25 | 0 | T1
800652 | 2060 Symons Valley PY NW - Unit 10000 | Calgary | Alberta | T3P 0M9 | Canada | w02018br1 |  | 5M | 10.32.140.1/25 |  | 10.22.25.1/24 | 0 | T1
800654 | 1803 STONE CHURCH RD E-UNIT 1 | STONEY CREEK | Ontario | L8J 0B4 | Canada | c02034cr1 |  | 5M | 0 | 10.137.48.128/25 | 10.143.51.1/25 | 0 | T1
800655 | 800 Yankiee Valley Blvd, Unit 325 | Ardie | Alberta | T4B 3Y2 | Canada | w02039br1 |  | 10M | 10.32.138.129/25 |  | 10.22.22.1/24 | 0 | T1
800656 | 752 UPPER JAMES ST | HAMILTON | Ontario | L9C 3A2 | Canada | c02042br1 |  | 5M | 0 | 10.137.82.128/25 | 10.131.39.1/25 | 0 | T1
800657 | 5085 HIGHWAY 69 N | HANMER | Ontario | P3P 1J6 | Canada | c02052br1 | 1 | T1 | 0 | 10.136.238.128/25 | 10.123.1.129/26 | 0 | 3M
800662 | 287 10TH ST | Hanover | Ontario | N4N1P1 | Canada | c02062br1 |  | T1 | 0 | 10.136.132.128/25 | 10.127.11.129/26 | 0 | T1
800663 | 11805 BRAMALEA RD | Brampton | Ontario | L6R 3S9 | Canada | c02064br1 |  | 5M | 10.32.146.129/25 |  | 10.22.38.1/24 | 0 | T1
800664 | 53 45TH AVE | LACHINE | Quebec | H8T2L8 | Canada | e02071br1 |  | 5M | 0 | 10.137.25.0/25 | 10.187.3.129/26 | 0 | T1
800665 | 1845 Main St W | HAMILTON | Ontario | L8S 1J2 | Canada | c02072br5 |  | Other | 0 | 10.136.39.128/25 | 10.151.1.1/26 | 0 | T1
800666 | 339 King St E | TORONTO | Ontario | M5A 1L1 | Canada | c02074br1 |  | 5M | 10.32.136.1/25 |  | 10.22.17.1/24 | 0 | T1
800667 | 11855 224TH ST | MAPLE RIDGE | British Columbia | V2X 6B1 | Canada | w02080cr1 |  | 5M | 0 | 10.137.166.128/25 | 10.23.35.1/25 | 10.23.35.129/25 | T1
800668 | 102 Elora St. S. | HARRISTON | Ontario | N0G1Z0 | Canada | c02082br1 |  | T1 | 0 | 10.138.27.0/25 | 10.127.19.193/26 | 0 | T1
800669 | 43 Fourth St Se | Hamiota | Manitoba | R0M 0T0 | Canada | w02087br5 |  | Other | 0 | 10.136.65.0/25 | 10.63.6.129/26 | 0 | T1
800670 | 1333 32ND AVE NE | CALGARY | Alberta | T2E 7Z5 | Canada | w02089br1 |  | 5M | 0 | 10.137.126.128/25 | 10.31.42.1/25 | 0 | T1
800672 | 8600 Newman Blvd | LASALLE | Quebec | H8N 1Y5 | Canada | e02091br1 | 1 | T1 | 0 | 10.137.209.128/25 | 10.207.52.1/25 | 0 | 3M
800673 | 51 WATER ST, PO BOX 1000 | DIGBY | Nova Scotia | B0V1A0 | Canada | e02093br1 | 1 | DSL | 0 | 10.138.61.128/25 | 10.191.4.129/26 | 0 | T1
800674 | 26 MILLTOWN BLVD | ST STEPHEN | New Brunswick | E3L1G3 | Canada | e02094br1 | 1 | DSL | 0 | 10.138.62.0/25 | 10.215.37.1/25 | 0 | T1
800675 | 533 Broadway Ave | Kilarney | Manitoba | R0K 1G0 | Canada | w02097br5 |  | Other | 0 | 10.136.65.128/25 | 10.31.1.129/26 | 0 | T1
800676 | Main & First | Elrose | Saskatchewan | S0L 0Z0 | Canada | w02098br5 |  | Other | 0 | 10.136.66.0/25 | 10.35.14.129/26 | 0 | T1
800677 | 19 FRONT ST E | HASTINGS | Ontario | K0L1Y0 | Canada | c02102br1 | 1 | DSL | 0 | 10.138.27.128/25 | 10.151.11.1/26 | 0 | T1
800678 | 61 Kelsey Dr | St John's | New Foundland | A1B5C8 | Canada | e02105br1 |  | 5M | 10.32.134.1/25 |  | 10.22.13.1/24 | 0 | T1
800679 | 5269 Memorial Dr Se | Calgary | Alberta | T2A 4V1 | Canada | w02109br5 | 1 | Other | 0 | 10.136.66.128/25 | 10.67.47.1/25 | 0 | T1
800680 | 801 MOHAWK RD W | HAMILTON | Ontario | L9C6C2 | Canada | c02112br1 |  | 5M | 0 | 10.137.170.128/25 | 10.127.12.129/26 | 0 | T1
800681 | 4056 CONFEDERATION PARKWAY | Mississauga | Ontario | L5B 0G4 | Canada | c02115br1 |  | 5M | 10.32.141.129/25 |  | 10.22.28.1/24 | 0 | T1
800682 | 632 MAIN ST | SAUBLE BEACH | Ontario | N0H 2G0 | Canada | c02122br1 |  | T1 | 0 | 10.138.28.0/25 | 10.131.21.129/26 | 0 | T1
800683 | 211 CENTRUM BLVD | Orleans | Ontario | K1E3X1 | Canada | e02124br1 | 1 | T1 | 0 | 10.137.210.0/25 | 10.187.48.1/25 | 0 | 3M
800684 | 5280 Saint Margarets Bay Rd | Upper Tantallon | Nova Scotia | B3Z 2J1 | Canada | e02125br1 |  | 5M | 10.32.5.65/26 |  | 10.11.55.129/25 | 0 | T1
800685 | 33 PRINCESS ST. | LEAMINGTON | Ontario | N8H5C5 | Canada | c02132br1 | 1 | DSL | 0 | 10.138.99.128/25 | 10.123.8.1/26 | 0 | T1
800686 | 97 MAIN ST | HILLSBURGH | Ontario | N0B1Z0 | Canada | c02142br1 | 1 | DSL | 0 | 10.138.28.128/25 | 10.131.23.1/26 | 0 | T1
800693 | 101 Dundas St W | Toronto | Ontario | M5G1C4 | Canada | e01951br1 |  | 5M | 10.32.139.1/25 |  | 10.22.23.1/24 | 0 | T1
800694 | 3297 PORTAGE AVE | WINNIPEG | Manitoba | R3K 0W7 | Canada | w02147br1 |  | 5M | 0 | 10.137.127.0/25 | 10.35.39.1/25 | 0 | 3M
800695 | 400 SPENCE AVE | HAWKESBURY | Ontario | K6A2Y3 | Canada | e02152br1 | 1 | DSL | 0 | 10.138.62.128/25 | 10.191.8.1/26 | 0 | T1
800696 | 382 YONGE ST | TORONTO | Ontario | M5B1S8 | Canada | c02157br1 |  | 5M | 10.32.135.129/25 |  | 10.22.16.1/24 | 0 | 5M
800697 | 11480 BRAESIDE DR SW | CALGARY | Alberta | T2W4X8 | Canada | w02159br1 | 1 | T1 | 0 | 10.137.223.0/25 | 10.23.28.1/25 | 0 | T1
800698 | HWY 62-HAGWILGET VILLAGE-PO BOX 339 | New Hazelton | British Columbia | V0J2J0 | Canada | w02160br1 |  | T1 | 0 | 10.138.114.0/25 | 10.19.4.129/26 | 0 | T1
800699 | 22 MAIN ST | HUNTSVILLE | Ontario | P1H 2C9 | Canada | c02162br1 |  | 5M | 0 | 10.137.83.0/25 | 10.139.11.1/25 | 0 | T1
800700 | 1004 Weber Greens Drive | Edmonton | Alberta | T5T 4K5 | Canada | w02164br1 |  | 5M | 10.32.137.129/25 |  | 10.22.20.1/24 | 0 | T1
800701 | 2320 KINGSWAY VANCOUVER BC Canada V5R 5G9 | Vancouver | British Columbia | V5R 5G9 | Canada | w02165br1 |  | 5M | 10.32.136.129/25 |  | 10.22.18.1/24 | 0 | T1
800702 | 2640 52ND ST NE | CALGARY | Alberta | T1Y 3R6 | Canada | w02169br1 |  | 5M | 0 | 10.137.127.128/25 | 10.23.30.1/25 | 0 | 3M
800703 | 156 THAMES ST S | INGERSOLL | Ontario | N5C2T4 | Canada | c02182br1 |  | DSL | 0 | 10.138.29.0/25 | 10.135.6.129/26 | 0 | T1
800704 | 1970 St Clair Avenue West - Suite 101 | Toronto | Ontario | M6N 0A3 | Canada | c02186br1 |  |  | #N/A |  | #N/A | #N/A | T1
800705 | 5602 4TH ST NW | CALGARY | Alberta | T2K1B2 | Canada | w02189br1 | 1 | T1 | 0 | 10.137.223.128/25 | 10.67.50.1/25 | 0 | T1
800706 | 1100 Wellington St | Montreal | Quebec | H3C 0M5 | Canada | e02201br1 |  | 5M | 10.32.142.1/25 |  | 10.22.29.1/24 | 0 | T1
800707 | 178 HWY #214 | ELMSDALE | Nova Scotia | B2S1H7 | Canada | e02203br1 | 1 | DSL | 0 | 10.138.63.0/25 | 10.183.39.1/25 | 0 | T1
800708 | 664 MAIN ST | SUSSEX | New Brunswick | E4E 7H9 | Canada | e02204cr1 |  | 5M | 0 | 10.137.51.128/25 | 10.203.38.1/25 | 10.203.38.129/25 | T1
800709 | 436 Main St | Esterhazy | Saskatchewan | S0A 0X0 | Canada | w02208br5 |  | Other | 0 | 10.136.35.0/25 | 10.31.9.1/26 | 0 | T1
800710 | 59 5TH AVE E | LA SARRE | Quebec | J9Z1L1 | Canada | e02211br1 |  | T1 | 0 | 10.136.165.128/25 | 10.183.1.1/26 | 0 | T1
800711 | 3425 Quance Street - Unit 100 | Regina | Saskatchewan | S4V 2J2 | Canada | w02214br1 |  | 5M | 10.32.139.129/25 |  | 10.22.24.1/24 | 0 | T1
800712 | 14 PARK NORTH | LAC DU BONNET | Manitoba | R0E 1A0 | Canada | w02217br1 |  | T1 | 0 | 10.136.196.128/25 | 10.31.1.1/25 | 0 | T1
800713 | 1100 BOUL MOODY | TERREBONNE | Quebec | J6W3K9 | Canada | e02221br1 |  | 5M | 0 | 10.138.63.128/25 | 10.215.47.1/25 | 0 | T1
800714 | 549 NOTRE DAME ST N | BELLE RIVER | Ontario | N0R1A0 | Canada | c02222br1 | 1 | DSL | 0 | 10.138.29.128/25 | 10.131.16.1/26 | 0 | T1
800715 | 3232 WEST YELLOWHEAD HWY 16 | HOUSTON | British Columbia | V0J1Z0 | Canada | w02240br1 |  | T1 | 0 | 10.136.222.128/25 | 10.67.4.1/26 | 0 | T1
800716 | 53 PLAZA DR | IROQUOIS | Ontario | K0E1K0 | Canada | e02242br1 | 1 | DSL | 0 | 10.138.64.0/25 | 10.191.11.1/26 | 0 | T1
800717 | 393 RYMAL RD | HAMILTON | Ontario | L9B1V2 | Canada | c02244br1 |  | T1 | 0 | 10.136.251.0/25 | 10.139.0.1/26 | 0 | T1
800718 | 3571 Dagenais Blvd West | LAVAL | Quebec | H7P 4X4 | Canada | e02271br1 |  | T1 | 0 | 10.136.166.0/25 | 10.207.8.1/26 | 0 | T1
800720 | 1500 MONETTE MTEE | LAVAL | Quebec | H7M5C9 | Canada | e02291br6 |  | T1 | 0 | 10.138.100.0/25 | 10.187.7.1/26 | 0 | T1
800719 | 1958 DES LAURENTIDES BLVD | LAVAL | Quebec | H7M 2R3 | Canada | e02291br1 |  | 5M | 0 | 10.137.25.128/25 | 10.195.45.1/25 | 0 | 3M
800721 | 250 SHAWVILLE BLVD SE-UNIT 144 | CALGARY | Alberta | T2Y 2Z7 | Canada | w02299br1 |  | 5M | 0 | 10.138.16.0/25 | 10.23.32.1/25 | 0 | 3M
800724 | 3100 LE CARREFOUR BLVD | LAVAL | Quebec | H7T2K7 | Canada | e02301cr1 |  | 10M | 0 | 10.137.69.128/25 | 10.203.74.1/24 | 10.203.75.1/24 | 3M
800728 | 41 UNION ST | GLACE BAY | Nova Scotia | B1A2P6 | Canada | e02313br1 | 1 | DSL | 0 | 10.137.249.0/25 | 10.179.10.129/26 | 0 | T1
800729 | 540 MAIN ST | WOODSTOCK | New Brunswick | E7M2C3 | Canada | e02314br1 | 1 | DSL | 0 | 10.137.249.128/25 | 10.215.36.1/25 | 0 | T1
800730 | 1202 4TH ST | ESTEVAN | Saskatchewan | S4A0W9 | Canada | w02318br1 | 1 | T1 | 0 | 10.136.11.128/25 | 10.35.11.1/26 | 0 | T1
800731 | 255 5TH AVE SW | CALGARY | Alberta | T2P3G6 | Canada | w02319br1 |  | 5M | 0 | 10.137.128.0/25 | 10.43.39.1/25 | 0 | 3M
800732 | 186 VICTORIA ST | KAMLOOPS | British Columbia | V2C 5R3 | Canada | w02320br1 |  | 5M | 0 | 10.137.128.128/25 | 10.67.78.1/24 | 0 | 3M
800733 | 144 MAIN ST S | KENORA | Ontario | P9N1S9 | Canada | w02322br1 | 1 | T1 | 0 | 10.136.0.0/25 | 10.27.9.129/26 | 0 | 3M
800734 | 3803 LOGGERS WAY | KINBURN | Ontario | K0A2H0 | Canada | e02342br1 |  | T1 | 0 | 10.136.166.128/25 | 10.191.12.1/26 | 0 | T1
800735 | 555 STRATHCONA BLVD SW-UNIT 10 | CALGARY | Alberta | T3H 2Z9 | Canada | w02349br1 |  | 5M | 0 | 10.137.129.0/25 | 10.55.8.129/25 | 0 | T1
800736 | 1210 Summit Dr | Kamloops | British Columbia | V2C 6M1 | Canada | w02360br5 | 1 | Other | 0 | 10.136.67.0/25 | 10.63.47.1/25 | 0 | T1
800737 | 757 QUEEN ST | KINCARDINE | Ontario | N2Z2Y8 | Canada | c02362br1 |  | T1 | 0 | 10.136.16.0/25 | 10.127.1.1/26 | 0 | T1
800738 | 20678 Willoughby Town Centre,Drive Bldg B | Langly | British Columbia | V2Y 0L7 | Canada | w02370br1 |  | 5M | 10.34.63.129/25 |  | 10.11.73.1/24 | 0 | T1
800740 | 1955 Mountain Rd | MONCTON | New Brunswick | E1G 1A8 | Canada | e02374br1 |  | 5M | 0 | 10.137.240.0/25 | 10.199.5.1/26 | 0 | T1
800742 | 65 PRINCESS ST | KINGSTON | Ontario | K7L 1A6 | Canada | c02382br1 |  | 5M | 0 | 10.137.66.128/25 | 10.143.76.1/24 | 0 | 3M
800743 | 131 RUE QUEEN | LENNOXVILLE | Quebec | J1M1J7 | Canada | e02391br1 |  | T1 | 0 | 10.136.167.0/25 | 10.179.3.1/26 | 0 | T1
800745 | 1665 ELLIS ST-SUITE 102 | KELOWNA | British Columbia | V1Y 2B3 | Canada | w02400br1 |  | 5M | 0 | 10.136.246.128/25 | 10.11.70.1/24 | 0 | 3M
800746 | 523 Gardiners Road | KINGSTON | Ontario | K7M3Y3 | Canada | c02402br1 |  | 5M | 0 | 10.137.7.128/25 | 10.127.71.1/23 | 0 | 3M
800747 | 10199 101 STREET NW | EDMONTON | Alberta | T5J3Y4 | Canada | W02409br1 |  | 5M | 0 | 10.138.95.128/25 | 10.75.62.1/25 | 0 | T1
800748 | 7955 Financial Dr | Brampton | Ontario | L6Y 0J8 | Canada | c02413br1 |  |  | #N/A |  | #N/A | #N/A | T1
800749 | 1313-10TH AVE SW | CALGARY | Alberta | T3C 3P9 | Canada | w02419br1 |  | 10M | 0 | 10.138.100.128/25 | 10.65.34.1/23 | 0 | 10M
800750 | 823 PRINCESS ST | KINGSTON | Ontario | K7L1G6 | Canada | c02422br1 |  | T1 | 0 | 10.136.133.0/25 | 10.143.7.129/26 | 0 | T1
800751 | 110 MAIN ST | GUYSBOROUGH | Nova Scotia | B0H1N0 | Canada | e02423br1 |  | T1 | 0 | 10.136.167.128/25 | 10.183.13.1/26 | 0 | T1
800754 | 34 Main St | Eyebrow | Saskatchewan | S0H 1L0 | Canada | w02428br1 |  | Other | 0 |  | 10.19.17.129/26 | 0
800757 | 5415 DE LA RIVE SUD BLVD | LEVIS | Quebec | G6V 4Z3 | Canada | e02431br1 |  | 5M | 0 | 10.137.115.0/25 | 10.215.41.1/25 | 0 | T1
800758 | 1840 COOPER RD | KELOWNA | British Columbia | V1Y 8K5 | Canada | w02440br1 |  | 5M | 0 | 10.137.129.128/25 | 10.23.52.1/25 | 0 | 3M
800759 | 11 DIVISION ST N | KINGSVILLE | Ontario | N9Y 1C7 | Canada | c02442br1 | 1 | DSL | 0 | 10.138.30.0/25 | 10.131.19.129/26 | 0 | T1
800763 | 3036 Pandosy St | Kelowna | British Columbia | V1Y 1W2 | Canada | w02450br5 | 1 | Other | 0 | 10.136.67.128/25 | 10.55.7.129/25 | 0 | T1
800766 | 72 Rue Du Palais De Justice | Montmagny | Quebec | G5V 1P5 | Canada | e02461br5 |  | Other | 0 | 10.136.46.128/25 | 10.199.1.129/26 | 0 | T1
800767 | 30 GOVERNMENT RD W | KIRKLAND LAKE | Ontario | P2N3H7 | Canada | c02462br1 |  | T1 | 0 | 10.136.133.128/25 | 10.131.11.129/26 | 0 | T1
800770 | Main & Ellis St | Manitou | Manitoba | R0G 1G0 | Canada | w02477br5 |  | Other | 0 | 10.136.68.0/25 | 10.55.4.129/26 | 0 | T1
800779 | 32 DUKE ST W | KITCHENER | Ontario | N2H 3W4 | Canada | c02482br1 |  | 5M | 0 | 10.138.9.128/25 | 10.131.42.1/25 | 0 | 3M
800783 | 30 DUKE ST W-8TH FLR , KITCHENER , ON, N2H 3W5 | KITCHENER | Ontario | N2H 3W5 | Canada | c02496br1 |  | 5M | 0 | 10.137.8.0/25 | 10.151.35.1/25 | 0 | 3M
800785 | 1020 OTTAWA ST N | KITCHENER | Ontario | N2A 3Z3 | Canada | c02502cr1 |  | 5M | 0 | 10.137.160.0/25 | 10.151.9.129/25 | 0 | 3M
800786 | 600 FAIRWAY RD S , KITCHENER , ON, N2C 1X3 | KITCHENER | Ontario | N2C1X3 | Canada | c02512br1 | 1 | T1 | 0 | 10.137.173.128/25 | 10.135.0.1/25 | 0 | T1
800787 | 5805 Almon St | Halifax | Nova Scotia | B3K 1T7 | Canada | e02533br5 | 1 | Other | 0 | 10.136.47.0/25 | 10.199.41.1/25 | 0 | T1
800788 | 29 Main St | Fillmore | Saskatchewan | S0G1N0 | Canada | w02538br5 |  | Other | 0 | 10.138.129.128/25 | 10.19.3.129/26 | 0 | T1
800789 | 740 8th Ave Sw | Calgary | Alberta | T2P 1H2 | Canada | w02539br5 |  | Other | 0 | 10.136.68.128/25 | 10.11.11.129/26 | 0 | T1
800790 | 8 NASHVILLE RD-PO BOX 293 | KLEINBURG | Ontario | L0J 1C0 | Canada | c02542br1 |  | 5M | 0 | 10.138.10.0/25 | 10.151.7.1/25 | 0 | T1
800794 | 413 HIGHLAND RD W | KITCHENER | Ontario | N2M 3C6 | Canada | c02552br1 |  | 5M | 0 | 10.137.83.128/25 | 10.135.8.129/25 | 0 | T1
800795 | 375 WALLINGER AVE | KIMBERLEY | British Columbia | V1A1Z3 | Canada | w02560br1 | 1 | DSL | 0 | 10.136.2.128/25 | 10.35.12.1/26 | 0 | T1
800797 | 50 QUEEN ST | LAKEFIELD | Ontario | K0L2H0 | Canada | c02562br1 | 1 | DSL | 0 | 10.138.30.128/25 | 10.147.12.1/26 | 0 | T1
800798 | 3900 COTE VERTU-SUITE 101 | ST-LAURENT | Quebec | H4R 1V4 | Canada | e02591br1 |  | 5M | 0 | 10.137.26.0/25 | 10.199.47.1/25 | 0 | 3M
800799 | 2550 MAIN ST | LONDON | Ontario | N6P1R1 | Canada | c02602br1 | 1 | DSL | 0 | 10.138.31.0/25 | 10.135.5.129/26 | 0 | T1
800800 | 516 Burrows Rd | Mccreary | Manitoba | R0J 1B0 | Canada | w02607br5 |  | Other | 0 | 10.136.69.0/25 | 10.55.5.1/26 | 0 | T1
800801 | 220 LAKESHORE RD W | MISSISSAUGA | Ontario | L5H 1G6 | Canada | c02612br1 |  | 5M | 10.33.2.1/26 |  | 10.147.5.1/26 | 0 | T1
800802 | 560 Cure Labelle Blvd. | Laval | Quebec | H7L4V6 | Canada | e02621br1 | 1 | T1 | 0 | 10.136.106.0/25 | 10.207.4.1/26 | 0 | T1
800803 | 378 CITY CENTRE | KITIMAT | British Columbia | V8C 1T6 | Canada | w02640br1 |  | T1 | 0 | 10.136.223.0/25 | 10.43.0.129/26 | 0 | T1
800804 | 35 TALBOT ST W | Leamington | Ontario | N8H1M3 | Canada | c02642br1 | 1 | DSL | 0 | 10.138.31.128/25 | 10.139.42.1/25 | 0 | T1
800805 | 405 Main St | Foam Lake | Saskatchewan | S0A 1A0 | Canada | w02648br5 |  | Other | 0 | 10.136.35.128/25 | 10.19.8.129/26 | 0 | T1
800806 | 807 49th Ave Sw | Calgary | Alberta | T2S 1G8 | Canada | w02649br5 |  | Other | 0 | 10.136.53.128/25 | 10.55.9.1/26 | 0 | T1
800807 | 189 KENT ST W | LINDSAY | Ontario | K9V 5G6 | Canada | c02662br1 |  | 5M | 0 | 10.137.84.0/25 | 10.139.37.1/25 | 0 | T1
800808 | 10 WEBSTER ST | LIONS HEAD | Ontario | N0H1W0 | Canada | c02682br1 |  | T1 | 0 | 10.136.134.0/25 | 10.127.20.1/26 | 0 | T1
800809 | 383 RICHMOND ST 7TH FL | LONDON | Ontario | N6A 3C4 | Canada | c02692cr1 |  | 5M | 0 | 10.136.247.0/25 | 10.143.64.1/24 | 0 | 3M
800812 | 411 58TH AVE SE | CALGARY | Alberta | T2H 0P5 | Canada | w02699br1 |  | 5M | 0 | 10.137.130.0/25 | 10.27.48.1/25 | 0 | T1
800813 | 175 WALLACE AVE N | LISTOWEL | Ontario | N4W1K8 | Canada | c02702br1 |  | T1 | 0 | 10.138.32.0/25 | 10.127.3.129/26 | 0 | T1
800814 | 155 Municipal Rd. 24, Walden Plaza | LIVELY | Ontario | P3Y1J1 | Canada | c02712br1 | 1 | DSL | 0 | 10.138.32.128/25 | 10.139.15.1/26 | 0 | T1
800816 | 383 RICHMOND ST | LONDON | Ontario | N6A 3C4 | Canada | c02722br1 |  | 5M | 0 | 10.137.84.128/25 | 10.143.66.1/24 | 0 | 3M
800820 | 440 BOLER RD | LONDON | Ontario | N6K 4L2 | Canada | c02732br1 |  | 5M | 0 | 10.137.85.0/25 | 10.127.14.129/26 | 0 | 3M
800821 | 85 Main St | Melita | Manitoba | R0M1L0 | Canada | w02737br5 |  | Other | 0 | 10.136.69.128/25 | 10.27.4.1/26 | 0 | T1
800822 | 621 HURON ST W | LONDON | Ontario | N5Y4J7 | Canada | c02752br1 |  | T1 | 0 | 10.136.134.128/25 | 10.147.12.129/26 | 0 | T1
800823 | 3535 ST CHARLES BLVD-SUITE 101 | KIRKLAND | Quebec | H9H 5B9 | Canada | e02755cr1 |  | 5M | 0 | 10.137.52.0/25 | 10.219.49.1/25 | 0 | 3M
800824 | 1670 DUNDAS ST E | LONDON | Ontario | N5W3C7 | Canada | c02762br1 | 1 | T1 | 0 | 10.137.179.0/25 | 10.143.43.1/25 | 0 | T1
800826 | 1530 ADELAIDE ST N | LONDON | Ontario | N5X1K4 | Canada | c02772br1 |  | T1 | 0 | 10.137.182.128/25 | 10.143.9.1/26 | 0 | T1
800827 | 1951 RUE BEAUBIEN E | MONTREAL | Quebec | H2G1M2 | Canada | e02781br1 |  | T1 | 0 | 10.136.168.0/25 | 10.203.0.1/26 | 0 | T1
800828 | 2329 LAKESHORE RD W | OAKVILLE | Ontario | L6L1H2 | Canada | c02782br1 |  | T1 | 0 | 10.136.135.0/25 | 10.19.36.129/25 | 0 | T1
800833 | 5205 Ladner Trunk Road | DELTA | British Columbia | V4K 1W4 | Canada | w02800br1 | 1 | T1 | 0 | 10.136.236.0/25 | 10.79.8.1/25 | 0 | T1
800834 | 7157 120TH ST | DELTA | British Columbia | V4E 2A9 | Canada | w02810br1 |  | 10M | 0 | 10.137.68.128/25 | 10.23.36.1/25 | 0 | 3M
800839 | 527 FIRST AVE | LADYSMITH | British Columbia | V9G1A7 | Canada | w02820br1 | 1 | DSL | 0 | 10.136.9.0/25 | 10.11.3.129/26 | 0 | T1
800846 | 8843 204th St | Langley | British Columbia | V1M2K4 | Canada | w02830br5 | 1 | Other | 0 | 10.136.70.0/25 | 10.23.31.1/25 | 0 | 3M
800850 | 1225 WONDERLAND RD N | LONDON | Ontario | N6G 2V9 | Canada | c02852br1 | 1 | T1 | 0 | 10.137.183.0/25 | 10.151.8.1/26 | 0 | T1
800851 | 2151 BOUL LAPINIERE | Brossard | Quebec | J4W2T5 | Canada | e02857br1 |  | T1 | 0 | 10.136.168.128/25 | 10.219.3.1/26 | 0 | T1
800853 | 1188 Conrad Ave | Gull Lake | Saskatchewan | S0N1A0 | Canada | w02868br5 |  | Other | 0 | 10.136.70.128/25 | 10.19.9.129/26 | 0 | T1
800854 | 8338 18th St Se | Calgary | Alberta | T2C4E4 | Canada | w02869br5 |  | Other | 0 | 10.136.71.0/25 | 10.11.50.1/25 | 0 | T1
800855 | 5001 YONGE ST | North York | Ontario | M2N6P6 | Canada | c02874br1 |  | 5M | 0 | 10.137.85.128/25 | 10.123.47.1/25 | 0 | 3M
800856 | 19888 WILLOWBROOK DR | LANGLEY | British Columbia | V2Y 1K9 | Canada | w02880br1 |  | 10M | 0 | 10.136.29.128/25 | 10.43.72.1/24 | 0 | 3M
800857 | 515 WHARNCLIFFE RD S | LONDON | Ontario | N6J2N1 | Canada | c02882br1 | 1 | T1 | 0 | 10.137.183.128/25 | 10.147.9.129/26 | 0 | T1
800858 | 403 MACKENZIE BLVD | MACKENZIE | British Columbia | V0J2C0 | Canada | w02890br1 |  | T1 | 0 | 10.136.2.0/25 | 10.43.1.129/26 | 0 | T1
800859 | 5755 Cavendish Blvd | Cote Saint-Luc | Quebec | H4W 2X8 | Canada | e02891br5 |  | Other | 0 | 10.136.47.128/25 | 10.199.0.1/26 | 0 | T1
800861 | 20059 40TH AVE | LANGLEY | British Columbia | V3A2W2 | Canada | w02900br1 | 1 | DSL | 0 | 10.138.83.0/25 | 10.23.58.1/25 | 0 | T1
800865 | 11910 207TH ST | MAPLE RIDGE | British Columbia | V2X1X7 | Canada | w02920br1 | 1 | DSL | 0 | 10.138.83.128/25 | 10.11.13.1/26 | 0 | T1
800867 | 5 COMPLEXE DESJARDINS | MONTREAL | Quebec | H5B1B4 | Canada | e02931br1 |  | 5M | 0 |  | 10.207.72.1/24 | 0 | 3M
800870 | 2090 QUILCHENA AVE | MERRITT | British Columbia | V1K1B8 | Canada | w02940br1 |  | T1 | 0 | 10.136.7.0/25 | 10.43.2.129/26 | 0 | T1
800871 | 5700 COTE DES NEIGES | MONTREAL | Quebec | H3T2A6 | Canada | e02941br1 | 1 | T1 | 0 | 10.136.255.128/25 | 10.207.39.1/25 | 0 | 3M
800873 | 75 CROWFOOT WAY NW | CALGARY | Alberta | T3G 2R2 | Canada | w02949br1 |  | 5M | 0 | 10.137.130.128/25 | 10.23.64.1/25 | 0 | 3M
800874 | 6205 AIRPORT RD | MISSISSAUGA | Ontario | L4V 1E1 | Canada | c02952br1 |  | 5M | 0 | 10.137.8.128/25 | 10.147.41.1/25 | 0 | T1
800875 | 1501 Lynn Valley Rd | NORTH VANCOUVER | British Columbia | V7J2B1 | Canada | w02960br5 | 1 | Other | 0 | 10.136.71.128/25 | 10.11.39.1/25 | 0 | T1
800876 | 5539 MAIN ST | MANOTICK | Ontario | K4M1A2 | Canada | e02962br1 | 1 | DSL | 0 |  | 10.219.3.129/26 | 0 | T1
800877 | 2690 MILL BAY RD | MILL BAY | British Columbia | V0R2P1 | Canada | w02970br1 |  | T1 | 0 | 10.136.112.128/25 | 10.63.2.1/26 | 0 | T1
800878 | 1105 WELLINGTON RD S | LONDON | Ontario | N6E1V4 | Canada | c02972br1 | 1 | T1 | 0 | 10.137.184.0/25 | 10.127.47.1/25 | 0 | 3M
800880 | 113 Lincoln St | Hanley | Saskatchewan | S0G2E0 | Canada | w02978br5 |  | Other | 0 | 10.136.72.0/25 | 10.35.1.1/26 | 0 | T1
800881 | 5102 50TH AVE | CAMROSE | Alberta | T4V0S7 | Canada | w02979br1 | 1 | DSL | 0 | 10.136.26.128/25 | 10.23.26.1/25 | 0 | T1
800882 | 47 MAIN ST N | MARKHAM | Ontario | L3P 1X3 | Canada | c02982br1 |  | 5M | 0 | 10.137.86.0/25 | 10.123.37.1/25 | 0 | T1
800886 | 61 Main St | Minnedosa | Manitoba | R0J1E0 | Canada | w02997br5 |  | Other | 0 | 10.136.72.128/25 | 10.31.3.1/26 | 0 | T1
800887 | 195 SAUBLE ST | MASSEY | Ontario | P0P1P0 | Canada | c03002br1 | 1 | DSL | 0 | 10.138.33.0/25 | 10.127.4.129/26 | 0 | T1
800888 | 7481 WOODBINE AVE | MARKHAM | Ontario | L3R 2W1 | Canada | c03012br1 |  | 5M | 0 | 10.137.86.128/25 | 10.147.38.1/25 | 0 | 3M
800894 | 7031 COTE ST LUC RD | MONTREAL | Quebec | H4V 1J2 | Canada | e03021br1 |  | 5M | 0 | 10.137.26.128/25 | 10.191.35.1/25 | 0 | 3M
800895 | 6570 LONGWOODS RD | MELBOURNE | Ontario | N0L1T0 | Canada | c03022br1 |  | T1 | 0 | 10.138.101.0/25 | 10.131.24.1/26 | 0 | T1
800898 | 7205 Goreway Dr | Mississauga | Ontario | L4T 2T9 | Canada | c03032br5 | 1 | Other | 0 | 10.136.40.0/25 | 10.151.37.1/25 | 0 | T1
800899 | 33114 1ST AVE | MISSION | British Columbia | V2V1G4 | Canada | w03040br1 | 1 | T1 | 0 | 10.136.21.0/25 | 10.55.6.129/26 | 0 | T1
800900 | 7945 BOUL MAURICE DUPLESSIS | MONTREAL | Quebec | H1E1M5 | Canada | e03041br1 |  | T1 | 0 | 10.136.106.128/25 | 10.187.35.1/25 | 0 | T1
800901 | 124 MAIN ST E-PO BOX 10 or 124 Main St E | MERRICKVILLE | Ontario | K0G 1N0 | Canada | e03042br1 |  | T1 | 0 | 10.136.169.0/25 | 10.191.7.129/26 | 0 | T1
800903 | 3131 COTE VERTU | ST-LAURENT | Quebec | H4R 1Y8 | Canada | e03051br1 |  | 5M | 0 | 10.138.93.128/25 | 10.191.59.1/25 | 0 | 3M
800905 | 8220 VICTORIA ST | METCALFE | Ontario | K0A2P0 | Canada | e03062br1 |  | T1 | 0 | 10.137.244.128/25 | 10.191.13.1/26 | 0 | T1
800906 | 271 KING ST | MIDLAND | Ontario | L4R 3M4 | Canada | c03082br1 |  | 5M | 0 | 10.137.87.0/25 | 10.131.10.129/25 | 0 | T1
800908 | 204 MAIN ST | CARDSTON | Alberta | T0K0K0 | Canada | w03089br1 |  | T1 | 0 | 10.136.197.0/25 | 10.19.10.129/26 | 0 | T1
800911 | 55 ONTARIO ST S | MILTON | Ontario | L9T 2M3 | Canada | c03092br1 |  | 5M | 0 | 10.137.87.128/25 | 10.135.57.1/25 | 0 | 3M
800912 | 1125 BLOOR ST E | Mississauga | Ontario | L4Y2N6 | Canada | c03102br1 |  | T1 | 0 | 10.137.184.128/25 | 10.147.7.129/25 | 0 | T1
800913 | 447 Leclerc St. | Repentigny | Quebec | J6A8J4 | Canada | e03111br1 | 1 | T1 | 0 | 10.137.210.128/25 | 10.187.45.1/25 | 0 | 3M
800915 | 205 COMMERCIAL ST | NANAIMO | British Columbia | V9R 5G8 | Canada | w03120br1 |  | 5M | 0 | 10.137.131.0/25 | 10.67.72.1/24 | 0 | 3M
800917 | 46 MCGIVERN ST | MOOREFIELD | Ontario | N0G2K0 | Canada | c03122br1 |  | T1 | 0 | 10.136.238.0/25 | 10.151.12.1/26 | 0 | T1
800918 | 33 CITY CENTRE DR | Mississauga | Ontario | L5B2N5 | Canada | c03132cr1 |  | 5M | #N/A | 10.137.49.128/25 | #N/A | #N/A | 3M
800920 | 22466 ADELAIDE RD | MOUNT BRYDGES | Ontario | N0L1W0 | Canada | c03142br1 | 1 | DSL | 0 | 10.138.33.128/25 | 10.131.2.129/26 | 0 | T1
800922 | 2000 ISLAND HWY N | NANAIMO | British Columbia | V9S5W3 | Canada | w03160br1 |  | 5M | 0 | 10.137.245.0/25 | 10.27.35.1/25 | 0 | T1
800928 | 4751 STEELES AVE E | SCARBOROUGH | Ontario | M1V4S5 | Canada | c03172br1 |  | 5M | 0 | 10.137.88.0/25 | 10.155.70.1/24 | 0 | 5M
800929 | 703 MAIN ST | HUMBOLDT | Saskatchewan | S0K2A0 | Canada | w03178br1 |  | 5M | 0 | 10.138.114.128/25 | 10.35.1.129/26 | 0 | T1
800930 | 49 6631 ISLAND HWY N Suite 49 | NANAIMO | British Columbia | V9T 4T7 | Canada | w03180br1 |  | 5M | 0 | 10.137.131.128/25 | 10.23.47.1/25 | 0 | 3M
800931 | 36 DUNDAS ST E | NAPANEE | Ontario | K7R 1H8 | Canada | c03182br1 | 1 | DSL | 0 | 10.137.244.0/25 | 10.131.5.129/26 | 0 | T1
800934 | 300 Royal St | Imperial | Saskatchewan | S0G2J0 | Canada | w03198br5 |  | Other | 0 | 10.136.73.0/25 | 10.63.1.129/26 | 0 | T1
800935 | 130 1ST AVE W | COCHRANE | Alberta | T4C1A5 | Canada | w03199br1 | 1 | DSL | 0 | 10.136.19.0/25 | 10.31.44.1/25 | 0 | T1
800936 | 401 Baker St | Nelson | British Columbia | V1L 4H7 | Canada | w03200br5 | 1 | Other | 0 | 10.136.73.128/25 | 10.63.42.1/25 | 0 | T1
800937 | 3435 TRIM RD | NAVAN | Ontario | K4B 1M8 | Canada | e03202br1 | 1 | DSL | 0 | 10.136.169.128/25 | 10.191.8.129/26 | 0 | T1
800938 | 2560 DE SALABERRY ST | MONTREAL | Quebec | H3M 1L3 | Canada | e03221br1 |  | 5M | 0 | 10.137.115.128/25 | 10.207.48.1/25 | 0 | 3M
800948 | 4141 DIXIE RD | MISSISSAUGA | Ontario | L4W 1V5 | Canada | c03232cr1 |  | 5M | 0 | 10.137.160.128/25 | 10.147.42.1/25 | 0 | T1
800950 | 6240 DIXIE RD | MISSISSAUGA | Ontario | L5T 1A6 | Canada | c03252br1 |  | 5M | 0 | 10.137.88.128/25 | 10.147.36.1/25 | 0 | 3M
800951 | 289 STEPHEN ST | MORDEN | Manitoba | R6M 1V2 | Canada | w03257br1 |  | 5M | 0 | 10.138.119.128/25 | 10.31.2.1/26 | 0 | T1
800952 | 22886 HAGERTY RD | NEWBURY | Ontario | N0L1Z0 | Canada | c03262br1 |  | T1 | 0 | 10.136.251.128/25 | 10.131.3.129/26 | 0 | T1
800953 | 101 DAVIDSON ST-PO BOX 1236 | NEEPAWA | Manitoba | R0J 1H0 | Canada | w03277br1 |  | T1 | 0 | 10.136.197.128/25 | 10.27.3.1/26 | 0 | T1
800954 | 626 6TH AVE | NEW WESTMINSTER | British Columbia | V3M 6Z2 | Canada | w03280br1 |  | 10M | 0 | 10.137.69.0/25 | 10.63.70.1/24 | 0 | 3M
800955 | 29 HURON ST | NEW HAMBURG | Ontario | N3A 1K1 | Canada | c03282br1 |  | T1 | 0 | 10.138.34.0/25 | 10.147.8.129/26 | 0 | T1
800956 | 5 ARMSTRONG ST | NEW LISKEARD | Ontario | P0J1P0 | Canada | c03302br1 |  | T1 | 0 | 10.137.185.0/25 | 10.131.12.129/26 | 0 | T1
800957 | 6390 Quinpool Rd | HALIFAX | Nova Scotia | B3L 4N2 | Canada | e03303br1 |  | 5M | 10.199.49.1/25 |  | 10.199.42.1/25 | 0 | T1
800966 | 501 Grand Ave | Indian Head | Saskatchewan | S0G 2K0 | Canada | w03308br5 |  | Other | 0 | 10.136.74.0/25 | 10.19.0.129/26 | 0 | T1
800967 | 5003 50TH ST | CONSORT | Alberta | T0C1B0 | Canada | w03309br1 |  | T1 | 0 | 10.136.198.0/25 | 10.23.5.1/26 | 0 | T1
800972 | 1181 DAVIS DR E | NEWMARKET | Ontario | L3Y 8R1 | Canada | c03322br1 |  | 5M | 0 | 10.137.9.0/25 | 10.131.37.1/25 | 0 | T1
800978 | 17770 YONGE ST | NEWMARKET | Ontario | L3Y 8P4 | Canada | c03342br1 |  | 3M | 0 | 10.137.181.128/25 | 10.131.38.1/25 | 0 | 3M
800980 | 7001 MUMFORD RD | HALIFAX | Nova Scotia | B3L2H8 | Canada | e03353br1 | 1 | T1 | 0 | 10.136.107.0/25 | 10.199.43.1/25 | 0 | 3M
800982 | 4491 QUEEN ST | NIAGARA FALLS | Ontario | L2E 2L4 | Canada | c03362br1 | 1 | T1 | 0 | 10.136.135.128/25 | 10.155.36.1/25 | 0 | T1
800985 | 4557 HURONTARIO ST-UNIT B2 | MISSISSAUGA | Ontario | L4Z 3M2 | Canada | c03372cr1 |  | 5M | 0 | 10.137.50.0/25 | 10.151.7.129/25 | 0 | T1
800988 | 6518 LUNDY`S LANE | NIAGARA FALLS | Ontario | L2G1T6 | Canada | c03382br1 | 1 | T1 | 0 | 10.137.185.128/25 | 10.155.2.129/26 | 0 | T1
800989 | 3499 PORTAGE RD | NIAGARA FALLS | Ontario | L2J2K5 | Canada | c03392br1 |  | 5M | 0 | 10.137.89.0/25 | 10.135.1.1/26 | 0 | T1
800995 | 43 RUE ST CHARLES ST W | LONGUEUIL | Quebec | J4H1C5 | Canada | e03411br1 |  | 5M | 0 | 10.138.14.128/25 | 10.203.76.1/24 | 0 | T1
800996 | 234 MARY ST | Niagara on the Lake | Ontario | L0S1J0 | Canada | c03412br1 | 1 | DSL | 0 | 10.138.34.128/25 | 10.135.2.1/26 | 0 | T1
800997 | 5855 Spring Garden Rd | Halifax | Nova Scotia | B3H 4S2 | Canada | e03413br5 | 1 | Other | 0 | 10.136.48.0/25 | 10.199.44.1/25 | 0 | 3M
800998 | 218 Main St N | Invermay | Saskatchewan | S0A1M0 | Canada | w03418br5 |  | Other | 0 | 10.138.130.0/25 | 10.19.17.1/26 | 0 | T1
800999 | 39 ATHABASCA AVE | DEVON | Alberta | T9G1G5 | Canada | w03419br1 |  | T1 | 0 | 10.136.113.0/25 | 10.31.4.1/26 | 0 | T1
801003 | 157 RAILWAY ST | NIPIGON | Ontario | P0T2J0 | Canada | w03422br1 | 1 | DSL | 0 | 10.138.84.0/25 | 10.19.11.129/26 | 0 | T1
801005 | 105 MAIN ST W | North Bay | Ontario | P1B 2T6 | Canada | c03442br1 |  | T1 | 0 | 10.137.186.0/25 | 10.139.40.1/25 | 0 | T1
801006 | 7191 NEWMAN BLVD | Lasalle | Quebec | H8N2K3 | Canada | e03451br1 | 1 | T1 | 0 | 10.137.211.0/25 | 10.215.38.1/25 | 0 | T1
801008 | 925 STOCKDALE RD-MAIN FLR | NORTH BAY | Ontario | P1B 9N5 | Canada | c03452br1 |  | 5M | 0 | 10.137.89.128/25 | 10.123.43.1/25 | 0 | T1
801010 | 5100 RUE SHERBROOKE E, RC 10 | MONTREAL | Quebec | H1V3R9 | Canada | e03461br1 | 1 | T1 | 0 | 10.137.0.0/25 | 10.187.0.1/26 | 0 | T1
801011 | 6683 FOURTH LINE RD- | NORTH GOWER | Ontario | K0A 2T0 | Canada | e03462br1 |  | 5M | 0 | 10.137.116.0/25 | 10.191.15.129/26 | 0 | T1
801013 | 2369 County Rd. 45 | Norwood | Ontario | K0L2V0 | Canada | c03482br1 |  | T1 | 0 | 10.136.136.0/25 | 10.151.13.129/26 | 0 | T1
801015 | 50 OCONNOR ST | OTTAWA | Ontario | K1P 6L2 | Canada | e03497sr1 |  | 5M | 0 | 10.137.169.128/25 | 10.193.88.1/24 | 0 | T1
801016 | 279 Lakeshore Rd E | OAKVILLE | Ontario | L6J 1H9 | Canada | c03502cr1 |  | 10M | 0 | 10.137.67.0/25 | 10.143.41.1/25 | 0 | 3M
801018 | 68 Railway Ave | Pierson | Manitoba | R0M 1S0 | Canada | w03517br5 |  | Other | 0 | 10.136.74.128/25 | 10.27.8.129/26 | 0 | T1
801019 | 789 FORTUNE DR | Kamloops | British Columbia | V2B2L3 | Canada | w03520br1 | 1 | DSL | 0 | 10.138.84.128/25 | 10.55.45.1/25 | 0 | T1
801020 | 15794 CENTRAL AVE | Inverness | Nova Scotia | B0E1N0 | Canada | e03523br1 | 1 | DSL | 0 | 10.138.64.128/25 | 10.183.14.1/26 | 0 | T1
801021 | 503 Main St | Ituna | Saskatchewan | S0A 1N0 | Canada | w03528br5 |  | Other | 0 | 10.136.75.0/25 | 10.35.6.129/26 | 0 | T1
801022 | 1911 20TH ST | DIDSBURY | Alberta | T0M0W0 | Canada | w03529br1 | 1 | DSL | 0 | 10.136.17.128/25 | 10.19.12.129/26 | 0 | T1
801025 | 147 HWY #2 (147 Main) | ODESSA | Ontario | K0H2H0 | Canada | c03542br1 | 1 | DSL | 0 | 10.138.87.128/25 | 10.139.12.129/26 | 0 | T1
801027 | 7151 JEAN TALON ST E-8TH FLR | ANJOU | Quebec | H1M 3N8 | Canada | e03561br1 |  | 5M | 0 | 10.137.27.0/25 | 10.203.35.1/25 | 0 | 3M
801028 | 136 BROADWAY Ave | ORANGEVILLE | Ontario | L9W 1J9 | Canada | c03562br1 |  | 5M | 0 | 10.137.90.0/25 | 10.127.42.1/25 | 0 | T1
801030 | 40 PETER ST S | ORILLIA | Ontario | L3V5B1 | Canada | c03582br1 | 1 | DSL | 0 | 10.138.35.0/25 | 10.155.40.1/25 | 0 | T1
801034 | 1005 SPEERS RD , OAKVILLE , ON, L6L 2X5 | OAKVILLE | Ontario | L6L 2X5 | Canada | c03592br1 |  | 5M | 0 | 10.137.239.0/25 | 10.127.15.129/25 | 0 | 3M
801041 | 9490 120TH ST | SURREY | British Columbia | V3V 4B9 | Canada | w03600br1 |  | 5M | 0 | 10.136.31.0/25 | 10.67.36.1/25 | 0 | 3M
801043 | 10470 152 ST-UNIT 150 | SURREY | British Columbia | V3R 0Y3 | Canada | w03610br1 |  | 5M | 0 | 10.137.132.0/25 | 10.11.40.1/25 | 0 | 3M
801046 | 15988 FRASER HWY-STE 307 | SURREY | British Columbia | V4N 0X8 | Canada | w03620br1 |  | 5M | 0 | 10.137.132.128/25 | 10.79.0.129/26 | 0 | T1
801047 | 27 SIMCOE ST N | OSHAWA | Ontario | L1G4R7 | Canada | c03622br1 | 1 | T1 | 0 | 10.136.136.128/25 | 10.127.49.1/25 | 0 | T1
801049 | 5455 152nd St. | SURREY | British Columbia | V3S5A5 | Canada | w03630cr1 |  | 5M | 0 | 10.137.167.0/25 | 10.43.52.1/25 | 0 | 3M
801050 | 300 LEO PARISEAU | MONTREAL | Quebec | H2X4B3 | Canada | e03631br1 |  | 5M | 0 | 10.138.94.0/25 | 10.187.41.1/25 | 0 | T1
801051 | 549 King St E | OSHAWA | Ontario | L1H1G3 | Canada | c03632br1 | 1 | T1 | 0 | 10.137.239.128/25 | 10.155.9.129/26 | 0 | T1
801052 | 63 WEBSTER ST | KENTVILLE | Nova Scotia | B4N 1H4 | Canada | e03633br1 | 1 | T1 | 0 | 10.137.27.128/25 | 10.199.37.1/25 | 0 | T1
801054 | 446 Pacific St | Kerrobert | Saskatchewan | S0L 1R0 | Canada | w03638br5 |  | Other | 0 | 10.136.75.128/25 | 10.19.13.129/26 | 0 | T1
801055 | 5001 51ST AVE | DRAYTON VALLEY | Alberta | T7A1R9 | Canada | w03639br1 | 1 | DSL | 0 | 10.136.12.128/25 | 10.43.0.1/26 | 0 | T1
801056 | 202 MAIN ST E | OTTERVILLE | Ontario | N0J1R0 | Canada | c03642br1 | 1 | DSL | 0 | 10.138.35.128/25 | 10.131.1.65/26 | 0 | T1
801057 | 1 LINDEN ST-PO BOX 189 | PINE FALLS | Manitoba | R0E 1M0 | Canada | w03647br1 |  | 5M | 0 | 10.138.120.0/25 | 10.55.3.129/25 | 0 | T1
801058 | 110 3RD AVE W | DRUMHELLER | Alberta | T0J0Y0 | Canada | w03649br1 | 1 | DSL | 0 | 10.136.29.0/25 | 10.43.1.1/26 | 0 | T1
801061 | 790 Sackville Dr. | LOWER SACKVILLE | Nova Scotia | B4E1R7 | Canada | e03653br1 |  | 5M | 0 | 10.138.65.0/25 | 10.179.41.1/25 | 0 | T1
801063 | 120 2nd St | Langenburg | Saskatchewan | S0A 2A0 | Canada | w03658br5 |  | Other | 0 | 10.136.36.0/25 | 10.19.15.129/26 | 0 | T1
801067 | 351 LAURIER AVE W | MONTREAL | Quebec | H2V 2K4 | Canada | e03661br1 |  | 5M | 0 | 10.137.28.0/25 | 10.219.38.1/25 | 0 | 3M
801069 | 900 2ND AVE E | OWEN SOUND | Ontario | N4K5P5 | Canada | c03662br1 | 1 | DSL | 0 | 10.138.36.0/25 | 10.155.16.1/26 | 0 | T1
801070 | 401 MAIN ST | KINDERSLEY | Saskatchewan | S0L1S0 | Canada | w03668br1 | 1 | T1 | 0 | 10.136.4.128/25 | 10.31.11.1/26 | 0 | T1
801071 | 1050 SIMCOE ST N | OSHAWA | Ontario | L1G4W5 | Canada | c03672br1 | 1 | T1 | 0 | 10.136.137.0/25 | 10.155.9.1/26 | 0 | T1
801072 | 10201 KING GEORGE BLVD | SURREY | British Columbia | V3T 2W6 | Canada | w03680br1 |  | 5M | 0 | 10.137.133.0/25 | 10.63.36.1/25 | 0 | 3M
801073 | 574 QUEEN ST W | PAISLEY | Ontario | N0G2N0 | Canada | c03682br1 |  | T1 | 0 | 10.138.101.128/25 | 10.127.6.129/25 | 0 | T1
801075 | 1405 KING ST E | COURTICE | Ontario | L1E2J6 | Canada | c03692br1 | 1 | T1 | 0 | 10.136.137.128/25 | 10.155.39.1/25 | 0 | T1
801078 | 2534 GRAHAM ST | PAKENHAM | Ontario | K0A2X0 | Canada | e03702br1 | 1 | DSL | 0 | 10.138.65.128/25 | 10.191.14.1/26 | 0 | T1
801080 | 3435 B PETAWAWA BLVD | PETAWAWA | Ontario | K8H1X4 | Canada | e03710br1 | 1 | DSL | 0 | 10.138.88.0/25 | 10.179.13.129/26 | 0 | T1
801082 | 48 PEMBROKE ST W | PEMBROKE | Ontario | K8A 5M6 | Canada | e03722cr1 |  | 5M | 0 | 10.137.163.0/25 | 10.191.50.1/25 | 10.191.50.129/25 | T1
801085 | 70 JOSEPH ST | PARRY SOUND | Ontario | P2A2G5 | Canada | c03732br1 | 1 | DSL | 0 | 10.138.36.128/25 | 10.131.2.1/26 | 0 | 3M
801087 | 6505 JEANNE D`ARC BLVD | Orleans | Ontario | K1C2R1 | Canada | e03742br1 | 1 | DSL | 0 | 10.136.170.0/25 | 10.191.10.1/26 | 0 | T1
801095 | 40 DOWNING DR W-UNIT 5 | LANIGAN | Saskatchewan | S0K2M0 | Canada | w03748br1 |  | T1 | 0 | 10.136.198.128/25 | 10.35.2.1/26 | 0 | T1
801096 | 10107 JASPER AVE NW | EDMONTON | Alberta | T5J 1W9 | Canada | w03749br1 |  | 5M | 0 | 10.137.133.128/25 | 10.27.74.1/24 | 0 | 3M
801097 | 806 CHEMONG RD | PETERBOROUGH | Ontario | K9H5Z6 | Canada | c03752br1 |  | T1 | 0 | 10.137.186.128/25 | 10.139.36.1/25 | 0 | T1
801098 | 111 VERMILLION RD | WINNIPEG | Manitoba | R2J4A9 | Canada | w03757br1 |  | T1 | 0 | 10.137.224.0/25 | 10.11.37.1/25 | 0 | T1
801099 | 44 GORE ST E | PERTH | Ontario | K7H1H7 | Canada | e03762br1 | 1 | DSL | 0 | 10.138.66.0/25 | 10.191.44.1/25 | 0 | T1
801100 | Peguis First Nations | Peguis | Manitoba | R0C 3J0 | Canada | w03767br5 |  | Other | 0 | 10.136.76.0/25 | 10.31.7.129/25 | 0 | T1
801102 | 140 Saskatchewan Ave E | Portage La Prairie | Manitoba | R1N 0L1 | Canada | w03777br5 |  | Other | 0 | 10.136.76.128/25 | 10.79.3.129/26 | 0 | T1
801103 | 10117 JASPER AVE | Edmonton | Alberta | T5J1W8 | Canada | w03779cr1 |  | 10M | 0 | 10.136.31.128/25 | 10.19.43.1/24 | 0 | T1
801104 | 401 GEORGE ST N | PETERBOROUGH | Ontario | K9H3R4 | Canada | c03782br1 |  | 5M | 0 | 10.136.241.128/25 | 10.151.40.1/25 | 0 | T1
801114 | 861 LANSDOWNE ST W | PETERBOROUGH | Ontario | K9J 1Z5 | Canada | c03802br1 |  | 5M | 10.32.137.1/25 |  | 10.22.19.1/24 | 0 | T1
801118 | 295 WATER ST | Plantagenet | Ontario | K0B1L0 | Canada | e03822br1 | 1 | DSL | 0 | 10.138.66.128/25 | 10.191.13.129/26 | 0 | T1
801120 | 1340 KINGSTON RD | PICKERING | Ontario | L1V 3M9 | Canada | c03832br1 |  | 5M | 0 | 10.137.91.0/25 | 10.123.45.1/25 | 0 | 3M
801122 | 3145 Edgemont Blvd | NORTH VANCOUVER | British Columbia | V7R 2N7 | Canada | w03840br1 |  | 5M | 0 | 10.136.77.0/25 | 10.23.40.1/25 | 0 | T1
801124 | 2600 Arthur Street East | THUNDER BAY | Ontario | P7E5P4 | Canada | w03852br1 |  | 5M | 0 | 10.137.134.0/25 | 10.43.12.1/26 | 0 | T1
801135 | 449 Hodder Ave | Thunder Bay | Ontario | P7A 1V2 | Canada | w03862br5 |  | Other | 0 | 10.136.77.128/25 | 0 | 0 | T1
801136 | 15735 97 St. NW. | EDMONTON | Alberta | T5X 0C7 | Canada | w03869br1 |  | T1 | 0 | 10.137.224.128/25 | 10.11.16.129/26 | 0 | T1
801137 | 640 River St | Thunder Bay | Ontario | P7A 3S4 | Canada | w03872br5 |  | Other | 0 | 10.136.78.0/25 | 10.79.43.1/25 | 0 | T1
801138 | 8171 Ackroyd Rd | Richmond | British Columbia | V6X 3K1 | Canada | w03880br5 | 1 | Other | 0 | 10.136.78.128/25 | 10.43.40.1/25 | 0 | 3M
801139 | 59 CLARENCE ST | PORT COLBORNE | Ontario | L3K 3G1 | Canada | c03882br1 |  | 5M | 0 | 10.137.91.128/25 | 10.155.3.1/26 | 0 | T1
801149 | 5701 MONKLAND AVENUE | MONTREAL | Quebec | H4A1E7 | Canada | e03901br1 |  | T1 | 0 | 10.136.170.128/25 | 10.215.39.1/25 | 0 | T1
801150 | 308 MAIN ST | PORT DOVER | Ontario | N0A 1N0 | Canada | c03902br1 |  | 5M | 0 | 10.137.92.0/25 | 10.131.13.129/26 | 0 | T1
801155 | 477 North Dollarton Hwy | NORTH VANCOUVER | British Columbia | V7G 1M9 | Canada | w03920br5 | 1 | Other | 0 | 10.136.79.0/25 | 10.11.1.129/26 | 0 | T1
801156 | 85 WALTON ST | PORT HOPE | Ontario | L1A1N4 | Canada | c03922br1 | 1 | DSL | 0 | 10.138.37.0/25 | 10.127.11.1/26 | 0 | T1
801160 | 4352 ST CLAIR PKWY | PORT LAMBTON | Ontario | N0P2B0 | Canada | c03942br1 |  | T1 | 0 | 10.138.102.0/25 | 10.127.20.129/26 | 0 | T1
801161 | 987 GORDON ST | GUELPH | Ontario | N1G4W3 | Canada | c03956br1 |  | T1 | 0 | 10.137.187.0/25 | 10.151.2.1/25 | 0 | T1
801162 | 210 QUEEN ST | PORT PERRY | Ontario | L9L1B9 | Canada | c03962br1 | 1 | DSL | 0 | 10.138.37.128/25 | 10.147.46.1/25 | 0 | T1
801163 | 209 MAIN ST | LIVERPOOL | Nova Scotia | B0T1K0 | Canada | e03963br1 | 1 | DSL | 0 | 10.138.67.0/25 | 10.183.15.1/26 | 0 | T1
801164 | 332 Main St | Lemberg | Saskatchewan | S0A 2B0 | Canada | w03968br1 |  | T1 | 0 |  | 10.19.18.1/26 | 0 | T1
801165 | 32 COLBORNE ST | PORTLAND | Ontario | K0G1V0 | Canada | e03972br1 |  | T1 | 0 | 10.136.171.0/25 | 10.183.15.129/26 | 0 | T1
801166 | 1801 MONT-ROYAL AVE E | MONTREAL | Quebec | H2H1J2 | Canada | e03981br1 | 1 | T1 | 0 | 10.137.28.128/25 | 10.187.47.1/25 | 0 | 3M
801167 | 302 KING ST W | Prescott | Ontario | K0E1T0 | Canada | e03982br1 | 1 | DSL | 0 | 10.138.67.128/25 | 10.179.11.129/26 | 0 | T1
801168 | 1789 LONSDALE AVE | NORTH VANCOUVER | British Columbia | V7M 2J6 | Canada | w04000br1 |  | 10M | 0 | 10.136.30.0/25 | 10.67.70.1/24 | 0 | 3M
801169 | 637 King St E | Cambridge | Ontario | N3H 3N7 | Canada | c04002br5 |  | Other | 0 | 10.136.40.128/25 | 10.135.1.129/25 | 0 | T1
801173 | 182 RAGLAN ST S | RENFREW | Ontario | K7V1R1 | Canada | e04022br1 | 1 | DSL | 0 | 10.138.68.0/25 | 10.191.6.1/26 | 0 | T1
801174 | 15420 BAYVIEW AVE UNIT #1 BUILDING C | Aurora | Ontario | L4G7J1 | Canada | c04030br1 |  | T1 | 0 | 10.137.187.128/25 | 10.167.1.1/26 | 0 | T1
801183 | 11000 YONGE ST-BLDG A | RICHMOND HILL | Ontario | L4C 3E4 | Canada | c04062br1 |  | 5M | 0 | 10.137.9.128/25 | 10.123.38.1/25 | 0 | 3M
801184 | 25A BEECH ST | LOCKEPORT | Nova Scotia | B0T1L0 | Canada | e04073br1 |  | T1 | 0 | 10.136.171.128/25 | 10.191.9.1/26 | 0 | T1
801185 | 6306 MAIN ST-PO BOX 519 | OLIVER | British Columbia | V0H1T0 | Canada | w04080br1 | 1 | DSL | 0 | 10.136.3.128/25 | 10.43.2.1/26 | 0 | T1
801186 | 1 MAIN ST E | RIDGETOWN | Ontario | N0P2C0 | Canada | c04082br1 | 1 | DSL | 0 | 10.138.38.0/25 | 10.123.2.1/26 | 0 | T1
801187 | 11010 23RD AVE NW | EDMONTON | Alberta | T6J 7J7 | Canada | w04089br1 | 1 | T1 | 0 | 10.137.225.0/25 | 10.63.39.1/25 | 0 | T1
801189 | 385 RIDGE RD-PO BOX 429 | RIDGEWAY | Ontario | L0S 1N0 | Canada | c04102br1 |  | 5M | 0 | 10.137.10.0/25 | 10.135.7.129/26 | 0 | T1
801190 | 2864 LAURIER ST | ROCKLAND | Ontario | K4K1L7 | Canada | e04104br1 | 1 | DSL | 0 | 10.138.68.128/25 | 10.191.14.129/26 | 0 | T1
801191 | 200 BIRCH AVE | 100 MILE HOUSE | British Columbia | V0K2E0 | Canada | w04120br1 | 1 | DSL | 0 | 10.138.85.0/25 | 10.35.43.1/25 | 0 | T1
801192 | 41 QUEEN ST-PO BOX 160 | RIPLEY | Ontario | N0G 2R0 | Canada | c04122br1 |  | T1 | 0 | 10.136.252.0/25 | 10.127.7.129/26 | 0 | T1
801193 | 152 SOUTH ALBERNI HWY | PARKSVILLE | British Columbia | V9P 2G5 | Canada | w04130cr1 |  | 5M | 0 | 10.137.167.128/25 | 10.23.48.1/25 | 10.23.48.129/25 | 3M
801194 | 118 MAIN ST-PO BOX 30 | ROCKWOOD | Ontario | N0B 2K0 | Canada | c04142br1 | 1 | DSL | 0 | 10.138.38.128/25 | 10.151.3.129/25 | 0 | T1
801197 | 302 MAIN ST | PENTICTON | British Columbia | V2A5C3 | Canada | w04160br1 | 1 | T1 | 0 | 10.137.225.128/25 | 10.23.27.1/25 | 0 | T1
801198 | 244 FURNIVAL RD | RODNEY | Ontario | N0L2C0 | Canada | c04162br1 | 1 | DSL | 0 | 10.138.39.0/25 | 10.127.8.129/26 | 0 | T1
801199 | 179 Main St W | Roblin | Manitoba | R0L 1P0 | Canada | w04167br5 |  | Other | 0 | 10.136.79.128/25 | 10.63.4.129/26 | 0 | T1
801200 | 490 RUE CAMBRONNE | BEAUPORT | Quebec | G1E6X1 | Canada | e04175br1 |  | 5M | 0 | 10.137.211.128/25 | 10.203.43.1/25 | 0 | T1
801201 | 1848 Main St. | PENTICTON | British Columbia | V2A5H3 | Canada | w04180br1 | 1 | T1 | 0 | 10.136.199.0/25 | 10.63.12.129/26 | 0 | T1
801203 | 7509 MAIN ST | LOUISBOURG | Nova Scotia | B1C1H8 | Canada | e04183br1 |  | T1 | 0 | 10.138.69.0/25 | 10.183.16.129/26 | 0 | T1
801204 | 2828 BOUL LAURIER-SUITE 600 | QUEBEC | Quebec | G1V 0B9 | Canada | e04194br1 |  | 5M | 0 | 10.137.29.0/25 | 10.207.8.129/25 | 0 | T1
801205 | 545 RYMAL RD E | HAMILTON | Ontario | L8W 0A6 | Canada | c04202br1 |  | 5M | 0 | 10.137.92.128/25 | 10.151.15.1/26 | 0 | T1
801208 | 14155 23 Ave. | Edmonton | Alberta | T6R0G4 | Canada | w04219br1 | 1 | T1 | 0 | 10.137.226.0/25 | 10.11.54.1/25 | 0 | T1
801209 | 80 KING ST-SUITE 1 | ST CATHARINES | Ontario | L2R 7G1 | Canada | c04222br1 |  | 5M | 0 | 10.137.10.128/25 | 10.151.62.1/24 | 0 | 3M
801213 | 4716 50TH AVE | LLOYDMINSTER | Alberta | T9V 0W4 | Canada | w04238cr1 |  | 5M | 0 | 10.137.168.0/25 | 10.41.138.1/24 | 0 | 3M
801214 | 2925 3RD AVE | PORT ALBERNI | British Columbia | V9Y2A6 | Canada | w04240br1 | 1 | DSL | 0 | 10.136.1.0/25 | 10.31.36.1/25 | 0 | T1
801215 | 380 Scott St | ST CATHARINES | Ontario | L2M 3W4 | Canada | c04242br5 | 1 | Other | 0 | 10.136.101.0/25 | 10.155.41.1/25 | 0 | 3M
801216 | 344 Glendale Ave | ST CATHARINES | Ontario | L2T 4E3 | Canada | c04252br1 |  | 5M | 10.33.2.193/26 |  | 10.147.55.1/25 | 0 | T1
801217 | 133 QUEEN ST E | ST MARYS | Ontario | N4X 1B3 | Canada | c04262br1 |  | T1 | 0 | 10.138.39.128/25 | 10.135.46.1/25 | 0 | T1
801220 | 367 TALBOT ST | ST THOMAS | Ontario | N5P1B7 | Canada | c04282br1 | 1 | DSL | 0 | 10.138.40.0/25 | 10.139.6.129/26 | 0 | T1
801227 | 84 PELHAM ST | Lunenburg | Nova Scotia | B0J2C0 | Canada | e04293br1 | 1 | DSL | 0 | 10.138.69.128/25 | 10.183.16.1/26 | 0 | T1
801228 | 325 JAMES ST N | LUMSDEN | Saskatchewan | S0G3C0 | Canada | w04298br1 |  | T1 | 0 | 10.136.199.128/25 | 10.19.16.129/26 | 0 | T1
801239 | 1099 TALBOT ST E | ST THOMAS | Ontario | N5P 1G4 | Canada | c04302br1 |  | 5M | 0 | 10.137.93.0/25 | 10.127.46.1/25 | 0 | 3M
801240 | 1349 LONDON RD | SARNIA | Ontario | N7S1P6 | Canada | c04312br1 |  | T1 | 0 | 10.136.138.0/25 | 10.139.7.1/26 | 0 | T1
801246 | 2581 SHAUGHNESSY ST | Port Coquitlam | British Columbia | V3C3G3 | Canada | w04320br1 | 1 | T1 | 0 | 10.137.226.128/25 | 10.79.44.1/25 | 0 | T1
801247 | 230 N CHRISTINA ST | SARNIA | Ontario | N7T 5V2 | Canada | c04322br1 |  | 5M | 0 | 10.137.93.128/25 | 10.131.41.1/25 | 0 | 3M
801248 | 15710 87TH AVE NW | Edmonton | Alberta | T5R5W9 | Canada | w04329br1 | 1 | T1 | 0 | 10.137.227.0/25 | 10.23.67.1/25 | 0 | T1
801249 | 3361 COAST MERIDIAN RD | Port Coquitlam | British Columbia | V3B3N6 | Canada | w04330br1 | 1 | T1 | 0 | 10.137.227.128/25 | 10.23.1.1/26 | 0 | T1
801252 | 1125 LAKESHORE RD | SARNIA | Ontario | N7V2V5 | Canada | c04342br1 | 1 | DSL | 0 | 10.138.40.128/25 | 10.135.4.129/26 | 0 | T1
801254 | 2633 66 ST NW | EDMONTON | Alberta | T6K 4E8 | Canada | w04349br1 |  | 5M | 0 | 10.137.134.128/25 | 10.31.45.1/25 | 0 | 3M
801255 | 500 HAZELDEAN RD | KANATA | Ontario | K2L2B5 | Canada | e04356cr1 |  | 5M | 0 | 10.137.163.128/25 | 10.179.2.1/25 | 0 | 3M
801256 | 5015 111th St | Edmonton | Alberta | T6H 4M6 | Canada | w04359br5 | 1 | Other | 0 | 10.136.80.128/25 | 10.67.48.1/25 | 0 | 3M
801259 | 602 QUEEN ST E | SAULT STE MARIE | Ontario | P6A 2A4 | Canada | c04362br1 |  | 5M | 0 | 10.137.94.0/25 | 10.135.50.1/25 | 0 | 3M
801261 | 311 DUNDAS ST S | CAMBRIDGE | Ontario | N1T1P8 | Canada | c04366br1 |  | T1 | 0 | 10.137.188.0/25 | 10.151.2.129/25 | 0 | T1
801264 | 312 2ND LINE W | SAULT STE MARIE | Ontario | P6C2J5 | Canada | c04392br1 |  | T1 | 0 | 10.136.138.128/25 | 10.131.6.129/26 | 0 | T1
801271 | 218 Newport Dr | Port Moody | British Columbia | V3H 5B9 | Canada | w04400br5 | 1 | Other | 0 | 10.136.81.0/25 | 10.79.0.1/26 | 0 | T1
801272 | 405 Grand Ave | Luseland | Saskatchewan | S0L2A0 | Canada | w04408br5 |  | Other | 0 | 10.138.130.128/25 | 10.19.5.129/26 | 0 | T1
801273 | 150A 82ND AVE & 83RD ST | EDMONTON | Alberta | T6C 4E3 | Canada | w04409cr1 |  | 5M | 0 | 10.137.52.128/25 | 10.31.46.1/25 | 10.31.46.129/25 | 3M
801288 | 181 MAIN ST N | RUSSELL | Manitoba | R0J 1W0 | Canada | w04427br1 |  | T1 | 0 | 10.136.221.128/25 | 10.55.5.129/26 | 0 | T1
801292 | 1496 WELLINGTON ST E | SAULT STE MARIE | Ontario | P6A2R1 | Canada | c04442br1 |  | T1 | 0 | 10.137.188.128/25 | 10.131.8.129/26 | 0 | T1
801301 | 1100 SHERBROOKE ST W | MONTREAL | Quebec | H3A 1G7 | Canada | e04461br1 |  | 5M | 0 | 10.137.29.128/25 | 10.207.49.1/25 | 0 | 3M
801306 | 7035 BARNET STREET | POWELL RIVER | British Columbia | V8A1Z9 | Canada | w04480br1 | 1 | DSL | 0 | 10.136.15.0/25 | 10.55.0.129/26 | 0 | T1
801315 | 315 Front St. W. | Toronto | Ontario | M5V3A4 | Canada | c04506br1 | 1 | T1 | 0 | 10.136.139.0/25 | 10.147.1.129/25 | 0 | T1
801316 | 2215 4TH ST SW | CALGARY | Alberta | T2S 1X1 | Canada | w04508br1 |  | 5M | 0 | 10.137.135.128/25 | 10.27.10.1/25 | 0 | T1
801317 | 10843 82ND AVE | EDMONTON | Alberta | T6E 2B2 | Canada | w04509br1 |  | 5M | 0 | 10.137.135.0/25 | 10.27.43.1/25 | 0 | 3M
801318 | 8249 HIGHWAY 1/ROUTE #1 | METEGHAN | Nova Scotia | B0W2J0 | Canada | e04513br1 |  | T1 | 0 | 10.136.172.0/25 | 10.191.5.1/26 | 0 | T1
801320 | 4816 50TH ST | MACKLIN | Saskatchewan | S0L2C0 | Canada | w04518br1 | 1 | DSL | 0 | 10.136.6.0/25 | 10.35.9.129/26 | 0 | T1
801322 | 9034 51ST AVE or 9042 51st? | EDMONTON | Alberta | T6E 5X4 | Canada | w04529br1 |  | 5M | 0 | 10.137.42.0/25 | 10.27.44.1/25 | 0 | T1
801323 | 550 VICTORIA ST | PRINCE GEORGE | British Columbia | V2L2K1 | Canada | w04530br1 |  | 5M | 0 | 10.137.136.0/25 | 10.63.76.1/24 | 0 | 3M
801324 | 3185 MASSEY DR | PRINCE GEORGE | British Columbia | V2N 2S9 | Canada | w04540br1 |  | 5M | 0 | 10.137.136.128/25 | 10.23.25.1/25 | 0 | 3M
801325 | 4286 JEAN TALON ST E | SAINT-LEONARD | Quebec | H1S 1J7 | Canada | e04541br1 |  | 5M | 0 | 10.137.30.0/25 | 10.187.1.1/26 | 0 | 3M
801326 | 203 AYLMER RD | GATINEAU | Quebec | J9H 6H4 | Canada | e04585br1 | 1 | T1 | 0 | 10.137.3.128/25 | 10.187.8.129/26 | 0 | 3M
801327 | 284 OAKLAND RD | SCOTLAND | Ontario | N0E1R0 | Canada | c04602br1 | 1 | DSL | 0 | 10.138.41.0/25 | 10.131.17.129/26 | 0 | T1
801331 | 13647 St Albert Trail N.W. | Edmonton | Alberta | T5L5E7 | Canada | w04620br1 | 1 | T1 | 0 | 10.137.228.0/25 | 10.79.45.1/25 | 0 | T1
801332 | 1043 ELIZABETH ST | SHARBOT LAKE | Ontario | K0H2P0 | Canada | c04622br1 |  | T1 | 0 | 10.136.252.128/25 | 10.131.20.129/26 | 0 | T1
801333 | 12332 HIGHWAY 224 | MIDDLE MUSQUODOBOIT | Nova Scotia | B0N1X0 | Canada | e04623br1 | 1 | DSL | 0 | 10.136.172.128/25 | 10.191.0.1/26 | 0 | T1
801334 | 125 Goulet St | Winnipeg | Manitoba | R2H 0R6 | Canada | w04627br5 | 1 | Other | 0 | 10.136.81.128/25 | 10.11.5.1/26 | 0 | T1
801336 | 115 MAIN ST | MARYFIELD | Saskatchewan | S0G3K0 | Canada | w04629br1 | 1 | T1 | 0 | 10.137.228.128/25 | 10.31.47.1/25 | 0 | 3M
801337 | 9499 137TH AVE - UNIT 1032 | Edmonton | Alberta | T5E5R8 | Canada | w04640br1 |  | T1 | 0 | 10.136.200.0/25 | 10.43.37.1/25 | 0 | T1
801338 | 500 WEST 2ND AVE | PRINCE RUPERT | British Columbia | V8J3T6 | Canada | c04642br1 | 1 | DSL | 0 | 10.138.41.128/25 | 10.131.18.129/26 | 0 | T1
801340 | 123 OWEN SOUND ST | SHELBURNE | Ontario | L9V 3L1 | Canada | c04662br1 |  | 5M | 0 | 10.138.42.0/25 | 10.127.43.1/25 | 0 | 3M
801341 | 55 NORFOLK ST S | SIMCOE | Ontario | N3Y2W1 | Canada | w04670br1 | 1 | T1 | 0 | 10.136.113.128/25 | 10.63.0.129/26 | 0 | T1
801342 | 133 WEST 2ND AVE | QUALICUM BEACH | British Columbia | V9K1T1 | Canada | c04682br1 |  | 5M | 0 | 10.137.11.0/25 | 10.143.44.1/25 | 0 | 3M
801344 | 3405 HARVESTER RD SUITE #201 | BURLINGTON | Ontario | L7N3N1 | Canada | w04687br1 |  | 5M | 0 | 10.138.120.128/25 | 10.79.38.1/25 | 0 | 3M
801345 | 1532 REGENT AVE W | WINNIPEG | Manitoba | R2C 3B4 | Canada | w04695br1 |  | 5M | 0 | 10.138.85.128/25 | 10.19.6.129/25 | 0 | T1
801346 | 3002 152nd St. | SURREY | British Columbia | V4P3N7 | Canada | e04701br1 |  | 5M | 0 | 10.137.30.128/25 | 10.207.40.1/25 | 0 | 3M
801347 | 5185 QUEEN MARY RD | MONTREAL | Quebec | H3W 1Y1 | Canada | e04702br1 | 1 | T1 | 0 | 10.136.173.0/25 | 10.191.45.1/25 | 0 | T1
801349 | 31 BECKWITH ST N | SMITHS FALLS | Ontario | K7A2B2 | Canada | w04720br1 | 1 | T1 | 0 | 10.136.223.128/25 | 10.63.41.1/25 | 0 | T1
801350 | 201 ST LAURENT AVE | QUESNEL | British Columbia | V2J 2C8 | Canada | c04722br1 | 1 | DSL | 0 | 10.138.42.128/25 | 10.127.0.1/26 | 0 | T1
801351 | 185 GRIFFIN ST N | SMITHVILLE | Ontario | L0R2A0 | Canada | e04733br1 |  | T1 | 0 | 10.136.173.128/25 | 10.191.5.129/26 | 0 | T1
801352 | 6 COMMERCIAL ST | MIDDLETON | Nova Scotia | B0S1P0 | Canada | w04738br1 |  | 5M | 0 | 10.138.125.128/25 | 10.35.15.1/26 | 0 | T1
801353 | 130 CENTRE ST-PO BOX 728 | MEADOW LAKE | Saskatchewan | S9X 1Y5 | Canada | w04739br1 |  | 10M | 10.34.2.193/26 |  | 10.11.115.129/25 | 0 | T1
801354 | 10180 101 ST NW | EDMONTON | Alberta | T5J 3S4 | Canada | c04742br5 |  | Other | 0 | 10.136.41.0/25 | 10.127.6.1/26 | 0 | T1
801356 | 28 Second Ave | Smooth Rock Falls | Ontario | P0L 2B0 | Canada | w04760br1 | 1 | DSL | 0 | 10.136.27.128/25 | 10.43.3.1/26 | 0 | T1
801358 | 123 MACKENZIE AVE | REVELSTOKE | British Columbia | V0E2S0 | Canada | e04782br1 |  | T1 | 0 | 10.136.174.0/25 | 10.183.20.1/26 | 0 | T1
801359 | 29 BENNETT ST | Spencerville | Ontario | K0E1X0 | Canada | c04786br1 |  | 5M | 0 | 10.137.94.128/25 | 10.143.46.1/25 | 0 | T1
801361 | 6400 NO 3 RD | RICHMOND | British Columbia | V6Y2C2 | Canada | w04800br1 |  | 5M | 0 | 10.136.244.128/25 | 10.79.70.1/24 | 0 | 3M
801362 | 237 MAIN ST | STAYNER | Ontario | L0M1S0 | Canada | c04812br1 | 1 | DSL | 0 | 10.138.43.0/25 | 10.139.2.129/25 | 0 | T1
801363 | 1863 Portage Ave | Winnipeg | Manitoba | R3J 0H1 | Canada | w04817br5 | 1 | Other | 0 | 10.136.82.0/25 | 10.55.38.1/25 | 0 | T1
801366 | 6085 HAZELDEAN RD | STITTSVILLE | Ontario | K2S 1B9 | Canada | e04842br1 |  | 5M | 0 | 10.137.31.0/25 | 10.179.15.1/25 | 0 | T1
801367 | 201 Main St | Melfort | Saskatchewan | S0E 1A0 | Canada | w04848br5 |  | Other | 0 | 10.136.82.128/25 | 10.35.6.1/26 | 0 | T1
801368 | 42 KING ST E | STONEY CREEK | Ontario | L8G1K1 | Canada | c04862br1 | 1 | DSL | 0 | 10.138.43.128/25 | 10.143.11.1/26 | 0 | T1
801369 | 125 10111 No. 3 Rd | RICHMOND | British Columbia | V7A 1W6 | Canada | w04880br1 |  | 5M | 10.34.4.65/26 |  | 10.11.114.129/25 | 0 | T1
801370 | 917 QUEENSTON RD | STONEY CREEK | Ontario | L8G 1B8 | Canada | c04882br1 |  | 5M | 0 | 10.136.242.0/25 | 10.135.56.1/25 | 0 | 3M
801373 | 33 DOWNIE ST | STRATFORD | Ontario | N5A1W6 | Canada | c04902br1 |  | 5M | 0 | 10.137.95.128/25 | 10.147.47.1/25 | 0 | T1
801374 | 7907 Highway 7 | Musquodoboit Harbour | Nova Scotia | B0J 2L0 | Canada | e04903br5 |  | Other | 0 | 10.136.48.128/25 | 10.191.1.129/26 | 0 | T1
801375 | 2600 COUNTY RD 43 | KEMPTVILLE | Ontario | K0G 1J0 | Canada | e04910br1 | 1 | DSL | 0 | 10.138.88.128/25 | 10.203.2.129/26 | 0 | T1
801376 | 966 ONTARIO ST | STRATFORD | Ontario | N5A3K1 | Canada | c04912br1 | 1 | T1 | 0 | 10.136.102.0/25 | 10.127.9.129/26 | 0 | T1
801377 | 38 FRONT ST W | STRATHROY | Ontario | N7G 1X4 | Canada | c04922br1 |  | 5M | 0 | 10.137.96.0/25 | 10.135.51.1/25 | 0 | T1
801378 | 189 QUEEN ST S | MISSISSAUGA | Ontario | L5M 1L4 | Canada | c04942br1 |  | 5M | 0 | 10.137.96.128/25 | 10.147.43.1/25 | 0 | 3M
801381 | 5253 HIGHWAY 10 | NEW GERMANY | Nova Scotia | B0R1E0 | Canada | e04953br1 | 1 | DSL | 0 | 10.138.70.0/25 | 10.183.18.129/26 | 0 | T1
801382 | 303 MAIN ST | MELVILLE | Saskatchewan | S0A2P0 | Canada | w04958br1 |  | T1 | 0 | 10.136.200.128/25 | 10.27.11.129/26 | 0 | T1
801383 | 11600 CAMBIE RD | RICHMOND | British Columbia | V6X1L5 | Canada | w04960br1 | 1 | 5M | 0 | 10.137.229.0/25 | 10.11.52.1/25 | 0 | T1
801384 | 170 KING ST | STURGEON FALLS | Ontario | P0H2G0 | Canada | c04962br1 | 1 | DSL | 0 | 10.138.44.0/25 | 10.127.4.1/26 | 0 | T1
801386 | 72 DURHAM ST-PO BOX 160 | SUDBURY | Ontario | P3E 3M6 | Canada | c04982br1 |  | 5M | 0 | 10.136.242.128/25 | 10.143.68.1/24 | 0 | 3M
801387 | 340 ALEXANDER ST-PO BOX 670 | SALMON ARM | British Columbia | V1E 4N8 | Canada | w04990br1 |  | 5M | 0 | 10.138.126.128/25 | 10.67.51.1/25 | 0 | T1
801388 | 1720 Lasalle Blvd | Sudbury | Ontario | P3A 2A1 | Canada | c04992br5 | 1 | Other | 0 | 10.136.41.128/25 | 10.131.46.1/25 | 0 | 3M
801389 | 301 Hwy 33 West | Kelowna | British Columbia | V1X 1X8 | Canada | w05000br5 | 1 | Other | 0 | 10.136.83.0/25 | 10.55.43.1/25 | 0 | T1
801390 | 5760 TEREDO ST Unit 100 | SECHELT | British Columbia | V0N3A0 | Canada | w05010cr1 |  | 5M | 0 | 10.136.11.0/25 | 10.23.38.1/25 | 10.23.38.129/25 | T1
801391 | 15 JOHN ST | SUNDRIDGE | Ontario | P0A1Z0 | Canada | c05022br1 |  | T1 | 0 | 10.136.139.128/25 | 10.131.13.1/26 | 0 | T1
801397 | 10567 Kingsway Ave | Edmonton | Alberta | T5H 4K1 | Canada | w05029br5 |  | Other | 0 | 10.136.83.128/25 | 10.11.48.1/25 | 0 | T1
801398 | 2464 BEACON AVE | SIDNEY | British Columbia | V8L 1X6 | Canada | w05030br1 |  | 5M | 0 | 10.137.137.128/25 | 10.23.49.1/25 | 0 | T1
801400 | 1106 MAIN ST | SMITHERS | British Columbia | V0J 2N0 | Canada | w05040cr1 |  | 5M | 0 | 10.136.224.128/25 | 10.75.36.1/25 | 10.73.158.1/24 | T1
801401 | 4395 George St. | SYDENHAM | Ontario | K0H2T0 | Canada | c05042br1 |  | T1 | 0 | 10.136.102.128/25 | 10.139.13.129/26 | 0 | T1
801402 | 6660 SOOKE RD | SOOKE | British Columbia | V9Z0A5 | Canada | w05050br1 |  | T1 | 10.32.145.129/25 |  | 10.22.36.1/24 | 0 | T1
801404 | 1879 REGENT ST S | SUDBURY | Ontario | P3E3Z7 | Canada | c05052br1 |  | 5M | 0 | 10.137.189.0/25 | 10.151.39.1/25 | 0 | 3M
801405 | 83 QUEEN ST | CHARLOTTETOWN | Prince Edward Island | C1A4A8 | Canada | e05054br1 |  | 5M | 0 | 10.137.116.128/25 | 10.207.35.1/25 | 0 | 3M
801406 | 110 DUNDAS ST | THAMESFORD | Ontario | N0M2M0 | Canada | c05062br1 |  | T1 | 0 | 10.136.140.0/25 | 10.131.22.129/26 | 0 | T1
801407 | 91 PROVOST ST | NEW GLASGOW | Nova Scotia | B2H2P5 | Canada | e05063br1 | 1 | DSL | 0 | 10.138.70.128/25 | 10.203.0.129/26 | 0 | T1
801408 | 335 UNIVERSITY AVE | Charlottetown | Prince Edward Island | C1A4M6 | Canada | e05064br1 |  | T1 | 0 | 10.137.0.128/25 | 10.187.2.1/25 | 0 | T1
801409 | 8165 YONGE ST | THORNHILL | Ontario | L3T2C6 | Canada | c05072br1 | 1 | T1 | 0 | 10.137.189.128/25 | 10.147.39.1/25 | 0 | 3M
801410 | 1136 CENTRE ST | THORNHILL | Ontario | L4J 3M8 | Canada | c05076br1 |  | 10M | 0 | 10.137.67.128/25 | 10.157.35.1/25 | 0 | 3M
801412 | 101 Cedar Dr | SPARWOOD | British Columbia | V0B2G0 | Canada | w05080br1 |  | T1 | 0 | 10.136.201.0/25 | 10.75.0.129/26 | 0 | T1
801413 | 52 FRONT ST S | THOROLD | Ontario | L2V3Y7 | Canada | c05082br1 |  | T1 | 0 | 10.137.190.0/25 | 10.155.10.129/26 | 0 | T1
801414 | 290 Memorial Ave | Thunder Bay | Ontario | P7B 3Y2 | Canada | w05092br5 | 1 | Other | 0 | 10.136.84.0/25 | 10.31.12.129/26 | 0 | T1
801415 | 1140 RUE ST CATHERINE O | MONTREAL | Quebec | H3B1H7 | Canada | e05101br1 |  | 5M | 0 | 10.137.31.128/25 | 10.191.41.1/25 | 0 | 3M
801416 | 121 BROADWAY ST | TILLSONBURG | Ontario | N4G 3P7 | Canada | c05102br1 |  | 5M | 0 | 10.137.11.128/25 | 10.139.39.1/25 | 0 | T1
801417 | 9256 COMMERCIAL ST | NEW MINAS | Nova Scotia | B4N4A9 | Canada | e05103br1 | 1 | DSL | 0 | 10.138.71.0/25 | 10.199.2.1/26 | 0 | T1
801418 | ROUTE #2 | HUNTER RIVER | Prince Edward Island | C0A1N0 | Canada | e05104br1 | 1 | DSL | 0 | 10.137.250.0/25 | 10.179.1.1/26 | 0 | T1
801419 | 38 PINE ST N-THE 101 MALL | TIMMINS | Ontario | P4N 6K6 | Canada | c05112br1 |  | 5M | 0 | 10.137.97.128/25 | 10.131.44.1/25 | 0 | T1
801420 | 38100 2ND AVE-PO BOX 770 | SQUAMISH | British Columbia | V8B 0A6 | Canada | w05120br1 |  | 5M | 0 | 10.137.138.0/25 | 10.23.39.1/25 | 0 | T1
801421 | 7519 PRAIRIE VALLEY RD | SUMMERLAND | British Columbia | V0H1Z4 | Canada | w05130br1 |  | T1 | 0 | 10.136.18.128/25 | 10.27.7.129/26 | 0 | T1
801422 | 1395 ELLICE AVE | WINNIPEG | Manitoba | R3G0G3 | Canada | w05137br1 |  | 5M | 0 | 10.137.42.128/25 | 10.79.72.1/24 | 0 | 3M
801423 | 1104 ALBION RD | Toronto | Ontario | M9V 1A8 | Canada | c05142br1 |  | 5M | 0 | 10.137.98.0/25 | 10.155.37.1/25 | 0 | 3M
801424 | 85 QUEEN ST N | TILBURY | Ontario | N0P2L0 | Canada | c05152br1 | 1 | DSL | 0 | 10.138.44.128/25 | 10.139.6.1/26 | 0 | T1
801427 | 5968 BATHURST ST | NORTH YORK | Ontario | M2R 1Z1 | Canada | c05172br1 |  | 5M | 0 | 10.137.98.128/25 | 10.123.55.1/25 | 0 | 3M
801428 | 3414 PLUMMER AVE | NEW WATERFORD | Nova Scotia | B1H4K4 | Canada | e05173br1 | 1 | DSL | 0 | 10.138.71.128/25 | 10.183.17.1/26 | 0 | T1
801429 | 52 HIGH ST W | MOOSE JAW | Saskatchewan | S6H1S3 | Canada | w05178br1 | 1 | T1 | #N/A | 10.136.201.128/25 | #N/A | #N/A | 3M
801430 | 11604 104TH AVE NW | EDMONTON | Alberta | T5K 2T7 | Canada | w05179br1 |  | 5M | 0 | 10.137.138.128/25 | 10.43.38.1/25 | 0 | 3M
801431 | 1235 MAIN ST N | MOOSE JAW | Saskatchewan | S6H 6M4 | Canada | w05188br1 |  | 5M | 0 | 10.137.139.0/25 | 10.35.14.1/26 | 0 | T1
801432 | 2788 BATHURST ST | North York | Ontario | M6B3A3 | Canada | c05192br1 |  | T1 | 0 | 10.136.140.128/25 | 10.155.11.1/26 | 0 | T1
801433 | 3740 MONCTON ST | RICHMOND | British Columbia | V7E3A4 | Canada | w05200br1 | 1 | T1 | 0 | 10.136.202.0/25 | 10.79.4.1/25 | 0 | T1
801434 | 222 Water St | SUMMERSIDE | Prince Edward Island | C1N 2V5 | Canada | e05204br1 |  | 5M | 0 | 10.137.32.0/25 | 10.215.7.1/26 | 0 | T1
801435 | 167 ST ANNE'S RD | WINNIPEG | Manitoba | R2M2Z7 | Canada | w05207br1 |  | T1 | 0 | 10.136.202.128/25 | 10.11.4.1/26 | 0 | T1
801437 | 13671- 72ND AVENUE | SURREY | British Columbia | v3w2p2 | Canada | w05220br6 | 1 | T1 | 0 | 10.138.102.128/25 | 10.67.52.1/25 | 0 | 3M
801436 | 13681 72ND AVE | SURREY | British Columbia | V3W 2P2 | Canada | w05220br1 |  | 5M | 0 | 10.136.230.0/25 | 10.67.37.1/25 | 0 | 3M
801438 | 4000 118TH AVE NW | Edmonton | Alberta | T5W1A1 | Canada | w05229br1 |  | T1 | 0 | 10.136.203.0/25 | 10.11.9.129/26 | 0 | T1
801439 | 600 Jean-talon St. E. | MONTREAL | Quebec | H2R3A8 | Canada | e05261br1 | 1 | T1 | 0 | 10.137.212.0/25 | 10.195.43.1/25 | 0 | 3M
801441 | 1554 BAYVIEW AVE L1 | Toronto | Ontario | M4G3B6 | Canada | c05272br1 | 1 | T1 | 0 | 10.136.141.0/25 | 10.147.11.1/26 | 0 | T1
801442 | 2514 BAYVIEW AVE | North York | Ontario | M2L1A9 | Canada | c05282br1 |  | 5M | 0 | 10.137.99.0/25 | 10.123.48.1/25 | 0 | 3M
801443 | 291 COMMERCIAL ST | NORTH SYDNEY | Nova Scotia | B2A1B9 | Canada | e05283br1 |  | DSL | #N/A | 10.138.72.0/25 | #N/A | #N/A | T1
801444 | 633 Main S | Moosomin | Saskatchewan | S0G 3N0 | Canada | w05288br5 |  | Other | 0 | 10.136.84.128/25 | 10.23.6.1/26 | 0 | T1
801449 | 436 Summerhill Ave | TORONTO | Ontario | M4W 2E4 | Canada | c05302br5 |  | Other | 0 | 10.136.42.0/25 | 10.155.5.1/26 | 0 | T1
801450 | 644 Central Ave | Ste Rose Du Lac | Manitoba | R0L 1S0 | Canada | w05337br5 |  | Other | 0 | 10.136.85.0/25 | 10.63.5.1/26 | 0 | T1
801451 | 800 du Square Victoria St. RC-04 | MONTREAL | Quebec | H4Z 1A1 | Canada | e05341br1 |  | 5M | 10.32.4.1/26 |  | 10.215.52.1/25 | 0 | T1
801452 | 972 BLOOR ST W | TORONTO | Ontario | M6H 1L6 | Canada | c05342br1 |  | 5M | 0 | 10.137.99.128/25 | 10.135.37.1/25 | 0 | T1
801454 | 2947 BLOOR ST W | Toronto | Ontario | M8X1B8 | Canada | c05362br1 |  | T1 | 0 | 10.137.190.128/25 | 10.135.4.1/26 | 0 | T1
801455 | 2329 BLOOR ST W | Toronto | Ontario | M6S1P1 | Canada | c05382br1 | 1 | T1 | 0 | 10.137.191.0/25 | 10.155.35.1/25 | 0 | T1
801456 | 188 MAIN ST | PARRSBORO | Nova Scotia | B0M1S0 | Canada | e05393br1 | 1 | DSL | 0 | 10.138.72.128/25 | 10.183.0.129/26 | 0 | T1
801457 | 9102 142ND ST NW | EDMONTON | Alberta | T5R 0M7 | Canada | w05399br1 |  | 5M | 0 | 10.137.139.128/25 | 10.27.42.1/25 | 0 | T1
801459 | 1281 56TH ST | DELTA | British Columbia | V4L 2A6 | Canada | w05400br1 |  | 5M | 0 | 10.138.17.0/25 | 10.23.63.1/25 | 0 | 3M
801460 | 401 THE WEST MALL | Toronto | Ontario | M9C5J5 | Canada | c05422br1 |  | T1 | 0 | 10.137.191.128/25 | 10.123.5.1/26 | 0 | T1
801461 | 129-137 MANNING DRIVE | Edmonton | Alberta | T5A5A1 | Canada | w05429br1 | 1 | T1 | 0 | 10.137.229.128/25 | 10.67.43.1/25 | 0 | 3M
801462 | 124 50TH ST | EDSON | Alberta | T7E1V4 | Canada | w05439br1 | 1 | DSL | 0 | 10.136.13.0/25 | 10.23.0.129/26 | 0 | T1
801463 | 4640 LAKELSE AVE | TERRACE | British Columbia | V8G1R2 | Canada | w05440br1 | 1 | T1 | 0 | 10.136.19.128/25 | 10.67.45.1/25 | 0 | 3M
801464 | 429 COLLEGE ST | TORONTO | Ontario | M5T 1T2 | Canada | c05442br1 |  | 5M | 0 | 10.137.100.0/25 | 10.135.36.1/25 | 0 | 3M
801465 | 739 BROADVIEW AV | TORONTO | Ontario | M4K2P6 | Canada | c05452br1 | 1 | T1 | 0 | 10.137.242.0/25 | 10.151.5.1/26 | 0 | T1
801466 | 831 COLLEGE ST MAIN FL | Toronto | Ontario | M6H1A1 | Canada | c05462br6 |  | T1 | #N/A | 10.136.216.0/25 | #N/A | #N/A | T1
801467 | 833 COLLEGE ST | TORONTO | Ontario | M6H1A1 | Canada | c05462br1 |  | T1 | 0 | 10.138.103.0/25 | 10.143.4.129/25 | 0 | T1
801468 | 366 MAIN ST Suite #7 | SELKIRK | Manitoba | R1A 1T6 | Canada | w05467br1 |  | 5M | 0 | 10.138.121.0/25 | 10.79.37.1/25 | 0 | T1
801471 | 253 COXWELL AVE | Toronto | Ontario | M4L3B4 | Canada | c05482br1 |  | T1 | 0 | 10.136.141.128/25 | 10.123.5.129/26 | 0 | T1
801472 | 390 BASELINE RD | SHERWOOD PARK | Alberta | T8H 1X1 | Canada | w05489br1 |  | 5M | 0 | 10.137.140.0/25 | 10.43.35.1/25 | 0 | 3M
801473 | 3880 GRANT MCCONACHIE WAY-B322 | RICHMOND | British Columbia | V7B 0A5 | Canada | w05500br1 |  | 5M | 0 | 10.137.140.128/25 | 10.67.5.129/25 | 0 | T1
801474 | 50 PLACE CREMAZIE O | MONTREAL | Quebec | H2P1A2 | Canada | e05501br1 | 1 | T1 | 0 | 10.137.212.128/25 | 10.187.46.1/25 | 0 | 3M
801475 | 1043 COXWELL AVE | Toronto | Ontario | M4C3G4 | Canada | c05502br1 | 1 | T1 | 0 | 10.136.142.0/25 | 10.123.2.129/26 | 0 | T1
801476 | 25 WATER ST | PICTOU | Nova Scotia | B0K1H0 | Canada | e05503br1 |  | T1 | 0 | 10.138.73.0/25 | 10.183.37.1/25 | 0 | T1
801477 | 5119 50TH ST | EVANSBURG | Alberta | T0E0T0 | Canada | w05509br1 |  | T1 | 0 | 10.136.203.128/25 | 10.19.3.1/26 | 0 | T1
801479 | 3076 ARBUTUS ST | VANCOUVER | British Columbia | V6J3Z2 | Canada | w05520br1 |  | T1 | 0 | 10.136.204.0/25 | 10.79.3.1/25 | 0 | T1
801480 | 2780 DANFORTH AVE | Toronto | Ontario | M4C1M1 | Canada | c05522br1 | 1 | T1 | 0 | 10.137.192.0/25 | 10.123.52.1/25 | 0 | T1
801481 | 118 1st Ave W | Nippawin | Saskatchewan | S0E 1E0 | Canada | w05538br5 |  | Other | 0 | 10.136.85.128/25 | 10.35.13.1/26 | 0 | T1
801482 | 2395 4TH AVE W | VANCOUVER | British Columbia | V6K1P2 | Canada | w05560br1 | 1 | T1 | 0 | 10.137.230.0/25 | 10.79.42.1/25 | 0 | T1
801483 | 3224 YONGE ST | Toronto | Ontario | M4N2L2 | Canada | c05562br1 |  | 5M | 0 | 10.137.192.128/25 | 10.135.5.1/26 | 0 | T1
801484 | 5228 Hwy 7 | Porter's Lake | Nova Scotia | B3E 1J8 | Canada | e05563br5 |  | Other | 0 | 10.136.49.0/25 | 10.179.14.129/26 | 0 | T1
801487 | 7155 JEAN TALON ST E | ANJOU | Quebec | H1M 3A4 | Canada | e05575br1 |  | 5M | 0 | 10.137.32.128/25 | 10.219.47.1/25 | 0 | 3M
801488 | 235 DIXON RD | Toronto | Ontario | M9P2M5 | Canada | c05582br1 | 1 | T1 | 0 | 10.137.193.0/25 | 10.155.13.129/26 | 0 | T1
801489 | 2665 RUE KING O | SHERBROOKE | Quebec | J1L2G5 | Canada | e05585br1 |  | 5M | 0 | 10.137.33.0/25 | 10.203.40.1/24 | 0 | 3M
801491 | 1510 FINCH AVE E | TORONTO | Ontario | M2J 4Y6 | Canada | c05592br1 |  | 5M | 0 | 10.137.12.0/25 | 10.123.49.1/25 | 0 | 3M
801492 | 410 Station Rd | Shoal Lake | Manitoba | R0J 1Z0 | Canada | w05597br5 |  | Other | 0 | 10.136.86.0/25 | 10.55.6.1/26 | 0 | T1
801493 | 505 WEST BROADWAY oe 398 West Broadway or both? | VANCOUVER | British Columbia | V5Z 1E7 | Canada | w05600br1 |  | 5M | 0 | 10.137.141.0/25 | 10.23.76.1/24 | 0 | 3M
801494 | 2765 DUFFERIN ST | Toronto | Ontario | M6B3R6 | Canada | c05602br1 |  | T1 | 0 | 10.136.142.128/25 | 10.135.3.129/26 | 0 | T1
801495 | 327 GRANVILLE ST | PORT HAWKESBURY | Nova Scotia | B9A 2M5 | Canada | e05613br1 |  | 5M | 0 | 10.138.15.0/25 | 10.179.9.129/26 | 0 | T1
801496 | 1101 101ST ST | NORTH BATTLEFORD | Saskatchewan | S9A 0Z5 | Canada | w05618br1 |  | 5M | 0 | 10.138.17.128/25 | 10.27.51.1/25 | 0 | T1
801497 | 10201 110TH ST | FAIRVIEW | Alberta | T0H1L0 | Canada | w05619br1 | 1 | DSL | 0 | 10.136.0.128/25 | 10.19.4.1/26 | 0 | T1
801498 | 9101 Weston Rd. | Vaughan | Ontario | L4H0L4 | Canada | c05633br1 | 1 | T1 | 0 | 10.137.193.128/25 | 10.147.15.1/25 | 0 | 3M
801499 | 4860 DUNDAS ST W | Toronto | Ontario | M9A1B5 | Canada | c05662br1 |  | 5M | 0 | 10.136.143.0/25 | 10.123.40.1/25 | 0 | T1
801501 | 1497 WEST BROADWAY | VANCOUVER | British Columbia | V6H 1H7 | Canada | w05680br1 |  | 5M | 0 | 10.137.141.128/25 | 10.31.41.1/25 | 0 | 3M
801505 | 95 KING S | WATERLOO | Ontario | N2J1P2 | Canada | c05702cr1 |  | 5M | 0 | 10.138.103.128/25 | 10.157.62.1/25 | 0 | 5M
801506 | 23564 WOODBINE AVE | KESWICK | Ontario | L4P 0E2 | Canada | c05714br6 |  | T1 | 0 | 10.136.216.128/25 | 10.147.5.129/26 | 0 | T1
801508 | 880 EGLINTON AVE W | Toronto | Ontario | M6C2B6 | Canada | c05722br1 |  | T1 | 0 | 10.137.194.0/25 | 10.143.12.1/26 | 0 | T1
801509 | 81 BALSAM ST | SNOW LAKE | Manitoba | R0B1M0 | Canada | w05727br1 |  | T1 | 0 | 10.136.204.128/25 | 10.55.3.1/26 | 0 | T1
801510 | 103 MAIN ST | OGEMA | Saskatchewan | S0C1Y0 | Canada | w05728br1 |  | T1 | 0 | 10.136.205.0/25 | 10.27.5.129/26 | 0 | T1
801511 | 120 MAIN ST | FOREMOST | Alberta | T0K0X0 | Canada | w05729br1 |  | T1 | 0 | 10.136.253.128/25 | 10.19.5.1/26 | 0 | T1
801512 | 111 GRANGEWAY AVE | Toronto | Ontario | M1H3E9 | Canada | c05752br1 |  | 5M | 0 | 10.136.243.0/25 | 10.143.78.1/24 | 0 | 3M
801514 | 2043 EGLINTON AVE E | Toronto | Ontario | M1L2M9 | Canada | c05762br1 | 1 | T1 | 0 | 10.137.194.128/25 | 10.155.38.1/25 | 0 | 3M
801515 | 271 LACEWOOD DR | HALIFAX | Nova Scotia | B3M 4K3 | Canada | e05783br1 |  | 5M | 0 | 10.137.33.128/25 | 10.191.52.1/25 | 0 | 3M
801517 | 531 WEST 57TH AVE | VANCOUVER | British Columbia | V6P1R8 | Canada | w05790br1 |  | T1 | 0 | 10.136.205.128/25 | 10.67.0.1/25 | 0 | T1
801518 | 648 Spadina Ave | TORONTO | Ontario | M5S 2H7 | Canada | c05802br5 |  | Other | 0 | 10.136.42.128/25 | 10.143.10.129/26 | 0 | T1
801522 | 1732 JANE ST | Toronto | Ontario | M9N2S4 | Canada | c05812br1 |  | T1 | 0 | 10.137.238.128/25 | 10.143.3.129/26 | 0 | T1
801523 | 119 Saskatchewan Ave E | Outlook | Saskatchewan | S0L 2N0 | Canada | w05828br5 |  | Other | 0 | 10.136.36.128/25 | 10.19.1.129/26 | 0 | T1
801524 | 9955 GRENVILLE ST | ST PETERS | Nova Scotia | B0E3B0 | Canada | e05833br1 | 1 | DSL | 0 | 10.138.73.128/25 | 10.183.7.1/26 | 0 | T1
801525 | 302 Main St | Oxbow | Saskatchewan | S0C 2B0 | Canada | w05838br5 |  | Other | 0 | 10.136.86.128/25 | 10.19.6.1/26 | 0 | T1
801526 | 9916 102ND ST or 9918 102ND ST ? | FORT SASKATCHEWAN | Alberta | T8L 2C3 | Canada | w05839br1 |  | 5M | 0 | 10.137.142.0/25 | 10.11.45.1/25 | 0 | T1
801527 | 15365 10 Hwy | SURREY | British Columbia | V3S0X9 | Canada | w05840br1 | 1 | T1 | 0 | 10.137.230.128/25 | 10.35.36.1/25 | 0 | T1
801528 | 1011 Gerrard St. E. | Toronto | Ontario | M4M1Z4 | Canada | c05842br1 |  | 5M | 0 | 10.137.195.0/25 | 10.147.16.1/26 | 0 | 3M
801529 | 4370 WELLINGTON ST | VERDUN | Quebec | H4G1W4 | Canada | e05855br1 |  | 5M | 0 | 10.138.104.0/25 | 10.197.0.1/23 | 0 | 5M
801530 | 309 3rd St | Somerset | Manitoba | R0G 2L0 | Canada | w05857br5 |  | Other | 0 | 10.136.87.0/25 | 10.27.1.1/26 | 0 | T1
801534 | 207304 Norway House Cree Nation, Norway House Mal | NORWAY HOUSE | Manitoba | R0B 1B0 | Canada | w05879br1 |  | 5M | 0 | 10.138.121.128/25 | 10.31.8.129/26 | 0 | T1
801535 | 3336 KEELE ST | Toronto | Ontario | M3J1L5 | Canada | c05882br1 | 1 | T1 | 0 | 10.137.195.128/25 | 10.123.6.129/26 | 0 | T1
801536 | 4720 JANE ST N | North York | Ontario | M3N2L2 | Canada | c05892br1 | 1 | T1 | 0 | 10.137.196.0/25 | 10.123.53.1/25 | 0 | T1
801544 | 2766 KEELE ST | NORTH YORK | Ontario | M3M 2G2 | Canada | c05902br1 |  | 5M | 0 | 10.137.101.0/25 | 10.123.35.1/25 | 0 | T1
801546 | 1715 COMMERCIAL DR | VANCOUVER | British Columbia | V5N 4A4 | Canada | w05920br1 |  | 5M | 0 | 10.137.142.128/25 | 10.67.35.1/25 | 0 | T1
801547 | 1421 KENNEDY RD | Toronto | Ontario | M1P2L6 | Canada | c05922br1 |  | 5M | 0 | 10.137.101.128/25 | 10.143.37.1/25 | 0 | 3M
801548 | 1571 SANDHURST CIRCLE | SCARBOROUGH | Ontario | M1V1V2 | Canada | c05942cr1 |  | 5M | 0 | 10.137.161.0/25 | 10.135.40.1/25 | 0 | 3M
801549 | 6 MAIN ST | SHERBROOKE | Nova Scotia | B0J3C0 | Canada | e05943br1 |  | T1 | 0 | 10.136.174.128/25 | 10.183.18.1/26 | 0 | T1
801550 | 9815 98TH ST | GRANDE PRAIRIE | Alberta | T8V2E4 | Canada | w05949br1 |  | 5M | 0 | 10.137.143.0/25 | 10.79.78.1/24 | 0 | 5M
801551 | 901 JANE ST | Toronto | Ontario | M6N4C6 | Canada | c05952br1 |  | T1 | 0 | 10.136.143.128/25 | 10.151.4.129/26 | 0 | T1
801556 | 5 Samson Blvd. | LAVAL | Quebec | H7X3S5 | Canada | e05970br1 |  | T1 | 0 | 10.136.175.0/25 | 10.191.39.1/25 | 0 | T1
801557 | 3105 BOUL DES RICOLLETS | TROIS-RIVIERES | Quebec | G9A6M1 | Canada | e05971br1 | 1 | T1 | 0 | 10.137.213.0/25 | 10.219.37.1/25 | 0 | T1
801558 | 47 CRESCENT AVE W-PO BOX 428 | SOURIS | Manitoba | R0K 2C0 | Canada | w05987br1 |  | 5M | 0 | 10.136.101.128/25 | 10.63.4.1/26 | 0 | T1
801559 | 936 Kingston Rd. | Toronto | Ontario | M4E1S7 | Canada | c05992br1 |  | T1 | 0 | 10.137.196.128/25 | 10.127.0.129/26 | 0 | T1
801560 | 945 Denman St | VANCOUVER | British Columbia | V6G 2M3 | Canada | w06000br5 | 1 | Other | 0 | 10.136.87.128/25 | 10.55.40.1/25 | 0 | 3M
801561 | 4374 Kingston Road East | Toronto | Ontario | M1E2M8 | Canada | c06002br1 | 1 | T1 | 0 | 10.136.254.128/25 | 10.135.36.129/25 | 0 | T1
801562 | 65 QUEEN ST. W. | TORONTO | Ontario | M5H2M5 | Canada | c06012br1 |  | T1 | 0 | 10.138.104.128/25 | 10.135.2.129/26 | 0 | T1
801564 | 3090 Kingston Rd | SCARBOROUGH | Ontario | M1M 1P2 | Canada | c06022br1 |  | T1 | 0 | 10.137.197.0/25 | 10.155.7.1/26 | 0 | T1
801565 | 260 EAST BEAVER CREEK RD | Richmond Hill | Ontario | L4B3M3 | Canada | c06032br1 |  | 10M | 0 | 10.136.228.0/25 | 10.200.84.1/23 | 0 | 3M
801566 | 2824 MAIN ST | SHUBENACADIE | Nova Scotia | B0N2H0 | Canada | e06053br1 |  | T1 | 0 | 10.136.175.128/25 | 10.191.0.129/26 | 0 | T1
801567 | 6051 RUE SHERBROOKE O | MONTREAL | Quebec | H4A1Y2 | Canada | e06061br1 | 1 | T1 | 0 | 10.137.213.128/25 | 10.199.35.1/25 | 0 | T1
801571 | 4205 Dunbar St | VANCOUVER | British Columbia | V6S 2G1 | Canada | w06080br5 | 1 | Other | 0 | 10.136.88.0/25 | 10.79.5.1/25 | 0 | T1
801574 | 3609 LAKESHORE BLVD W | Toronto | Ontario | M8W1P4 | Canada | c06102br1 |  | T1 | 0 | 10.136.144.0/25 | 10.155.12.129/26 | 0 | T1
801575 | 140 LA ROSE AVE | Toronto | Ontario | M9P1B2 | Canada | c06112br1 |  | T1 | 0 | 10.136.144.128/25 | 10.155.4.129/26 | 0 | T1
801576 | 339 Herring Cove Rd | Halifax | Nova Scotia | B3R 1V5 | Canada | e06113br5 |  | Other | 0 | 10.136.49.128/25 | 10.187.53.1/25 | 0 | T1
801577 | 288 MAIN ST | STEINBACH | Manitoba | R5G 1Y8 | Canada | w06117br1 |  | 5M | 0 | 10.138.122.0/25 | 10.79.40.1/25 | 0 | T1
801579 | 6510 AVE SOMERLED | MONTREAL | Quebec | H4V1S8 | Canada | e06141br1 |  | T1 | 0 | 10.136.176.0/25 | 10.199.36.1/25 | 0 | T1
801580 | 1090 DON MILLS RD | Toronto | Ontario | M3C3R6 | Canada | c06142br1 |  | 5M | 0 | 10.137.12.128/25 | 10.123.72.1/24 | 0 | 3M
801581 | 340 MAIN ST | STONEWALL | Manitoba | R0C2Z0 | Canada | w06147br1 |  | T1 | 0 | 10.136.17.0/25 | 10.31.3.129/25 | 0 | T1
801582 | 6505 FRASER ST | VANCOUVER | British Columbia | V5X 3T4 | Canada | w06160br1 |  | 5M | 0 | 10.137.143.128/25 | 10.55.36.1/25 | 0 | 3M
801583 | 254 FOORD ST | STELLARTON | Nova Scotia | B0K 1S0 | Canada | e06163br1 |  | 5M | 0 | 10.137.34.0/25 | 10.215.1.129/26 | 0 | T1
801584 | 249 Centre St | Ponteix | Saskatchewan | S0N 1Z0 | Canada | w06168br5 |  | Other | 0 | 10.136.88.128/25 | 10.35.3.1/26 | 0 | T1
801585 | 301 CENTRE ST | HANNA | Alberta | T0J1P0 | Canada | w06169br1 | 1 | DSL | 0 | 10.136.12.0/25 | 10.19.7.1/26 | 0 | T1
801586 | 3091 LAWRENCE AVE E | Toronto | Ontario | M1H1A1 | Canada | c06172br1 | 1 | T1 | 0 | 10.137.197.128/25 | 10.143.8.1/26 | 0 | T1
801587 | 502 MAIN ST E-PO BOX 940 | SWAN RIVER | Manitoba | R0L 1Z0 | Canada | w06177br1 |  | 5M | 0 | 10.138.122.128/25 | 10.79.6.129/26 | 0 | T1
801588 | 1919 LAWRENCE AVE E L1 | Toronto | Ontario | M1R2Y6 | Canada | c06182br1 |  | 5M | 0 |  | 10.135.39.1/25 | 0 | T1
801589 | 65 OVERLEA BLVD | Toronto | Ontario | M4H1P1 | Canada | c06192br1 |  | T1 | 0 | 10.136.145.0/25 | 10.151.10.129/26 | 0 | T1
801590 | 3570 Lawrence Ave East | Toronto | Ontario | M1G 0A3 | Canada | c06202br1 |  | 5M | 10.33.5.193/26 |  | 10.11.43.129/25 | 0 | T1
801593 | 2835 AVE VAN HORNE | MONTREAL | Quebec | H3S1P6 | Canada | e06221br1 |  | T1 | 0 | 10.136.176.128/25 | 10.207.41.1/25 | 0 | T1
801594 | 650 DANFORTH AVE | TORONTO | Ontario | M4K 1R3 | Canada | c06222br1 |  | 5M | 0 | 10.138.10.128/25 | 10.135.35.1/25 | 0 | 3M
801595 | 106 Millennium Dr. | Fort Mcmurray | Alberta | T9K2S8 | Canada | w06231br1 | 1 | T1 | 0 | 10.136.206.0/25 | 10.23.34.129/26 | 0 | T1
801596 | 301 Edwards Ave | The Pas | Manitoba | R9A 1L1 | Canada | w06247br5 |  | Other | 0 | 10.136.89.0/25 | 10.27.3.129/26 | 0 | T1
801598 | 2175 QUEEN ST E | TORONTO | Ontario | M4E 1E5 | Canada | c06262cr1 |  | 10M | 10.147.52.1/25 |  | 10.147.37.1/25 | 10.147.37.129/25 | T1
801599 | 801 15TH ST E-SUITE 735 | PRINCE ALBERT | Saskatchewan | S6V 0C7 | Canada | w06278br1 |  | 5M | 0 | 10.138.117.0/25 | 10.11.65.1/25 | 0 | 3M
801600 | 5117 49TH ST | HIGH PRAIRIE | Alberta | T0G1E0 | Canada | w06279br1 | 1 | DSL | 0 | 10.136.7.128/25 | 10.19.8.1/26 | 0 | T1
801603 | 4851 VAN HORNE AVE | MONTREAL | Quebec | H3W 1J2 | Canada | e06301br1 |  | 5M | 0 | 10.137.34.128/25 | 10.207.37.1/25 | 0 | 3M
801604 | 1233 THE QUEENSWAY | ETOBICOKE | Ontario | M8Z 1S1 | Canada | c06302br1 |  | 3M | 0 | 10.136.240.128/25 | 10.147.44.1/25 | 0 | 3M
801607 | 129 REXDALE BLVD | ETOBICOKE | Ontario | M9W 1P4 | Canada | c06342br1 |  | 5M | 0 | 10.137.102.0/25 | 10.123.0.1/25 | 0 | T1
801608 | 179 Roncesvalles Ave. | Toronto | Ontario | M6R2L5 | Canada | c06352br1 | 1 | T1 | 0 | 10.137.198.0/25 | 10.143.49.1/25 | 0 | T1
801609 | 23 SELKIRK AVE | THOMPSON | Manitoba | R8N0M5 | Canada | w06377br1 |  | T1 | 0 | 10.136.206.128/25 | 10.27.2.129/26 | 0 | T1
801610 | 102 3RD AVE W | HIGH RIVER | Alberta | T1V 1M4 | Canada | w06389cr1 |  | 3M | 0 | 10.136.33.128/25 | 10.11.53.1/25 | 0 | T1
801611 | 229 7TH AVE S-PO BOX 1750 | VIRDEN | Manitoba | R0M 2C0 | Canada | w06397br1 |  | 5M | 0 | 10.138.123.0/25 | 10.27.1.129/26 | 0 | T1
801612 | 10 ST CLAIR AVE W | Toronto | Ontario | M4V1L4 | Canada | c06402br1 |  | 3M | 10.33.62.129/25 | 10.33.62.128/25 | 10.139.35.1/25 | 0 | 3M
801614 | 759 RUE DE ST JOVITE | Mont-Tremblant | Quebec | J8E3J8 | Canada | e06419br1 |  | T1 | 0 | 10.136.177.0/25 | 10.191.2.1/26 | 0 | T1
801615 | 935 ST CLAIR AVE W | Toronto | Ontario | M6C1C7 | Canada | c06422br1 | 1 | T1 | 0 | 10.136.145.128/25 | 10.143.5.1/26 | 0 | T1
801616 | 803 O`CONNOR DR | Toronto | Ontario | M4B2S7 | Canada | c06442br1 |  | T1 | 0 | 10.136.146.0/25 | 10.123.3.129/26 | 0 | T1
801617 | 4022 SHEPPARD AVE E | SCARBOROUGH | Ontario | M1S1S6 | Canada | c06462br1 | 1 | 5M | 10.32.145.1/25 |  | 10.22.35.1/24 | 0 | T1
801618 | 5125 SHEPPARD AVE E | Toronto | Ontario | M1S 4N8 | Canada | c06492br1 |  | 5M | 10.33.1.1/26 |  | 10.11.18.1/25 | 0 | T1
801619 | 8888 Country Hills Blvd., N.W. - Unit #1000 | CALGARY | Alberta | T3G5T4 | Canada | w06498br1 | 1 | T1 | 0 | 10.137.231.0/25 | 10.35.37.1/25 | 0 | T1
801623 | 2441 7TH AVE N | REGINA | Saskatchewan | S4R 0K4 | Canada | w06508br1 |  | 5M | 0 | 10.137.144.0/25 | 10.27.70.1/24 | 0 | 3M
801624 | 1545 STEELES AVE E | TORONTO | Ontario | M2M 3Y7 | Canada | c06512br1 |  | 5M | 0 | 10.137.102.128/25 | 10.123.50.1/25 | 0 | 3M
801626 | 8585 GRANVILLE ST | VANCOUVER | British Columbia | V6P4Z7 | Canada | w06520br1 | 1 | T1 | 0 | 10.137.231.128/25 | 10.67.44.1/25 | 0 | 3M
801627 | 4 KAMOTIK ST | CAMBRIDGE BAY | Nunavut | X0B0C0 | Canada | w06527br1 |  | 2M | #N/A | 10.138.113.0/25 | #N/A | #N/A | T1
801628 | 2786 VICTORIA PARK AVE | NORTH YORK | Ontario | M2J 4A8 | Canada | c06532br1 |  | 5M | 0 | 10.137.103.0/25 | 10.123.54.1/25 | 0 | 3M
801629 | 443 UNIVERSITY AVE | Toronto | Ontario | M5G2H6 | Canada | c06542br1 |  | 5M | 0 | 10.137.13.0/25 | 10.155.0.1/24 | 0 | 3M
801631 | 685 WEST HASTINGS ST | VANCOUVER | British Columbia | V6B 1N9 | Canada | w06550br1 |  | 5M | 0 | 10.136.32.0/25 | 10.23.74.1/24 | 0 | 3M
801632 | 290 THE WEST MALL | Toronto | Ontario | M9C 1C6 | Canada | c06572br1 |  | T1 | 0 | 10.137.198.128/25 | 10.155.10.1/26 | 0 | T1
801633 | 1906 WESTON RD | Toronto | Ontario | M9N1W2 | Canada | c06582br1 |  | T1 | 0 | 10.136.146.128/25 | 10.143.3.1/26 | 0 | T1
801634 | 404 CHARLOTTE ST | SYDNEY | Nova Scotia | B1P 1E2 | Canada | e06603cr1 |  | 5M | 0 | 10.137.164.0/25 | 10.183.41.1/25 | 0 | T1
801636 | 874 CARMICHAEL LANE | HINTON | Alberta | T7V1Y6 | Canada | w06609br1 |  | T1 | 0 | 10.136.3.0/25 | 10.23.1.129/26 | 0 | T1
801637 | 415 THE WESTWAY | Toronto | Ontario | M9R1H5 | Canada | c06612br1 |  | 5M | 0 | 10.136.147.0/25 | 10.123.6.1/26 | 0 | T1
801638 | 10611 BOUL PIE IX | MONTREAL NORTH | Quebec | H1H4A3 | Canada | e06621br1 | 1 | T1 | #N/A | 10.137.214.0/25 | #N/A | #N/A | 3M
801639 | 4401 BATHURST ST | NORTH YORK | Ontario | M3H 3R9 | Canada | c06622br1 |  | 5M | 0 | 10.137.13.128/25 | 10.155.42.1/25 | 0 | 3M
801640 | 2381 HASTINGS ST E | VANCOUVER | British Columbia | V5L 1V6 | Canada | w06640br1 |  | 5M | 0 | 10.137.144.128/25 | 10.11.36.1/25 | 0 | T1
801641 | 3461 Gouin Blvd E | Montreal-Nord | Quebec | H1H 1B2 | Canada | e06651br5 |  | Other | 0 | 10.136.50.0/25 | 10.187.0.129/26 | 0 | T1
801642 | 2076 DANFORTH AVE | Toronto | Ontario | M4C1J6 | Canada | c06662br1 | 1 | T1 | 0 | 10.136.147.128/25 | 10.123.4.129/26 | 0 | T1
801643 | 150 WYNFORD HEIGHTS CRES | Toronto | Ontario | M3C1K6 | Canada | c06672br1 |  | T1 | 0 | 10.136.148.0/25 | 10.147.13.1/26 | 0 | T1
801644 | 26 WESTMINSTER N | MONTREAL | Quebec | H4X1Z2 | Canada | e06701br1 |  | T1 | 0 | 10.136.177.128/25 | 10.207.0.129/26 | 0 | T1
801645 | 2 BLOOR ST E | TORONTO | Ontario | M4W1A8 | Canada | c06702cr1 |  | 10M | 10.33.63.1/24 |  | 10.143.74.1/23 | 0 | 5M
801646 | 3816 ALBERT ST | REGINA | Saskatchewan | S4S3R3 | Canada | w06718br1 |  | 5M | 10.34.17.1/25 | 10.137.43.0/25 | 10.35.40.1/25 | 0 | 3M
801647 | 1010 Hornby St | VANCOUVER | British Columbia | V6Z 1V6 | Canada | w06720br1 |  | 5M | 10.34.3.193/26 |  | 10.11.50.129/25 | 0 | T1
801648 | 2346 YONGE ST | TORONTO | Ontario | M4P 2W7 | Canada | c06722br1 |  | 5M | 0 | 10.137.103.128/25 | 10.135.48.1/25 | 0 | 3M
801649 | 468 YONGE ST | TORONTO | Ontario | M4Y 1X3 | Canada | c06742br1 |  | 5M | 0 | 10.137.14.0/25 | 10.147.45.1/25 | 0 | T1
801650 | 500 DUNDAS ST W | TORONTO | Ontario | M5T 1G9 | Canada | c06752br1 |  | 5M | 0 | 10.137.14.128/25 | 10.135.49.1/25 | 0 | 3M
801652 | 5700 Yonge St. | Toronto | Ontario | M2M 4K2 | Canada | c06762br1 | 1 | T1 | 0 | 10.137.199.0/25 | 10.123.11.1/26 | 0 | T1
801653 | 147 4TH ST | WAWANESA | Manitoba | R0K2G0 | Canada | w06767br1 |  | T1 | 0 | 10.136.207.0/25 | 10.79.2.129/26 | 0 | T1
801654 | 2880 2ND AVE W | PRINCE ALBERT | Saskatchewan | S6V5Z4 | Canada | w06768br1 |  | T1 | 0 | 10.136.207.128/25 | 10.35.13.129/26 | 0 | T1
801658 | 260 SPADINA AVE | TORONTO | Ontario | M5T2E4 | Canada | c06776br1 |  | 5M | 0 | 10.138.105.0/25 | 10.139.0.129/26 | 0 | 5M
801659 | 1427 GRAHAM BLVD | MONT-ROYAL | Quebec | H3P 3M9 | Canada | e06781br1 |  | 5M | 0 | 10.137.35.0/25 | 10.191.54.1/25 | 0 | 3M
801660 | 2208 WEST 41TH AVE | VANCOUVER | British Columbia | V6M1Z8 | Canada | w06800br1 |  | 5M | 0 | 10.137.145.128/25 | 10.31.50.1/25 | 0 | 3M
801661 | 2559 YONGE ST | Toronto | Ontario | M4P2J1 | Canada | c06802br1 |  | 5M | 0 | 10.136.148.128/25 | 10.143.9.129/25 | 0 | T1
801662 | 2350 MCPHILLIPS ST | WINNIPEG | Manitoba | R2V 4J6 | Canada | w06807br1 |  | 5M | 0 | 10.138.124.0/25 | 10.79.39.1/25 | 0 | 3M
801663 | 3935 OAK ST | VANCOUVER | British Columbia | V6H2M7 | Canada | w06820br1 | 1 | T1 | 0 | 10.136.208.0/25 | 10.11.12.1/25 | 0 | T1
801665 | 940 PRINCE ST | TRURO | Nova Scotia | B2N 1H5 | Canada | e06823br1 |  | 5M | 0 | 10.137.117.0/25 | 10.215.35.1/25 | 0 | 3M
801666 | 1846 Main St | Winnipeg | Manitoba | R2V 3H2 | Canada | w06827br5 | 1 | Other | 0 | 10.136.89.128/25 | 10.27.0.129/26 | 0 | T1
801667 | 1246 BROAD ST | REGINA | Saskatchewan | S4R1Y3 | Canada | w06828br1 | 1 | T1 | 0 | 10.136.208.128/25 | 10.63.0.1/26 | 0 | T1
801670 | 4962 52ND ST | INNISFAIL | Alberta | T4G1S7 | Canada | w06829br1 | 1 | DSL | 0 | 10.136.23.128/25 | 10.27.6.1/26 | 0 | T1
801671 | 2900 WARDEN AVE | SCARBOROUGH | Ontario | M1W 2S8 | Canada | c06832cr1 |  | 5M | 0 | 10.137.161.128/25 | 10.135.53.1/25 | 0 | 3M
801672 | 3318 KINGSWAY | VANCOUVER | British Columbia | V5R 5K7 | Canada | w06840br1 |  | 5M | 0 | 10.137.146.0/25 | 10.11.35.1/25 | 0 | 3M
801673 | 1399 MCPHILLIPS ST | WINNIPEG | Manitoba | R2V 3C4 | Canada | w06857br1 |  | 5M | 0 | 10.137.146.128/25 | 10.63.38.1/25 | 0 | T1
801676 | 7371 HWY #6 , TOBERMORY , ON, N0H 2R0 | TOBERMORY | Ontario | N0H2R0 | Canada | c06862br1 |  | T1 | 0 | 10.138.126.0/25 | 10.151.13.1/26 | 0 | T1
801677 | 220 OKINGUTIGIIT BUILDING | RANKIN INLET | Northwest Territories | X0C0G0 | Canada | w06887br1 |  | 2M | #N/A | 10.138.113.128/25 | #N/A | #N/A | T1
801678 | 5222 130TH AVE SE | CALGARY | Alberta | T2Z 0G4 | Canada | w06892cr1 |  | 5M | 0 | 10.137.53.0/25 | 10.19.36.1/25 | 0 | 3M
801679 | 225 MAIN ST | WINKLER | Manitoba | R6W4B3 | Canada | w06907br1 |  | T1 | 0 | 10.136.209.0/25 | 10.79.7.1/26 | 0 | T1
801680 | 5500 AVE ROYALMOUNT | MONT-ROYAL | Quebec | H4P1H7 | Canada | e06941br1 |  | T1 | 0 | 10.136.178.0/25 | 10.207.2.129/26 | 0 | T1
801682 | 714 ROSSLAND RD | WHITBY | Ontario | L1N 9L3 | Canada | c06962br1 |  | 5M | 0 | 10.137.15.0/25 | 10.151.8.129/26 | 0 | T1
801695 | 5022 50TH AVE | LACOMBE | Alberta | T4L2L1 | Canada | w07049br1 | 1 | DSL | 0 | 10.136.25.0/25 | 10.31.6.1/26 | 0 | T1
801699 | 1298 VAN HORNE AVE | OUTREMONT | Quebec | H2V 1K6 | Canada | e07091br1 |  | 5M | 10.32.2.193/26 |  | 10.215.51.1/25 | 0 | T1
801700 | 13135 BOUL GOUIN O | PIERRE FONDS | Quebec | H8Z1X1 | Canada | e07111br1 |  | T1 | 0 | 10.136.178.128/25 | 10.219.45.1/25 | 0 | T1
801701 | 400 MAIN ST 2ND FL | VANCOUVER | British Columbia | V6A2T5 | Canada | w07120br1 |  | 5M | 0 | 10.137.147.0/25 | 10.43.70.1/24 | 0 | 3M
801702 | 101 BOUL CARDINAL LEGER | PINCOURT | Quebec | J7V3Y3 | Canada | e07121br1 | 1 | DSL | 0 | 10.138.74.0/25 | 10.207.0.1/26 | 0 | T1
801704 | 6615 HWY #1 | COLDBROOK | Nova Scotia | B4R1B6 | Canada | e07153br1 | 1 | DSL | 0 | 10.138.74.128/25 | 10.199.2.129/26 | 0 | T1
801705 | 10 LEDUC TOWNE CTR | LEDUC | Alberta | T9E 7K6 | Canada | w07159br1 |  | 5M | 0 | 10.137.147.128/25 | 10.27.46.1/25 | 0 | T1
801706 | 321 BOUL ST JEAN | Pointe Claire | Quebec | H9R3J1 | Canada | e07171br1 |  | T1 | 0 | 10.137.214.128/25 | 10.207.5.1/26 | 0 | T1
801708 | 610 ST-JEAN BOULEVARD | POINTE-CLAIRE | Quebec | H9R 3K2 | Canada | e07191br1 |  | 5M | 0 | 10.137.35.128/25 | 10.215.70.1/24 | 0 | 3M
801710 | 4095 Main St | VANCOUVER | British Columbia | V5V 3P5 | Canada | w07200br5 | 1 | Other | 0 | 10.136.90.0/25 | 10.67.0.129/26 | 0 | T1
801711 | 4095 Main St | Vancouver | British Columbia | V5V 3P5 | Canada | w07200br5 | 1 | Other | 0 | 10.136.90.0/25 | 10.67.0.129/26 | 0 | T1
801716 | 1635 AVENUE RD | TORONTO | Ontario | M5M 3X8 | Canada | c07212br1 |  | 5M | 0 | 10.137.15.128/25 | 10.157.45.1/25 | 0 | 3M
801717 | 968 ROUTE #335 | WEST PUBNICO | Nova Scotia | B0W3S0 | Canada | e07213br1 |  | T1 | 0 | 10.136.179.0/25 | 10.191.9.129/26 | 0 | T1
801719 | 950 VICTORIA AVE E | REGINA | Saskatchewan | S4N 7A9 | Canada | w07218br1 |  | 5M | 0 | 10.137.148.0/25 | 10.67.40.1/25 | 0 | 3M
801720 | 3405 HARVESTER RD | BURLINGTON | Ontario | L7N3N1 | Canada | c07233br1 | 1 | 20M | 0 | 10.137.65.0/25 | 10.141.112.1/24 | 0 | T1
801722 | 1813 MAIN ST | WESTVILLE | Nova Scotia | B0K2A0 | Canada | e07263br1 | 1 | DSL | 0 | 10.136.222.0/25 | 10.199.4.1/26 | 0 | T1
801723 | 213 Main St | Rosetown | Saskatchewan | S0L 2V0 | Canada | w07268br5 |  | Other | 0 | 10.136.90.128/25 | 10.31.10.1/26 | 0 | T1
801724 | 614 4TH AVE S | LETHBRIDGE | Alberta | T1J0N7 | Canada | w07269br1 |  | 5M | 0 | 10.137.148.128/25 | 10.43.78.1/24 | 0 | 3M
801725 | 1700 CORYDON AVE SUITE #100 | WINNIPEG | Manitoba | R3N0K1 | Canada | w07287br1 | 1 | T1 | 0 | 10.136.209.128/25 | 10.67.39.1/25 | 0 | T1
801726 | 195 FORT ST | WINNIPEG | Manitoba | R3C3N1 | Canada | w07310br1 |  | T1 | 0 | 10.138.105.128/25 | 10.63.40.1/25 | 0 | T1
801727 | 3466 Queen Street | RAWDON | Quebec | J0K 1S0 | Canada | e07311br1 |  | 5M | 0 | 10.137.117.128/25 | 10.195.57.1/25 | 0 | T1
801728 | 1240 2A AVE N | LETHBRIDGE | Alberta | T1H 0E4 | Canada | w07319br1 |  | 5M | 0 | 10.137.149.0/25 | 10.27.12.1/26 | 0 | T1
801730 | 650 WEST 41ST AVE | VANCOUVER | British Columbia | V5Z 2M9 | Canada | w07360br1 |  | 10M | 0 | 10.136.32.128/25 | 10.23.70.1/24 | 0 | 3M
801731 | 7 King St E | Forest | Ontario | N0N 1J0 | Canada | c07372br5 |  | Other | 0 | 10.136.43.0/25 | 10.135.10.1/26 | 0 | T1
801732 | ROUTE #1 | WEYMOUTH | Nova Scotia | B0W3T0 | Canada | e07373br1 |  | T1 | 0 | 10.136.253.0/25 | 10.183.10.129/26 | 0 | T1
801733 | 154 1ST AVE S | SASKATOON | Saskatchewan | S7K 1K2 | Canada | w07378br1 | 1 | 5M | 0 | 10.136.245.0/25 | 10.63.74.1/24 | 0 | 3M
801734 | 1139 Mayor Magrath Dr | Lethbridge | Alberta | T1K 2P9 | Canada | w07379br5 |  | Other | 0 | 10.136.91.0/25 | 10.23.3.1/26 | 0 | T1
801735 | 1 St-Germain St E | Rimouski | Quebec | G5L 1A1 | Canada | e07381br5 |  | Other | #N/A | 10.136.50.128/25 | #N/A | #N/A | T1
801736 | 2030 AVENUE C N | SASKATOON | Saskatchewan | S7L 1M2 | Canada | w07388br1 |  | 5M | 0 | 10.137.150.0/25 | 10.31.70.1/24 | 0 | T1
801737 | 319 Ludlow St. | SASKATOON | Saskatchewan | S7S1N6 | Canada | w07408br1 | 1 | T1 | 0 | 10.136.210.0/25 | 10.55.50.1/25 | 0 | T1
801743 | 84 BROADWAY ST E UNIT #1 | Yorkton | Saskatchewan | S3N0K9 | Canada | w07410br1 | 1 | T1 | 0 | 10.136.210.128/25 | 10.43.7.129/26 | 0 | T1
801745 | 2501 Third Line | OAKVILLE | Ontario | L6M5A9 | Canada | c07412br1 |  | T1 | 0 | 10.136.149.0/25 | 10.131.0.1/26 | 0 | T1
801746 | 123 Lenore Dr | Saskatoon | Saskatchewan | S7K 7H9 | Canada | w07418br5 | 1 | Other | 0 | 10.136.91.128/25 | 10.35.42.1/25 | 0 | T1
801747 | 1219 GRANT AVE | WINNIPEG | Manitoba | R3M1Z1 | Canada | w07437br1 | 1 | T1 | 0 | 10.137.232.0/25 | 10.11.43.1/25 | 0 | 3M
801748 | 1716 RENFREW ST | VANCOUVER | British Columbia | V5M3H8 | Canada | w07440br1 | 1 | 5M | 0 | 10.136.211.0/25 | 10.31.0.1/26 | 0 | T1
801749 | 893 BOUL ST JOSEPH | ROBERVAL | Quebec | G8H2L8 | Canada | e07451br1 | 1 | DSL | 0 | 10.138.75.0/25 | 10.183.8.129/26 | 0 | T1
801750 | 9791 Jane St | Maple | Ontario | L6A3N9 | Canada | c07472br1 | 1 | DSL | 0 | 10.138.45.0/25 | 10.155.6.1/25 | 0 | T1
801755 | 96 FANSHAWE PARK RD E | LONDON | Ontario | N5X4C5 | Canada | c07482br1 |  | 5M | 10.33.7.65/26 |  | 10.167.2.129/26 | 0 | T1
801756 | 72 VILLAGE RD | WHYCOCOMAGH | Nova Scotia | B0E3M0 | Canada | e07483br1 |  | T1 | 0 | 10.136.179.128/25 | 10.191.10.129/26 | 0 | T1
801757 | 1402 College Dr | Saskatoon | Saskatchewan | S7N 0W7 | Canada | w07488br5 | 1 | Other | 0 | 10.136.92.0/25 | 10.55.1.1/26 | 0 | T1
801759 | 8540 MANNING AVE | FORT MCMURRAY | Alberta | T9H5G2 | Canada | w07489br1 |  | 10M | 10.34.63.1/25 | 10.137.150.128/25 | 10.43.36.1/25 | 0 | 3M
801760 | 1795 HENDERSON HWY | WINNIPEG | Manitoba | R2G 1P3 | Canada | w07497br1 |  | 5M | 0 | 10.138.115.0/25 | 10.31.37.1/25 | 0 | T1
801762 | 2 QUEEN ST S | TOTTENHAM | Ontario | L0G1W0 | Canada | c07522br1 | 1 | DSL | 0 | 10.138.45.128/25 | 10.131.10.1/25 | 0 | T1
801765 | 112 DUNDAS ST W | TRENTON | Ontario | K8V 5R7 | Canada | c07542br1 | 1 | T1 | 0 | 10.137.199.128/25 | 10.131.5.1/26 | 0 | 3M
801766 | 1159 ALLOY DR | THUNDER BAY | Ontario | P7B 6M8 | Canada | w07546br1 |  | 5M | 0 | 10.137.151.0/25 | 10.67.41.1/24 | 0 | T1
801767 | 30-3140 Highway 69 N | VAL CARON | Ontario | P3N 1G3 | Canada | c07572br1 |  | T1 | 0 | 10.136.111.128/25 | 10.139.10.1/26 | 0 | T1
801769 | 552 JAMES ST | WALLACEBURG | Ontario | N8A2N9 | Canada | c07582br1 | 1 | DSL | 0 | 10.138.46.0/25 | 10.139.7.129/26 | 0 | 3M
801770 | 395 GRANDE COTE | ROSEMERE | Quebec | J7A 4R2 | Canada | e07591br1 |  | 5M | 0 | 10.137.36.0/25 | 10.219.1.129/26 | 0 | T1
801771 | 111 WATER ST | Windsor | Nova Scotia | B0N2T0 | Canada | e07593br1 | 1 | DSL | 0 | 10.138.75.128/25 | 10.203.46.1/25 | 0 | T1
801772 | 842 Broadway Ave | Saskatoon | Saskatchewan | S7N 1B6 | Canada | w07598br5 |  | Other | 0 | 10.136.92.128/25 | 10.11.7.1/26 | 0 | T1
801773 | 580 3RD ST SE | MEDICINE HAT | Alberta | T1A0H3 | Canada | w07599br1 | 1 | T1 | 0 | 10.137.232.128/25 | 10.23.29.1/25 | 0 | T1
801774 | 4501 West 10th Ave | VANCOUVER | British Columbia | V6R 2J2 | Canada | w07600br5 | 1 | Other | 0 | 10.136.93.0/25 | 10.11.51.1/25 | 0 | T1
801775 | 36 MAIN ST | WARKWORTH | Ontario | K0K3K0 | Canada | c07602br1 | 1 | DSL | 0 | 10.138.46.128/25 | 10.131.16.129/26 | 0 | T1
801780 | 2901 13TH AVE SE | MEDICINE HAT | Alberta | T1A3R1 | Canada | w07619br1 | 1 | T1 | 0 | 10.137.245.128/25 | 10.31.9.129/26 | 0 | T1
801785 | 100 RUE DU TERMINUS O | ROUYN NORANDA | Quebec | J9X6H7 | Canada | e07661br1 |  | T1 | 0 | 10.136.180.0/25 | 10.183.35.1/25 | 0 | T1
801786 | 304 DUNDAS ST E-PO BOX 80 | WATERDOWN | Ontario | L0R 2H0 | Canada | c07662br1 |  | 5M | 10.33.7.1/26 |  | 10.127.39.1/25 | 0 | T1
801790 | 4400 BOUL SOURCES | Dollard Des Ormeaux | Quebec | H8Y3B7 | Canada | e07671br1 | 1 | DSL | 0 | 10.138.76.0/25 | 10.219.2.1/26 | 0 | T1
801792 | 2490 MACDONALD ST | VANCOUVER | British Columbia | V6K3Z1 | Canada | w07680br1 | 1 | T1 | 0 | 10.137.233.0/25 | 10.23.2.129/25 | 0 | T1
801793 | 70-74 KING ST S | WATERLOO | Ontario | N2J 1N8 | Canada | c07682br1 |  | 5M | 10.33.0.129/26 |  | 10.127.16.129/26 | 0 | T1
801795 | 50 Westmount Rd N | Waterloo | Ontario | N2L 2R5 | Canada | c07692br5 |  | Other | 0 | 10.136.43.128/25 | 10.135.0.129/26 | 0 | T1
801801 | 248 KING ST N | WATERLOO | Ontario | N2J2Y7 | Canada | c07702br1 |  | 5M | 10.33.6.193/26 | 10.136.149.128/25 | 10.135.9.1/26 | 0 | T1
801803 | 437 main street | WOLFVILLE | Nova Scotia | B4P1E1 | Canada | e07703br1 | 1 | DSL | 0 | 10.138.76.128/25 | 10.215.5.1/26 | 0 | T1
801808 | 61 RUE ST VINCENT | SAINTE AGATHE DES MONTS | Quebec | J8C2A5 | Canada | e07711br1 | 1 | DSL | 0 | 10.138.77.0/25 | 10.215.6.129/26 | 0 | T1
801809 | 585 WEBER ST N | WATERLOO | Ontario | N2V1V8 | Canada | c07712br1 | 1 | T1 | 0 | 10.136.150.0/25 | 10.151.3.1/25 | 0 | T1
801812 | 30 CLAIREVUE BLVD W | ST-BRUNO | Quebec | J3V 1P8 | Canada | e07721br1 |  | 5M | 0 | 10.136.246.0/25 | 10.191.55.1/25 | 0 | 3M
801813 | 72 BROADWAY AVE | WAWA | Ontario | P0S1K0 | Canada | c07722br1 |  | T1 | 0 | 10.136.150.128/25 | 10.131.3.1/26 | 0 | T1
801816 | 12095 1e Ave | St-Georges | Quebec | G5Y 2E2 | Canada | e07731br5 | 1 | Other | 0 | 10.136.51.0/25 | 10.187.39.1/25 | 0 | T1
801817 | 1110 BOUL SACRE COEUR | ST FELICIEN | Quebec | G8K1A2 | Canada | e07741br1 | 1 | DSL | 0 | 10.138.77.128/25 | 10.183.9.1/26 | 0 | T1
801818 | 41 MAIN ST E | WELLAND | Ontario | L3B 3W4 | Canada | c07742br1 |  | T1 | 0 | 10.136.151.0/25 | 10.155.3.129/26 | 0 | T1
801819 | 15 WOROBETZ PL | SASKATOON | Saskatchewan | S7L6R4 | Canada | w07748br1 | 1 | T1 | 0 | 10.137.233.128/25 | 10.11.6.129/24 | 0 | T1
801820 | 430 ARTHUR SAUVE BLVD | ST-EUSTACHE | Quebec | J7R6V6 | Canada | e07751br1 | 1 | DSL | 0 | 10.138.78.0/25 | 10.207.47.1/25 | 0 | 3M
801824 | 2802 8TH ST E | SASKATOON | Saskatchewan | S7H 0V9 | Canada | w07758br1 |  | 5M | 0 | 10.137.151.128/25 | 10.27.72.1/24 | 0 | 3M
801825 | 6490 VICTORIA DR | VANCOUVER | British Columbia | V5P3X7 | Canada | w07760br1 | 1 | T1 | 0 | 10.137.234.0/25 | 10.55.37.1/25 | 0 | T1
801827 | 201 Frederica St W | Thunder Bay | Ontario | P7E 3W1 | Canada | w07782br5 | 1 | Other | 0 | 10.136.93.128/25 | 10.67.2.1/26 | 0 | T1
801828 | 571 NIAGARA ST | WELLAND | Ontario | L3C1L7 | Canada | c07792br1 |  | T1 | 0 | 10.136.151.128/25 | 10.155.11.129/26 | 0 | T1
801829 | 1050 CASAVANT BLVD W | SAINT-HYACINTHE | Quebec | J2S 8B9 | Canada | e07811br1 |  | 5M | 0 | 10.136.239.128/25 | 10.219.41.1/25 | 0 | T1
801830 | 399 MAIN ST | YARMOUTH | Nova Scotia | B5A 1G3 | Canada | e07813br1 |  | 5M | 0 | 10.136.227.0/25 | 10.183.40.1/25 | 0 | T1
801831 | 540 MAIN ST | WINNIPEG | Manitoba | R3B1C4 | Canada | w07817br1 | 1 | T1 | 0 | 10.137.234.128/25 | 10.11.38.1/25 | 0 | T1
801832 | 304 Centre St | Shaunavon | Saskatchewan | S0N 2M0 | Canada | w07818br5 |  | Other | 0 | 10.136.94.0/25 | 10.27.8.1/26 | 0 | T1
801833 | 10 TALBOT ST E | WHEATLEY | Ontario | N0P2P0 | Canada | c07822br1 | 1 | DSL | 0 | 10.138.47.0/25 | 10.131.14.129/26 | 0 | T1
801837 | 2517 BURRARD AVE | VANDERHOOF | British Columbia | V0J3A0 | Canada | w07840br1 | 1 | T1 | 0 | 10.136.224.0/25 | 10.63.10.1/26 | 0 | T1
801838 | 460 LABELLE ST | SAINT-JEROME | Quebec | J7Z 5L3 | Canada | e07841br1 |  | 5M | 0 | 10.137.37.0/25 | 10.215.44.1/25 | 0 | T1
801839 | 307 BROCK ST S | Whitby | Ontario | L1N4K3 | Canada | c07842br1 | 1 | DSL | 0 | 10.138.47.128/25 | 10.135.38.1/25 | 0 | 3M
801843 | 204 ELGIN ST | WHITE RIVER | Ontario | P0M3G0 | Canada | c07862br1 |  | T1 | 0 | 10.138.48.0/25 | 10.127.7.1/26 | 0 | T1
801844 | 135 RUE RICHELIEU | SAINT JEAN SUR RICHELIEU | Quebec | J3B6X7 | Canada | e07871br1 |  | T1 | 0 | 10.136.180.128/25 | 10.203.45.1/25 | 0 | T1
801845 | 577 BERFORD ST | WIARTON | Ontario | N0H2T0 | Canada | c07882br1 |  | T1 | 0 | 10.138.48.128/25 | 10.131.15.129/26 | 0 | T1
801846 | 481 MAIN ST | WINCHESTER | Ontario | K0C2K0 | Canada | e07902br1 | 1 | DSL | 0 | 10.138.78.128/25 | 10.179.12.1/26 | 0 | T1
801849 | 3130 30TH AVE or 3129 30th Ave or 3131 30th Ave? | VERNON | British Columbia | V1T 2C4 | Canada | w07920br1 |  | 5M | 0 | 10.137.152.0/25 | 10.67.42.1/25 | 0 | T1
801850 | 245 OUELLETTE AVE | Windsor | Ontario | N9A7J2 | Canada | c07922br1 |  | 5M | 0 | 10.137.104.0/25 | 10.131.70.1/24 | 0 | 3M
801856 | 165 Keats St | Southey | Saskatchewan | S0G 4P0 | Canada | w07928br5 |  | Other | 0 | 10.136.94.128/25 | 10.35.0.1/26 | 0 | T1
801857 | 9921 102 ST | MORINVILLE | Alberta | T8R1E7 | Canada | w07929br1 | 1 | DSL | 0 | 10.136.14.0/25 | 10.75.1.129/26 | 0 | T1
801858 | 2306 #6 Hwy. | VERNON | British Columbia | V1T7E3 | Canada | w07930br1 | 1 | T1 | 0 | 10.137.2.0/25 | 10.27.52.1/25 | 0 | T1
801862 | 635 VICTORIA AVE | ST-LAMBERT | Quebec | J4P 3R4 | Canada | e07941br1 |  | 5M | 0 | 10.137.118.0/25 | 10.219.2.129/25 | 0 | T1
801863 | 2669 HOWARD AVE | Windsor | Ontario | N8X4Z3 | Canada | c07942br1 | 1 | T1 | 0 | 10.137.200.0/25 | 10.151.10.1/26 | 0 | 3M
801864 | 669 Osborne St | Winnipeg | Manitoba | S0G 4P0 | Canada | w07947br5 |  | Other | 0 | 10.136.95.0/25 | 10.11.4.129/26 | 0 | T1
801865 | 4900 27TH ST | VERNON | British Columbia | V1T7G7 | Canada | w07950br1 |  | T1 | 0 | 10.136.212.0/25 | 10.63.9.1/26 | 0 | T1
801866 | 1600 HURON CHURCH RD | WINDSOR | Ontario | N9C 2L1 | Canada | c07952br1 |  | 5M | 0 | 10.136.233.0/25 | 10.139.3.129/26 | 0 | T1
801894 | 1079 DOUGLAS ST | VICTORIA | British Columbia | V8W2C5 | Canada | w08000cr1 |  | 5M | 0 | 10.136.247.128/25 | 10.43.74.1/24 | 0 | 3M
801895 | 4635 WYANDOTTE ST E | Windsor | Ontario | N8Y1H6 | Canada | c08002br1 |  | T1 | 0 | 10.136.152.0/25 | 10.155.14.129/26 | 0 | T1
801900 | 2614 TECUMSEH RD E | Windsor | Ontario | N8W1G2 | Canada | c08022br1 |  | T1 | 0 | 10.136.152.128/25 | 10.139.5.1/26 | 0 | T1
801902 | 707 FORT ST-2ND FLR | VICTORIA | British Columbia | V8W 3G3 | Canada | w08030br1 |  | 5M | 0 | 10.137.152.128/25 | 10.63.37.1/25 | 0 | T1
801903 | 144 Elizabeth St. | Okotoks | Alberta | T1S1K4 | Canada | w08039br1 | 1 | DSL | 0 | 10.136.28.0/25 | 10.11.14.129/25 | 0 | 3M
801905 | 304 Cook St | Victoria | British Columbia | V8V 3X6 | Canada | w08040br5 |  | Other | 0 | 10.136.95.128/25 | 10.79.1.129/26 | 0 | T1
801906 | 1282 HWY #8 | WINONA | Ontario | L8E5R1 | Canada | c08042br1 | 1 | DSL | 0 |  | 10.143.2.129/26 | 0 | T1
801907 | 6700 46 ST | OLDS | Alberta | T4H 0A2 | Canada | w08049br1 |  | 5M | 0 | 10.136.33.0/25 | 10.27.12.129/26 | 0 | T1
801908 | 8135 Wyandotte St E | Windsor | Ontario | N8S 1T4 | Canada | c08052br5 |  | Other | 0 | 10.136.44.0/25 | 10.139.10.129/26 | 0 | T1
801909 | 10036 100 ST | PEACE RIVER | Alberta | T8S1S8 | Canada | w08059br1 | 1 | DSL | 0 | 10.136.10.0/25 | 10.19.9.1/26 | 0 | T1
801910 | 777 ROYAL OAK DR Suite 600 | VICTORIA | British Columbia | V8X 4V1 | Canada | w08060br1 |  | 5M | 0 | 10.137.153.0/25 | 10.23.46.1/25 | 0 | T1
801911 | 131 WOODBRIDGE AVE | WOODBRIDGE | Ontario | L4L2S6 | Canada | c08062br1 |  | 5M | 0 | 10.137.200.128/25 | 10.127.36.1/25 | 0 | T1
801912 | 2855 PEMBINA HWY-UNIT 26 | WINNIPEG | Manitoba | R3T 2H5 | Canada | w08067br1 |  | 5M | 0 | 10.138.124.128/25 | 10.35.38.1/25 | 0 | 3M
801913 | 1701 Douglas Street - Unit #5 | VICTORIA | British Columbia | V8W 0C1 | Canada | w08080br1 |  | 5M | 10.34.3.1/26 |  | 10.67.56.1/25 | 0 | T1
801914 | 1127 DECARIE BLVD | ST-LAURENT | Quebec | H4L 3M8 | Canada | e08081br1 |  | 5M | 0 | 10.137.37.128/25 | 10.207.7.129/26 | 0 | 3M
801915 | 452 DUNDAS ST | WOODSTOCK | Ontario | N4S 1C1 | Canada | c08082br1 |  | 5M | 0 | 10.137.104.128/25 | 10.143.10.1/26 | 0 | T1
801916 | 3679 Westminster HWY | RICHMOND | British Columbia | V7C 5V2 | Canada | w08088br1 | 1 | T1 | 0 | 10.136.212.128/25 | 10.27.4.129/25 | 0 | T1
801917 | 101 College St. | Toronto | Ontario | M5G1L7 | Canada | c08099br1 |  | T1 | 0 |  | 10.131.25.129/25 | 0 | T1
801918 | 218 SPRINGBANK AVE | WOODSTOCK | Ontario | N4S7R3 | Canada | c08102br1 |  | T1 | 0 | 10.138.49.0/25 | 10.147.11.129/26 | 0 | T1
801919 | 4220 COMMERCE CIRCLE | VICTORIA | British Columbia | V8Z6N6 | Canada | w08110br1 | 1 | T1 | 0 | 10.136.213.0/25 | 10.55.49.1/25 | 0 | T1
801920 | 8689 VIAU BLVD | SAINT-LEONARD | Quebec | H1R 2T9 | Canada | e08111br1 |  | 5M | 0 | 10.137.118.128/25 | 10.187.1.129/25 | 0 | 3M
801921 | 3985 Highway 7 | Markham | Ontario | L3R 2A2 | Canada | c08112br1 |  | 5M | 10.33.4.193/26 |  | 10.11.111.129/25 | 0 | T1
801923 | 4186 PETROLIA ST | PETROLIA | Ontario | N0N1R0 | Canada | c08122br1 | 1 | DSL | 0 | 10.138.49.128/25 | 10.139.5.129/26 | 0 | T1
801930 | 109 Mountain St | Strasbourg | Saskatchewan | S0G 4V0 | Canada | w08148br5 |  | Other | 0 | 10.136.96.0/25 | 10.35.0.129/26 | 0 | T1
801931 | 732 MAIN ST | PINCHER CREEK | Alberta | T0K1W0 | Canada | w08149br1 | 1 | DSL | 0 | 10.136.8.128/25 | 10.19.10.1/26 | 0 | T1
801932 | 3854 DOUGALL AVE | Windsor | Ontario | N9G1X2 | Canada | c08152br1 |  | T1 | 0 | 10.137.201.0/25 | 10.127.3.1/26 | 0 | T1
801933 | 306 BURNSIDE RD WEST | VICTORIA | British Columbia | V8Z 1M1 | Canada | w08160br1 |  | 5M | 0 | 10.137.153.128/25 | 10.23.44.1/25 | 0 | T1
801934 | 5031 51ST AVE | PONOKA | Alberta | T4J1R7 | Canada | w08189br1 | 1 | DSL | 0 | 10.136.22.128/25 | 10.31.10.129/26 | 0 | T1
801935 | 885 PORTAGE AVE | WINNIPEG | Manitoba | R3G0P3 | Canada | w08197br1 | 1 | T1 | 0 | 10.137.235.0/25 | 10.27.38.1/25 | 0 | T1
801937 | 68 de la Gare St | Saint-Sauveur | Quebec | J0R 1R0 | Canada | e08211br1 |  | 5M | 0 | 10.136.240.0/25 | 10.215.50.1/25 | 0 | 3M
801938 | 370 Labelle Blvd. | ROSEMERE | Quebec | J7A3R8 | Canada | e08221br1 | 1 | T1 | 0 | 10.137.215.0/25 | 10.203.51.1/25 | 0 | 3M
801939 | 5117 50TH AVE | WHITECOURT | Alberta | T7S1A1 | Canada | w08229br1 | 1 | DSL | 0 | 10.136.24.0/25 | 10.75.2.129/26 | 0 | T1
801941 | 6791 Gaetz Ave (50 Ave) | RED DEER | Alberta | T4N 4C9 | Canada | w08249br1 |  | 5M | 0 | 10.138.18.0/25 | 10.11.7.129/26 | 0 | T1
801942 | 261 1st Ave Nw | Swift Current | Saskatchewan | S9H 0N1 | Canada | w08258br5 | 1 | Other | 0 | 10.136.96.128/25 | 10.31.48.1/25 | 0 | 3M
801943 | 4943 ROSS ST | RED DEER | Alberta | T4N 1X8 | Canada | w08259br1 |  | 5M | 0 | 10.137.43.128/25 | 10.27.76.1/24 | 0 | 3M
801945 | 2025 WILLIAM O`CONNELL BLVD | BURLINGTON | Ontario | L7M4E4 | Canada | c08272br1 |  | T1 | 0 | 10.137.201.128/25 | 10.151.5.129/25 | 0 | T1
801946 | 1195 PACIFIC BLVD | VANCOUVER | British Columbia | V6Z2R8 | Canada | w08280br1 |  | T1 | 0 | 10.137.235.128/25 | 10.19.38.129/25 | 0 | T1
801947 | 211 MARYCROFT AVE-SUITE 1 | WOODBRIDGE | Ontario | L4L 5X8 | Canada | c08282br1 |  | 5M | 0 | 10.137.105.0/25 | 10.155.5.129/25 | 0 | 3M
801948 | 1102 100th St | Tisdale | Saskatchewan | S0E 1T0 | Canada | w08288br5 |  | Other | 0 | 10.136.97.0/25 | 10.35.8.129/26 | 0 | T1
801949 | 440 Rue Brochu | Sept-Iles | Quebec | G4R 2W8 | Canada | e08291br5 |  | Other | 0 | 10.136.51.128/25 | 10.183.36.1/25 | 0 | T1
801950 | 2945 Jacklin Rd | VICTORIA | British Columbia | V9B5E3 | Canada | w08300br1 | 1 | T1 | 0 | 10.137.236.0/25 | 10.63.11.129/26 | 0 | T1
801951 | 2610 50 AVE-UNIT 100 | RED DEER | Alberta | T4R 1M3 | Canada | w08319br1 |  | 5M | 0 | 10.137.154.0/25 | 10.11.14.1/26 | 0 | T1
801952 | 370 PORTAGE AVE | WINNIPEG | Manitoba | R3C 0H3 | Canada | w08327br1 | 1 | 5M | 0 | 10.137.44.0/25 | 10.11.57.1/25 | 0 | 3M
801956 | 2255 OAK BAY AVE | VICTORIA | British Columbia | V8R 1G4 | Canada | w08340br1 | 1 | 5M | 0 | 10.137.155.128/25 | 10.23.50.1/25 | 0 | 3M
801957 | 3970 SHELBOURNE ST | VICTORIA | British Columbia | V8N 3E2 | Canada | w08370br1 |  | 5M | 0 | 10.137.154.128/25 | 10.23.45.1/25 | 0 | 3M
801959 | 1 PLAZA DE LA MAURICIE | SHAWINIGAN | Quebec | G9N7C1 | Canada | e08371br1 | 1 | DSL | 0 | 10.138.106.0/25 | 10.219.0.129/26 | 0 | T1
801958 | 695 7e Rue | SHAWINIGAN | Quebec | G9N7C1 | Canada | e08371br6 | 1 | DSL | 0 | 10.138.86.128/25 | 10.215.4.1/26 | 0 | T1
801960 | 476 PEEL ST | WOODSTOCK | Ontario | N4S1K1 | Canada | c08372br1 |  | 5M | 0 | 10.138.106.128/25 | 10.127.5.129/26 | 0 | 5M
801962 | 3650 GOSSET RD | Westbank | British Columbia | V4T2N4 | Canada | w08380br1 |  | 5M | 0 | 10.136.21.128/25 | 10.55.44.1/25 | 0 | T1
801963 | 164 SANDALWOOD PKY | BRAMPTON | Ontario | L6Z3S4 | Canada | c08382br1 | 1 | T1 | 0 | 10.137.202.0/25 | 10.155.6.129/26 | 0 | 3M
801967 | 341 Main Street | SHAWVILLE | Quebec | J0X2Y0 | Canada | e08391br1 |  | T1 | 0 | 10.136.5.0/25 | 10.183.13.129/26 | 0 | T1
801968 | 11 BELLEROSE DR-UNIT 24 | ST ALBERT | Alberta | T8N 5E1 | Canada | w08399br1 |  | 5M | 0 | 10.137.155.0/25 | 10.23.69.1/25 | 0 | 3M
801969 | 1705 MARINE DR | WEST VANCOUVER | British Columbia | V7V 1J5 | Canada | w08400cr1 |  | 10M | 0 | 10.137.70.0/25 | 10.23.42.1/25 | 0 | 3M
801970 | 2403 MARINE DR | WEST VANCOUVER | British Columbia | V7V 1L3 | Canada | w08440br1 |  | 5M | 0 | 10.137.156.0/25 | 10.79.1.1/26 | 0 | T1
801971 | 9921 100TH ST | SEXSMITH | Alberta | T0H3C0 | Canada | w08479br1 |  | T1 | 0 | 10.136.213.128/25 | 10.19.11.1/26 | 0 | T1
801972 | 672 Park Royal North | West Vancouver | British Columbia | V7T 1H9 | Canada | w08480br5 | 1 | Other | 0 | 10.136.97.128/25 | 10.23.41.1/25 | 0 | 3M
801973 | 4000 WHISTLER WAY- | WHISTLER | British Columbia | V0N 1B4 | Canada | w08500br1 |  | 5M | 0 | 10.137.156.128/25 | 10.23.68.1/25 | 0 | 3M
801980 | 105 MAIN ST | WADENA | Saskatchewan | S0A4J0 | Canada | w08538br1 | 1 | T1 | 0 | 10.136.108.128/25 | 10.35.12.129/26 | 0 | T1
801981 | 763 RUE KING E | SHERBROOKE | Quebec | J1G1C6 | Canada | e08541br1 |  | T1 | 0 | 10.136.181.0/25 | 10.179.2.129/26 | 0 | T1
801982 | 9325 Yonge St. | Richmond Hill | Ontario | L4C 0A8 | Canada | c08552br1 |  | 5M | 0 | 10.137.105.128/25 | 10.151.36.1/25 | 0 | 3M
801983 | 12675 RUE SHERBROOKE E | POINTE AUX TREMBLES | Quebec | H1A3W7 | Canada | e08561br1 | 1 | T1 | 0 | 10.137.215.128/25 | 10.187.36.1/25 | 0 | 3M
801984 | 33-35 HWY #20 E | FONTHILL | Ontario | L0S1E0 | Canada | c08562br1 | 1 | DSL | 0 | 10.138.50.0/25 | 10.155.4.1/26 | 0 | T1
801985 | 5128 Roblin Blvd | Winnipeg | Manitoba | R3R 0G9 | Canada | w08567br5 |  | Other | 0 | 10.136.98.0/25 | 10.19.41.129/25 | 0 | T1
801986 | 1550 ST MARYS RD | WINNIPEG | Manitoba | R2M 5M9 | Canada | w08577br1 |  | 5M | 0 | 10.137.157.0/25 | 10.23.53.1/25 | 0 | 3M
801987 | 1588 JOHNSTON RD or 1584 Johnson | WHITE ROCK | British Columbia | V4B 3Z7 | Canada | w08580br1 |  | 5M | 0 | 10.137.44.128/25 | 10.23.37.1/25 | 0 | 3M
801989 | 204 MAIN ST N | SLAVE LAKE | Alberta | T0G2A0 | Canada | w08589br1 | 1 | DSL | 0 | 10.136.1.128/25 | 10.75.1.1/26 | 0 | T1
801992 | 908 2ND AVE E--suite 300 | OWEN SOUND | Ontario | N4K2H6 | Canada | c08596br1 |  | 5M | 0 | 10.138.50.128/25 | 10.151.9.1/26 | 0 | T1
801993 | 1658 128ST | SURREY | British Columbia | V4A3V3 | Canada | w08610br1 | 1 | DSL | 0 | 10.138.86.0/25 | 10.67.1.1/25 | 0 | T1
801994 | 51 FOURTH AVE N | WILLIAMS LAKE | British Columbia | V2G4S1 | Canada | w08640br1 | 1 | T1 | 0 | 10.136.23.0/25 | 10.11.47.1/25 | 0 | 3M
801995 | 129 NOTRE DAME ST W | THETFORD MINES | Quebec | G6G 1J4 | Canada | e08641br1 |  | 5M | 0 | 10.137.38.128/25 | 10.219.0.1/26 | 0 | T1
801997 | 2310 RUE SAINT LOUIS | GATINEAU | Quebec | J8T5L7 | Canada | e08661br1 |  | T1 | 0 | 10.136.181.128/25 | 10.187.37.1/25 | 0 | T1
802007 | 202 Main St | Watrous | Saskatchewan | S0K 4T0 | Canada | w08698br5 |  | Other | 0 | 10.136.98.128/25 | 10.19.1.1/26 | 0 | T1
802008 | 4601 50TH ST | SPIRIT RIVER | Alberta | T0H3G0 | Canada | w08699br1 | 1 | DSL | 0 | 10.136.8.0/25 | 10.19.12.1/26 | 0 | T1
802010 | 4 MCLEOD AVE | SPRUCE GROVE | Alberta | T7X 4B8 | Canada | w08719br1 |  | 5M | 0 | 10.137.157.128/25 | 10.11.63.1/25 | 0 | 3M
802011 | 75 COWICHAN LAKE RD | LAKE COWICHAN | British Columbia | V0R2G0 | Canada | w08720br1 |  | T1 | 0 | 10.136.214.0/25 | 10.75.0.1/26 | 0 | T1
802033 | 5853 Rochdale Blvd | REGINA | Saskatchewan | S4X 4K8 | Canada | w08755br1 |  | T1 | 0 | 10.136.214.128/25 | 10.11.17.1/26 | 0 | T1
802037 | 25 MILVERTON DR | MISSISSAUGA | Ontario | L5R 3G2 | Canada | c08802br1 |  | 5M | 0 | 10.137.16.0/25 | 10.123.44.1/25 | 0 | T1
802038 | 107 Main St | Wawota | Saskatchewan | S0G5A0 | Canada | w08808br5 |  | Other | 0 | 10.138.131.0/25 | 10.19.13.1/26 | 0 | T1
802039 | 4125 BOUL DES FORGES | TROIS-RIVIERES | Quebec | G8Y1W1 | Canada | e08811br1 |  | T1 | 0 | 10.136.182.0/25 | 10.179.6.1/26 | 0 | T1
802041 | 13281 TECUMSEH RD E | TECUMSEH | Ontario | N8N3T4 | Canada | c08842br1 |  | T1 | 0 | 10.138.51.0/25 | 10.127.12.1/26 | 0 | T1
802042 | 689 3RD AVE | VAL-DOR | Quebec | J9P 1S7 | Canada | e08851br1 |  | 5M | 0 | 10.137.39.0/25 | 10.191.36.1/25 | 0 | T1
802048 | 220 Souris Ave | Weyburn | Saskatchewan | S4H 0C5 | Canada | w08918br1 |  | 5M | 0 | 10.136.99.0/25 | 10.31.4.129/26 | 0 | T1
802049 | 4920 51ST ST | STETTLER | Alberta | T0C2L0 | Canada | w08919br1 | 1 | DSL | 0 | 10.136.6.128/25 | 10.75.3.1/26 | 0 | T1
802050 | 169 RUE VICTORIA | VALLEYFIELD | Quebec | J6T1A5 | Canada | e08921br1 |  | T1 | 0 | 10.136.182.128/25 | 10.219.4.1/25 | 0 | T1
802051 | 209 COUNTY COURT BLVD | BRAMPTON | Ontario | L6W 4P5 | Canada | c08932br1 |  | 5M | 0 | 10.137.106.0/25 | 10.143.36.1/25 | 0 | 3M
802055 | 40 PLACE DU COMMERCE | Verdun | Quebec | H3E1J6 | Canada | e08971br1 | 1 | T1 | 0 | 10.136.183.0/25 | 10.191.58.1/25 | 0 | T1
802057 | 220 NORTH SERVICE RD W | OAKVILLE | Ontario | L6M2Y3 | Canada | c08982br1 |  | T1 | 0 | 10.136.153.0/25 | 10.19.37.129/25 | 0 | T1
802059 | 1950 BOUL RENE GAULTIER | VARENNES | Quebec | J3X1P5 | Canada | e08991br1 |  | T1 | 0 | 10.136.183.128/25 | 10.187.5.129/25 | 0 | T1
802060 | 1314 TOPSAIL RD | PARADISE | Newfoundland | A1L1n9 | Canada | e09003br1 |  | T1 | 0 | 10.137.216.0/25 | 10.179.4.129/26 | 0 | T1
802061 | 114 2nd Ave E | Wilkie | Saskatchewan | S0K 4W0 | Canada | w09028br5 |  | Other | 0 | 10.136.37.0/25 | 10.35.10.129/26 | 0 | T1
802062 | 100 Ranch Market Suite 121 | STRATHMORE | Alberta | T1P 0A8 | Canada | w09029br1 |  | 5M | 10.34.3.65/25 |  | 10.31.35.129/25 | 0 | T1
802063 | 652 Erb St. W.--unit B13 | WATERLOO | Ontario | N2T2Z7 | Canada | c09037br1 |  | T1 | 0 | 10.136.103.0/25 | 10.151.14.129/25 | 0 | T1
802065 | B 3089 WONDERLAND RD S | LONDON | Ontario | N6L1R4 | Canada | c09047cr1 |  | 5M | 0 | 10.137.238.0/25 | 10.155.44.1/25 | 0 | T1
802066 | 2121 CARLING AVE. | OTTAWA | Ontario | K2A1H2 | Canada | e09057br1 |  | 5M | 0 | 10.138.94.128/25 | 10.135.45.1/25 | 0 | 3M
802070 | 270 THE KINGSWAY | Etobicoke | Ontario | M9A3T7 | Canada | c09067br1 |  | T1 | 0 | 10.136.153.128/25 | 10.147.10.1/25 | 0 | T1
802074 | 550 LAVAL DR-UNIT 100 | OSHAWA | Ontario | L1J 0B5 | Canada | c09077cr1 |  | 5M | 0 | 10.136.227.128/25 | 10.155.46.1/25 | 0 | T1
802076 | 211 MARTINDALE RD | ST CATHARINES | Ontario | L2S 3V7 | Canada | c09082br1 |  | 5M | 0 | 10.137.16.128/25 | 10.147.0.129/25 | 0 | T1
802079 | 66 WEST ST | CORNER BROOK | Newfoundland | A2H 2Z3 | Canada | e09103br1 |  | 5M | 0 | 10.137.39.128/25 | 10.203.42.1/25 | 0 | T1
802080 | 588 SARGENT AVE | WINNIPEG | Manitoba | R3E0A1 | Canada | w09107br1 | 1 | T1 | 0 | 10.137.236.128/25 | 10.27.37.1/25 | 0 | T1
802082 | 133 RAILWAY AVE | WINDTHORST | Saskatchewan | S0G5G0 | Canada | w09138br1 |  | 5M | 0 | 10.138.116.0/25 | 10.27.5.1/26 | 0 | T1
802084 | 4370 RUE WELLINGTON | Verdun | Quebec | H4G1W4 | Canada | e09151br1 | 1 | T1 | 0 | 10.136.184.0/25 | 10.203.39.1/25 | 0 | T1
802085 | 78 ELIZABETH DR | GANDER | Newfoundland | A1V1J8 | Canada | e09153br1 |  | T1 | 0 | 10.136.184.128/25 | 10.203.41.1/25 | 0 | T1
802086 | 4818 53RD ST | TABER | Alberta | T1G1W4 | Canada | w09179br1 | 1 | DSL | 0 | 10.136.9.128/25 | 10.19.14.1/26 | 0 | T1
802087 | 118 NOTRE DAME ST E | VICTORIAVILLE | Quebec | G6P 3Z6 | Canada | e09181cr1 |  | 5M | 0 | 10.136.230.128/25 | 10.219.35.1/25 | 0 | T1
802088 | 1875 RUE NOTRE DAME | ANCIENNE-LORETTE | Quebec | G2E4K1 | Canada | e09191br1 |  | T1 | 0 | 10.136.185.0/25 | 10.203.1.129/26 | 0 | T1
802089 | 19 CROMER AVE | GRAND FALLS/WINDSOR | Newfoundland | A2A2K5 | Canada | e09203br1 | 1 | DSL | 0 | 10.138.79.0/25 | 10.179.7.129/26 | 0 | T1
802093 | 130 Country Village Rd. N.e. - Unit 100 | CALGARY | Alberta | T3K6B8 | Canada | w09219br1 | 1 | T1 | 0 | 10.137.237.0/25 | 10.35.35.1/25 | 0 | T1
802094 | 1 WESTMOUNT SQUARE | WESTMOUNT | Quebec | H3Z2P9 | Canada | e09231br1 |  | 5M | 0 | 10.137.40.0/25 | 10.215.45.1/25 | 0 | 3M
802095 | 75 RYLANDER BLVD | Toronto | Ontario | M1B5M5 | Canada | c09242br1 | 1 | T1 | 0 | 10.137.202.128/25 | 10.143.6.1/26 | 0 | T1
802096 | 45 COMMONWEALTH AVE | Mount Pearl | Newfoundland | A1N1W7 | Canada | e09243br1 |  | T1 | 0 | 10.136.185.128/25 | 10.179.5.1/26 | 0 | T1
802098 | 78 BROADWAY ST E | YORKTON | Saskatchewan | S3N 0K9 | Canada | w09248br1 |  | 5M | 0 | 10.138.18.128/25 | 10.31.49.1/25 | 0 | 3M
802099 | 501 MAIN ST | THREE HILLS | Alberta | T0M2A0 | Canada | w09249br1 | 1 | DSL | 0 | 10.136.13.128/25 | 10.19.15.1/26 | 0 | T1
802100 | 230-236 MAIN ROAD | HEARTS CONTENT | Newfoundland | A0B1Z0 | Canada | e09253br1 |  | T1 | 0 | 10.136.186.0/25 | 10.183.11.129/26 | 0 | T1
802109 | 3131 Strandherd Dr. | NEPEAN | Ontario | K2J5N1 | Canada | c09277br1 |  | 5M | 0 | 10.138.51.128/25 | 10.135.41.1/25 | 0 | T1
802150 | 396 CONCEPTION BAY HWY-ROUTE 60 | HOLYROOD | Newfoundland | A0A2R0 | Canada | e09303br1 |  | T1 | 0 | 10.136.114.0/25 | 10.183.4.129/26 | 0 | T1
802151 | 4849 SHERBROOKE ST W | WESTMOUNT | Quebec | H3Z 1G6 | Canada | e09311br1 |  | 5M | 0 | 10.137.40.128/25 | 10.187.40.1/25 | 0 | T1
802192 | 91 Conception Bay Hwy | Conception Bay South | Newfoundland | A1N3A3 | Canada | e09353br1 |  | T1 | 0 | 10.136.107.128/25 | 10.195.55.1/25 | 0 | T1
802194 | 104 MAIN ST | TURNER VALLEY | Alberta | T0L2A0 | Canada | w09359br1 | 1 | DSL | 0 | 10.136.14.128/25 | 10.19.40.129/25 | 0 | T1
802196 | 401 10TH ST | WAINWRIGHT | Alberta | T9W1N9 | Canada | w09389br1 |  | T1 | 0 | 10.136.215.0/25 | 10.27.11.1/26 | 0 | T1
802197 | 10427 100TH AVE | WESTLOCK | Alberta | T7P2J2 | Canada | w09399br1 | 1 | DSL | 0 | 10.136.15.128/25 | 10.23.5.129/26 | 0 | T1
802198 | 61 BLOCKHOUSE ROAD | Placentia | Newfoundland | A0B2Y0 | Canada | e09403br1 |  | T1 | 0 | 10.136.186.128/25 | 10.183.3.129/26 | 0 | T1
802202 | 649 Yonge St. | BARRIE | Ontario | L4N4E7 | Canada | c09409br1 | 1 | T1 | 0 | 10.136.154.0/25 | 10.135.42.1/25 | 0 | T1
802206 | 226 WATER ST | ST JOHNS | Newfoundland | A1C 1A9 | Canada | e09453br1 |  | 5M | 0 | 10.137.41.0/25 | 10.199.70.1/24 | 0 | 3M
802214 | 4916 50TH AVE | Wetaskiwin | Alberta | T9A3P8 | Canada | w09459br1 | 1 | DSL | 0 | 10.136.27.0/25 | 10.27.6.129/26 | 0 | T1
802221 | 65 ELIZABETH AVE | ST. JOHN'S | Newfoundland | A1A1W8 | Canada | e09503br1 |  | 5M | 0 | 10.137.41.128/25 | 10.191.38.1/25 | 0 | T1
802223 | 1296 TORBAY RD | TORBAY | Newfoundland | A1K1K5 | Canada | e09563br1 | 1 | DSL | 0 | 10.138.79.128/25 | 10.179.11.1/26 | 0 | T1
802224 | 337 FRESHWATER RD-PO BOX 8277 | ST JOHNS | Newfoundland | A1B 3N4 | Canada | e09573br1 |  | 5M | 0 | 10.137.119.0/25 | 10.179.39.1/25 | 0 | T1
802227 | 664 TOPSAIL RD | ST. JOHN'S | Newfoundland | A1E2E2 | Canada | e09603br1 |  | T1 | 0 | 10.137.216.128/25 | 10.179.4.1/26 | 0 | T1
802232 | 73 MAIN ST | STEPHENVILLE | Newfoundland | A2N1H9 | Canada | e09703br1 | 1 | DSL | 0 | 10.138.80.0/25 | 10.183.5.129/26 | 0 | T1
802233 | 17 WEST ST | Trinity | Newfoundland | A0C2S0 | Canada | e09753br1 |  | T1 | 0 | 10.136.187.0/25 | 10.183.5.1/26 | 0 | T1
802234 | 36 GRENFELL ST | HAPPY VALLEY GOOSE BAY | Newfoundland | A0P1E0 | Canada | e09801br1 |  | T1 | 0 | 10.136.187.128/25 | 10.183.38.1/25 | 0 | T1
802235 | 1761 Victoria St. East | Whitby | Ontario | L1N9W4 | Canada | c09837br1 | 1 | T1 | 0 | 10.137.203.0/25 | 10.135.58.1/25 | 0 | T1
802246 | 800 TAUNTON RD E | OSHAWA | Ontario | L1H 7K5 | Canada | c09847br1 |  | 5M | 0 | 10.137.106.128/25 | 10.157.48.1/25 | 0 | T1
802247 | IGLUVUT BUILDING #922 | IQALUIT | Northwest Territories | X0A0H0 | Canada | e09851br1 |  | 2M | #N/A | 10.138.115.128/25 | #N/A | #N/A | T1
802248 | 3205 Monarch Dr. | Orillia | Ontario | L3V7Z4 | Canada | c09857br1 | 1 | T1 | 0 | 10.137.203.128/25 | 10.157.53.1/25 | 0 | T1
802249 | 77 Woodland Dr | Hay River | Northwest Territories | X0E 1G1 | Canada | w09859br1 |  | T1 | #N/A | 10.136.99.128/25 | #N/A | #N/A | T1
802267 | 4920 52nd St | Yellowknife | Northwest Territories | X1A 3T1 | Canada | w09879br5 |  | Other | 0 | 10.136.37.128/25 | 10.63.43.1/25 | 0 | T1
802282 | 705 CENTRAL AVE | SASKATOON | Saskatchewan | S7N2S4 | Canada | w09902br1 |  | T1 | 0 | 10.136.215.128/25 | 10.55.1.129/26 | 0 | T1
802293 | 4110 4th Ave | Whitehorse | YT | Y1A 4N7 | Canada | w09950br1 |  | T1 | #N/A | 10.136.100.0/25 | #N/A | #N/A | T1
802317 | 10098 Mclauglin Rd. | BRAMPTON | Ontario | L7A2X6 | Canada | c09970br1 |  | T1 | 0 | 10.137.204.0/25 | 10.147.13.129/26 | 0 | T1
802318 | 1240 Steeles Ave. E.--Building D | Milton | Ontario | L9T6R1 | Canada | c09971br1 | 1 | T1 | 0 | 10.137.204.128/25 | 10.167.2.1/25 | 0 | T1
802319 | 11492 SARCEE TRAIL NW 0r 11792 SARCEE? | CALGARY | Alberta | T3R 0A1 | Canada | w09974br1 |  | 5M | 0 | 10.137.158.0/25 | 10.43.49.1/25 | 0 | T1
802323 | 564 HWY 132 SERVICE RD-SUITE 800 | SAINT-CONSTANT | Quebec | J5A 2S6 | Canada | e09985br1 |  | 5M | 0 | 10.137.119.128/25 | 10.191.40.1/25 | 0 | T1
802324 | 2965 Argentia Rd. | Mississauga | Ontario | L5N 0A2 | Canada | c09987br1 | 1 | T1 | 0 | 10.137.205.0/25 | 10.127.52.1/25 | 0 | 3M
802325 | 1450 Major Mackenzie Dr. | Richmond Hill | Ontario | L4S0A1 | Canada | c09998br1 |  | T1 | 0 | 10.137.205.128/25 | 10.157.40.1/25 | 0 | T1
802326 | 12935 YONGE ST | RICHMOND HILL | Ontario | L4E 0G7 | Canada | c09999br1 |  | 5M | 0 | 10.137.107.0/25 | 10.157.50.1/25 | 0 | T1
802357 | 3100 LE CARREFOUR | LAVAL | Quebec | H7T2K7 | Canada | e10756br1 |  | T1 | 0 | 10.137.242.128/25 | 10.203.54.1/25 | 0 | T1
802361 | 2 BLOOR ST E-23rd floor | TORONTO | Ontario | M4W 1A8 | Canada | c10761br1 |  | 10M | 0 | 10.137.68.0/25 | 10.143.77.1/24 | 0 | 3M
802366 | 4 ROBERT SPECK PKWY | MISSISSAUGA | Ontario | L4Z1S1 | Canada | c10766br1 |  | 10M | 0 | 10.138.128.128/25 | 10.157.38.129/25 | 0 | 3M
802372 | 10117 JASPER AVE | EDMONTON | Alberta | T5J1W8 | Canada | w10773br1 |  | 10M | 0 | 10.138.96.0/25 | 10.11.69.1/25 | 0 | T1
802382 | 238A BROWNLOW AVE | DARTMOUTH | Nova Scotia | B3B2B4 | Canada | e11176sr1 |  | T1 | 0 | 10.138.107.0/25 | 10.207.6.1/26 | 0 | T1
802442 | 1220 Lebourgneuf Street | Quebec City | Quebec | G2K2G4 | Canada | e12113sr1 |  | T1 | 0 | 10.136.110.0/25 | 10.195.54.1/25 | 0 | T1
802444 | 2 Bloor St. E. Lower Concourse | Toronto | Ontario | M4W1A8 | Canada | c12991sr1 |  | T1 | 0 | 10.136.218.0/25 | 10.157.44.1/25 | 0 | T1
802470 | 111 GRANGEWAY AVE-SUITE 400 | SCARBOROUGH | Ontario | M1H 3E9 | Canada | c13147sr1 |  | 5M | 0 | 10.137.53.128/25 | 10.153.16.1/24 | 0 | 3M
802473 | 383 RICHMOND ST. 8TH FLR | LONDON | Ontario | N6A3C4 | Canada | c13158sr1 |  | T1 | 0 | 10.136.218.128/25 | 10.123.9.129/26 | 0 | T1
802774 | 10655 SOUTHPORT RD SW | CALGARY | Alberta | T2W4Y1 | Canada | w15112sr1 |  | 10M | 0 | 10.138.107.128/25 | 10.139.43.1/25 | 0 | 10M
802778 | 287 LACEWOOD DR | HALIFAX | Nova Scotia | B3M 3Y7 | Canada | e15227sr1 |  | 5M | 0 | 10.137.54.0/25 | 10.191.16.1/26 | 0 | T1
802796 | 2485 Appleby Line - Unit G2 | BURLINGTON | Ontario | L7L0B6 | Canada | c15286sr1 | 1 | T1 | 0 | 10.136.109.0/25 | 10.155.48.1/25 | 0 | T1
802815 | 25 Peel Centre Drive - Unit 435 | BRAMPTON | Ontario | L6T3R5 | Canada | c15405sr1 | 1 | T1 | 0 | 10.136.109.128/25 | 10.155.49.1/25 | 0 | T1
802819 | 2525 Prince Michael Drive | OAKVILLE | Ontario | L6H0E9 | Canada | c15432sr1 |  | T1 | 0 | 10.136.237.128/25 | 10.143.53.1/25 | 0 | T1
802896 | 3960 Quadra St. | VICTORIA | British Columbia | V8X4A3 | Canada | Not found! |  |  | #N/A |  | #N/A | #N/A | T1
802898 | 2985 VIRTUAL WAY UNIT 300 | VANCOUVER | British Columbia | V5M4X7 | Canada | w16113sr1 |  | 5M | 0 | 10.138.108.0/25 | 10.147.49.1/24 | 0 | 5M
802899 | 300 ANEMKI PL, STE E THUNDER BAY ON Canada P7G 1H9 | Thunder Bay | Ontario | P791H9 | Canada | w16147br5 |  | Other | 0 | 10.136.100.128/25 | sh int g0/2.2 | 0 | T1
802902 | 610 SIXTH ST SUITE 201 | New Westminster | British Columbia | V3L 3C2 | Canada | w16258br1 |  | 10M | 10.34.62.129/25 |  | 10.63.71.1/24 | 0 | 5M
802904 | 221 Woodlawn Rd. W.--unit B11 and B12 | GUELPH | Ontario | N1H 8P4 | Canada | c16345br1 |  | 5M | 0 | 10.136.243.128/25 | 10.135.65.1/25 | 0 | 3M
802928 | 1 ADELAIDE ST E | TORONTO | Ontario | M5C2V9 | Canada | c16481vr1 |  | 10M | 0 | 10.138.108.128/25 | 10.135.74.1/24 | 0 | 10M
803012 | 6455 RUE JEAN-TALON E | St Leonard | Quebec | H1S3E8 | Canada | e17322br1 |  | 5M | 10.32.129.1/25 |  | 10.22.3.1/24 | 0 | T1
803014 | 412 DU SUD | COWANSVILLE | Quebec | J2K2X7 | Canada | e90322vr6 |  | T1 | 0 | 10.138.109.0/25 | 10.193.65.1/24 | 0 | T1
803015 | 1129 4TH STREET | ESTEVAN | Saskatchewan | S4A0W6 | Canada | w90771vr6 |  | T1 | #N/A | 10.138.109.128/25 | #N/A | #N/A | T1
803019 | 1959 Upper Water St. | HALIFAX | Nova Scotia | B3J3N2 | Canada | e90270vr1 |  | 10M | 10.32.27.2/25 |  | 10.195.44.2/25 | 0 | 3M
803021 | 296 MAIN ST | YARMOUTH | Nova Scotia | B5A 1E4 | Canada | e90270vr6 |  | 5M | 10.32.4.65/26 |  | 10.11.41.129/25 | 0 | 5M
803020 | 410 MAIN STREET | WOLFVILLE | Nova Scotia | B4P1C9 | Canada | e90270vr3 |  | 5M | 0 | 10.138.110.0/25 | 10.191.16.129/26 | 0 | 5M
803022 | 10 FORT WILLIAM PL-SUITE 803 | ST JOHNS | Newfoundland | A1C 5P9 | Canada | e90275vr1 |  | 5M | 0 | 10.137.58.0/25 | 10.193.121.1/24 | 0 | 3M
803024 | 44 CHIPMAN HILL | SAINT JOHN | New Brunswick | E2L2A9 | Canada | e90282vr1 |  | 5M | 0 | 10.138.96.128/25 | 10.193.141.1/24 | 0 | T1
803025 | 371 QUEEN ST | FREDERICTON | New Brunswick | E3B4Y9 | Canada | e90283vr1 |  | 10M | 0 | 10.136.229.0/25 | 10.193.93.1/24 | 0 | 3M
803026 | 633 Main St. | MONCTON | New Brunswick | E1C9X9 | Canada | e90286vr1 |  | 5M | 0 | 10.137.58.128/25 | 10.195.51.1/25 | 0 | 3M
803028 | 134 KENT ST SUITE #602 PO BOX #276 | Charlottetown | Prince Edward Island | C1A8R8 | Canada | e90288vr1 |  | 5M | 0 | 10.137.177.128/25 | 10.193.48.1/24 | 0 | 3M
803029 | 10665 1ere Ave, Suite 210 | Saint Georges | Quebec | G5Y 6X8 | Canada | e90301vr1 | 1 | Other | 0 | 10.138.127.0/25 | 10.11.58.129/25 | 0 | 3M
803030 | 1501 AVE MCGILL COLLEGE | MONTREAL | Quebec | H3A3M8 | Canada | e90311vr1 |  | 10M | 0 | 10.33.67.0/24 | 10.193.52.2/24 | 0 | 10M
803031 | 4 WESTMOUNT SQUARE SUITE #130 | WESTMOUNT | Quebec | H3Z2S6 | Canada | e90313vr1 |  | T1 | 0 | 10.136.219.128/25 | 10.193.4.1/24 | 0 | T1
803032 | 383 SIR WILFRID LAURIER BD | MONT-SAINT-HILARIE | Quebec | J3H 3P1 | Canada | e90314vr1 |  | DSL | 10.32.128.129/25 |  | 10.22.2.1/24 | 0 | T1
803033 | 35 RUE DUFFERIN | GRANBY | Quebec | J2G4W5 | Canada | e90322vr1 | 1 | T1 | 0 | 10.138.91.128/25 | 10.193.28.1/24 | 0 | 3M
803034 | 9140 Boulevard Leduc Suite 220 | Brossard | Quebec | J4Y 0L2 | Canada | e90323vr1 |  | 5M | 10.32.2.65/26 |  | 10.11.40.129/25 | 0 | T1
803035 | 455 RUE KING O BUREAU | SHERBROOKE | Quebec | J1H6E9 | Canada | e90326vr1 |  | 5M | 0 | 10.137.178.0/25 | 10.193.16.1/24 | 0 | 5M
803036 | 1000 rue de la Gauchetière O | MONTRÉAL | Quebec | H3B 4W5 | Canada | e90327vr1 | 1 | 20M | 10.32.3.2/25 |  | 10.193.133.2/24 | 0 | T1
803038 | 2828 LAURIER BD. | QUEBEC | Quebec | G1V2M1 | Canada | e90331vr1 |  | 10M | 10.219.52.129/25 |  | 10.219.52.1/25 | 0 | 10M
803039 | 497 Racine St. E. | Chicoutimi | Quebec | G7H1T8 | Canada | e90333vr1 | 1 | T1 | 0 | 10.138.90.128/25 | 10.195.9.129/26 | 0 | 3M
803040 | 25 RUE DES FORGES | TROIS-RVIERES | Quebec | G9A6A7 | Canada | e90337vr1 |  | 5M | 0 | 10.137.59.0/25 | 10.193.129.1/24 | 0 | 10M
803041 | 2450 Pierre-Péladeau Ave | LAVAL | Quebec | H7T3B3 | Canada | e90341vr1 | 1 | 5M | 0 | 10.33.73.0/24 | 10.195.68.1/24 | 0 | 10M
803042 | 755 BOUL ST JEAN | Pointe Claire | Quebec | H9R5M9 | Canada | e90345vr1 |  | 10M | 0 | 10.33.65.0/24 | 10.193.81.2/24 | 0 | 10M
803043 | 975 BOUL ST JOSEPH | HULL | Quebec | J8Z1W8 | Canada | e90348vr1 |  | 5M | 0 | 10.137.59.128/25 | 10.193.72.1/24 | 0 | 3M
803045 | 17120 Leslie St. - Suite 200 | NEWMARKET | Ontario | L3Y8K7 | Canada | c90407vr1 |  | 5M | 0 | 10.136.231.0/25 | 10.167.54.1/25 | 0 | 10M
803046 | 14785 YONGE ST-2ND FLR | AURORA | Ontario | L4G 1N1 | Canada | c90409vr1 |  | 5M | 0 | 10.137.170.0/25 | 10.151.15.129/26 | 0 | 3M
803047 | 5140 YONGE ST PO BOX #28--SUITE 2120 | Toronto | Ontario | M2N6L7 | Canada | c90411vr1 | 1 | 20M | 0 | 10.33.74.0/24 | 10.165.48.1/24 | 0 | 10M
803048 | 3300 HWY #7 -suite 701 | Concord | Ontario | L4K4M3 | Canada | c90414vr1 |  | 5M | 0 | 10.136.248.128/25 | 10.165.12.1/24 | 0 | 10M
803049 | 260 EAST BEAVER CREEK RD, SUITE Suite 500 – 5th F | Richmond Hill | Ontario | L4B3M3 | Canada | c90416vr1 | 1 | 20M | 0 | 10.33.70.0/23 | 10.165.68.1/24 | 0 | 10M
803050 | 111 Grangeway Ave | SCARBOROUGH | Ontario | M1H 3E9 | Canada | c90417vr1 |  | 5M | 10.33.3.129/26 |  | 10.165.4.1/24 | 0 | T1
803051 | 2 BLOOR ST -23rd Floor | Toronto | Ontario | M4W1A8 | Canada | c90428vr1 | 1 | 5M | 0 | 10.138.92.0/25 | 10.165.80.1/24 | 0 | 10M
803052 | 3250 BLOOR ST W SUITE #705 | Etobicoke | Ontario | M8X2X9 | Canada | c90439cr1 |  | 10M | 0 | 10.136.228.128/25 | 10.165.8.1/24 | 10.167.39.129/25 | 10M
803053 | 2345 YONGE ST | Toronto | Ontario | M4P2E6 | Canada | c90447vr1 |  | 10M | 10.33.0.1/26 |  | 10.165.16.1/24 | 0 | T1
803054 | 45 Saint Clair Avenue West --11th floor--Suite 11 | Toronto | Ontario | M4V1K9 | Canada | c90452vr1 |  | 5M | 0 | 10.138.90.0/25 | 10.135.66.1/25 | 0 | 10M
803055 | 65 Ontario St. South. Unit H | Milton | Ontario | L9T2T2 | Canada | c90500cr1 |  | 5M | 0 | 10.137.169.0/25 | 10.157.63.1/25 | 0 | T1
803056 | 45 O'connor St. --suite 900 | Ottawa | Ontario | K1P1A4 | Canada | e90501vr1 | 1 | 10M | 0 | 10.33.68.0/24 | 10.193.157.2/24 | 0 | 10M
803057 | 333 Preston Street | OTTAWA | Ontario | K1S5N4 | Canada | e90503vr1 | 1 | 5M | 0 | 10.138.92.128/25 | 10.195.56.1/25 | 0 | 10M
803058 | 82 KING ST W | BROCKVILLE | Ontario | K6V 3P9 | Canada | e90504vr1 |  | 10M | 0 | 10.137.71.128/25 | 10.193.8.1/24 | 0 | 3M
803059 | 10 THIRD ST E | CORNWALL | Ontario | K6H 2C7 | Canada | e90505vr1 |  | 5M | 0 | 10.137.60.0/25 | 10.193.113.1/24 | 0 | T1
803060 | 303 MOODIE DR 5TH FL--suite 5500 | NEPEAN | Ontario | K2H9R4 | Canada | e90508vr1 |  | 5M | 0 | 10.136.248.0/25 | 10.193.76.1/24 | 0 | 5M
803061 | 366 KING ST E SUITE E #210 | KINGSTON | Ontario | K7K6Y3 | Canada | c90509vr1 |  | 5M | 0 | 10.137.55.128/25 | 10.165.32.1/24 | 0 | 5M
803062 | 60 HUNTER STREET EAST | PETERBOROUGH | Ontario | K9H1G5 | Canada | c90511vr1 |  | 5M | 10.167.59.129/25 |  | 10.167.59.1/25 | 0 | 5M
803064 | 204D DIVISION ST | COBOURG | Ontario | K9A 3P7 | Canada | c90514vr1 |  | 5M | 0 | 10.137.171.0/25 | 10.165.106.1/24 | 0 | T1
803065 | 10 FRONT ST S-3RD FLR | BELLEVILLE | Ontario | K8N 2Y3 | Canada | c90515vr1 |  | 5M | 0 | 10.137.56.0/25 | 10.165.36.1/24 | 0 | 3M
803066 | 17 King St. E.--3rd floor | OSHAWA | Ontario | L1H1A8 | Canada | c90522vr1 |  | 5M | 0 | 10.136.249.0/25 | 10.167.40.1/25 | 0 | 5M
803067 | 1672 Lakeshore Rd. W. | Clarkson | Ontario | L5J1J5 | Canada | c90530vr1 |  | 5M | 0 | 10.137.178.128/25 | 10.157.6.129/26 | 0 | 3M
803068 | 50 QUEEN ST W SUITE #300 | BRAMPTON | Ontario | L6X4H3 | Canada | c90531vr1 |  | 5M | 0 | 10.137.171.128/25 | 10.165.96.1/24 | 0 | 5M
803069 | 210 BROADWAY AVE SUITE #207 | ORANGEVILLE | Ontario | L9W5G4 | Canada | c90533vr1 |  | T1 | 0 | 10.136.219.0/25 | 10.165.190.1/24 | 0 | T1
803070 | 4 Robert Speck Parkway-suite 1100 | Mississauga | Ontario | L4Z1S1 | Canada | c90535vr1 | 1 | 5M | 0 | 10.33.72.0/24 | 10.157.38.1/25 | 0 | 10M
803071 | 210 LAKESHORE RD E | OAKVILLE | Ontario | L6L 1H2 | Canada | c90536vr1 |  | 5M | 0 | 10.138.22.128/25 | 10.129.20.1/24 | 0 | 3M
803072 | 435 North Service Rd. W. | OAKVILLE | Ontario | L6M4X8 | Canada | c90537vr1 | 1 | 5M | 0 | 10.33.75.0/24 | 10.167.52.1/25 | 0 | 10M
803073 | 60 REBECCA ST | OAKVILLE | Ontario | L6K1J2 | Canada | c90537vr6 |  | 5M | 10.33.3.193/26 |  | 10.11.36.129/25 | 0 | 10M
803074 | 4475 North Service Rd | Burlington | Ontario | L7L4X7 | Canada | rbCABU4475r04g1 |  | 10M | 10.86.130.0/25 | 10.86.130.0/25 | 10.86.128.0/24 | 0 | T1
803075 | 11 Victoria St. --Suite 100 | BARRIE | Ontario | L3N6T3 | Canada | c90541vr1 |  | 5M | 0 | 10.137.172.0/25 | 10.127.51.1/25 | 0 | 10M
803076 | 19 FRONT ST N-SUITE 200 | ORILLIA | Ontario | L3V 4R6 | Canada | c90542vr1 |  | 5M | 0 | 10.137.172.128/25 | 10.167.8.129/26 | 0 | 3M
803077 | 1 First St. - Suite 230 | COLLINGWOOD | Ontario | L9Y1A1 | Canada | c90544vr1 |  | 5M | 0 | 10.137.173.0/25 | 10.167.53.1/25 | 0 | 3M
803078 | 30 West Mall Rd | BRACEBRIDGE | Ontario | P1L 2G3 | Canada | c90546vr1 |  | 3M | 0 | 10.137.182.0/25 | 10.167.14.1/26 | 0 | 3M
803079 | 512 Yonge St | MIDLAND | Ontario | L4R 2C5 | Canada | c90547vr1 |  | 3M | 0 | 10.138.24.0/25 | 10.167.13.129/26 | 0 | 3M
803080 | 42 WYNDHAM ST N PO BOX #995 | GUELPH | Ontario | N1H4E6 | Canada | c90551vr1 |  | 5M | 0 | 10.136.249.128/25 | 10.165.186.1/24 | 0 | 3M
803081 | 231 Shearson Crescent, 3rd Floor | CAMBRIDGE | Ontario | N1T1J5 | Canada | c90555vr1 |  | 5M | 0 | 10.137.174.0/25 | 10.167.13.1/26 | 0 | 3M
803082 | 95 KING ST S-3RD FLR | WATERLOO | Ontario | N2J 5A2 | Canada | c90561vr1 | 1 | 10M | 0 | 10.33.69.0/24 | 10.167.76.1/24 | 0 | 10M
803083 | 274 LYNDEN RD | BRANTFORD | Ontario | N3T 5L8 | Canada | c90565vr1 |  | 5M | 0 | 10.137.174.128/25 | 10.167.0.65/26 | 0 | 3M
803084 | 100 KING ST W-SUITE 1500/STELCO Building | HAMILTON | Ontario | L8P 1A2 | Canada | c90571cr1 | 1 | 20M | 0 | 10.136.232.0/25 | 10.165.28.24/24 | 10.165.30.2/24 | 10M
803085 | 259 WILSON AVE | ANCASTER | Ontario | L9G2B8 | Canada | c90571vr6 | 1 | 5M | 10.167.58.129/25 |  | 10.167.58.1/25 | 0 | 10M
803086 | 41 MAIN ST W | GRIMSBY | Ontario | L3M1R3 | Canada | c90571vr3 |  | 5M | 10.151.16.193/26 |  | 10.151.16.129/26 | 0 | 5M
803087 | 63 CHURCH ST SUITE #306 | ST CATHARINES | Ontario | L2R3C4 | Canada | c90581vr1 |  | 10M | 10.32.130.1/25 |  | 10.22.5.1/24 | 0 | 5M
803088 | 2 NORFOLK ST S-UNIT 100 | NORFOLK | Ontario | N3Y2V9 | Canada | c90583vr1 |  | 5M | 10.157.5.65/26 |  | 10.157.5.1/26 | 0 | 5M
803089 | 4342 Queen St. | Niagara Falls | Ontario | L2E2K9 | Canada | c90587vr1 |  | 5M | 0 | 10.137.175.0/25 | 10.167.12.1/26 | 0 | 3M
803090 | 187 Ontario Street -1st and 2nd floor | STRATFORD | Ontario | N5A3H3 | Canada | c90588vr1 |  | 5M | 0 | 10.137.175.128/25 | 10.167.9.1/26 | 0 | 3M
803091 | 619 10TH ST W. | OWEN SOUND | Ontario | N4K3R9 | Canada | c90591vr1 |  | 5M | 0 | 10.137.176.0/25 | 10.156.34.1/24 | 0 | 3M
803092 | 945 STOCKDALE ROAD | NORTH BAY | Ontario | P1B9S5 | Canada | c90601vr1 |  | 5M | 10.165.41.1/24 |  | 10.157.23.129/25 | 0 | T1
803093 | 85 PINE ST S | Timmins | Ontario | P4N 2K1 | Canada | c90605vr5 |  | Other | #N/A | 10.138.127.128/25 | #N/A | #N/A | T1
803094 | 1001 Williams St. | THUNDER BAY | Ontario | P7B6M1 | Canada | w90608vr1 |  | 5M | 0 | 10.137.60.128/25 | 10.43.8.1/26 | 0 | 3M
803096 | 1361 PARIS ST SUITE 200 | SUDBURY | Ontario | P3E3B6 | Canada | c90613vr1 |  | 5M | 10.33.1.129/26 |  | 10.165.114.1/24 | 0 | T1
803097 | 432 GREAT NORTHERN RD-3RD FLR | SAULT STE MARIE | Ontario | P6B 4Z9 | Canada | c90615vr1 |  | 5M | 0 | 10.137.57.0/25 | 10.167.56.1/25 | 0 | 3M
803098 | 1922 WYANDOTTE ST E 3RD FL | Windsor | Ontario | N8Y1E4 | Canada | c90621vr2 |  | 5M | 0 | 10.138.93.0/25 | 10.165.166.1/24 | 0 | 10M
803099 | 5 MILL ST | LEAMINGTON | Ontario | N8H1R6 | Canada | c90621vr1 | 1 | T1 | 0 | 10.138.110.128/25 | 10.156.14.1/24 | 0 | 3M
803100 | 340 NORTH FRONT STREET | SARNIA | Ontario | N7T5S7 | Canada | c90631vr1 |  | 5M | 0 | 10.137.176.128/25 | 10.165.170.1/24 | 0 | 3M
803101 | 302 JAMES | WALLACEBURG | Ontario | N8A2N5 | Canada | c90635vr1 |  | 5M | 10.157.0.193/26 |  | 10.156.18.1/24 | 0 | T1
803102 | 44 WILLIAM ST N | CHATHAM | Ontario | N7M 4L2 | Canada | c90637vr1 |  | 5M | 0 | 10.137.177.0/25 | 10.157.8.1/26 | 0 | 3M
803103 | 148 FULLARTON ST 19TH FL -suite 1900 | LONDON | Ontario | N6A5P3 | Canada | c90641vr1 | 1 | 20M | 0 | 10.33.66.0/24 | 10.165.174.2/24 | 0 | 10M
803104 | 26 HURON ST | WOODSTOCK | Ontario | N4S 6Z2 | Canada | c90647vr1 |  | 5M | 0 | 10.137.57.128/25 | 10.165.154.1/24 | 0 | 3M
803106 | 600 Crowfoot Crescent N.W. - Unit 410 | CALGARY | Alberta | T3G0B4 | Canada | w90706vr1 |  | 5M | 0 | 10.137.61.0/25 | 10.43.50.1/25 | 0 | 3M
803108 | 204 1ST AVE S | LETHBRIDGE | Alberta | T1J0A4 | Canada | w90711vr1 |  | 5M | 0 | 10.137.61.128/25 | 10.41.36.1/24 | 0 | 5M
803110 | 320 South Railway Street S.E. | MEDICINE HAT | Alberta | T1A2V4 | Canada | w90715vr1 |  | 5M | 0 | 10.137.62.0/25 | 10.43.9.1/26 | 0 | 3M
803111 | 14505 Bannister Rd. S.E. - Unit 203 | CALGARY | Alberta | T2X3J3 | Canada | w90717vr1 |  | 5M | 10.75.35.129/25 |  | 10.75.68.1/24 | 0 | T1
803112 | 111 FAIRFORD ST E | MOOSE JAW | Saskatchewan | S6H 7X5 | Canada | w90718vr1 |  | 5M | 0 | 10.137.179.128/25 | 10.41.142.1/24 | 0 | T1
803113 | 4901 48TH ST UNIT #301 | RED DEER | Alberta | T4N6M4 | Canada | w90721vr1 |  | 10M | 10.32.129.129/25 |  | 10.22.4.1/24 | 0 | 5M
803114 | 10155 102 ST NW | EDMONTON | Alberta | T5J 4L4 | Canada | w90731vr1 |  | 5M | 0 | 10.136.34.0/25 | 10.73.150.1/24 | 0 | T1
803116 | 10180-101ST ST | EDMONTON | Alberta | T5J3S4 | Canada | w90731vr1 |  | 5M | 0 | 10.136.34.0/25 | 10.73.150.1/24 | 0 | 3M
803115 | 289 Powder Drive | Fort Mcmurray | Alberta | T9K0M5 | Canada | w90731vr6 | 1 | T1 | 0 | 10.137.243.128/25 | 10.43.8.129/26 | 0 | 3M
803118 | 9856 97TH AVE (old address: 9815 98 | GRANDE PRAIRIE | Alberta | T8V7K2 | Canada | w90734vr1 | 1 | T1 | 0 | 10.136.220.0/25 | 10.73.78.1/24 | 0 | T1
803120 | 10235 101TH ST SUITE #2400 | Edmonton | Alberta | T5J2K8 | Canada | w90736vr1 |  | 10M | 10.75.72.1/24 |  | 10.73.66.1/24 | 0 | T1
803121 | 3106 3rd Ave - 4th Flr Hougen | Whitehorse | YT | Y1A 5G1 |  | w90752vr5 | 1 | Other | 0 | 10.138.128.0/25 | sh int g0/2.2 | 0 | T1
803124 | 410 22nd St E | Saskatoon | Saskatchewan | S7K3S5 | Canada | w90761vr1 |  | 10M | 0 | 10.137.72.0/25 | 10.41.162.2/24 | 0 | 10M
803125 | 1101 101st STREET SUITE #601 | NORTH BATTLEFORD | Saskatchewan | S9A0Z5 | Canada | w90762vr1 | 1 | T1 | 0 | 10.136.220.128/25 | 10.73.14.1/24 | 0 | T1
803128 | 1129 4th St Estevan SK Canada S4A 0W6 | Estevan | Saskatchewan | S4A0W6 |  | w90771vr1 |  |  | #N/A |  | #N/A | #N/A | 3M
803130 | 137 1ST AVE NE | SWIFT CURRENT | Saskatchewan | S9H 3X3 | Canada | w90776vr1 |  | 5M | 0 | 10.137.180.0/25 | 10.41.98.1/24 | 0 | T1
803132 | 2052 WEST 41ST AVE | VANCOUVER | British Columbia | V6M1Y8 | Canada | w90805vr1 | 1 | 5M | 0 | 10.136.22.0/25 | 10.41.28.1/24 | 0 | 10M
803134 | 960 QUAYSIDE DR-SUITE 201 | NEW WESTMINSTER | British Columbia | V3M 6G2 | Canada | w90806vr1 |  | 5M | 10.34.15.1/25 |  | 10.73.2.1/24 | 0 | T1
803135 | 2001 McCALLUM RD | ABBOTSFORD | British Columbia | V2S3N5 | Canada | w90808vr1 |  | 5M | 0 | 10.136.231.128/25 | 10.41.158.1/24 | 0 | 10M
803138 | 250 15TH ST | WEST VANCOUVER | British Columbia | V7T2X4 | Canada | w90809vr1 |  | 5M | 0 | 10.136.20.0/25 | 10.41.24.1/24 | 0 | 10M
803140 | 2626 CROYDEN DR | SURREY | British Columbia | V3S 0S8 | Canada | w90810vr1 |  | 10M | 10.67.54.130/25 |  | 10.67.54.2/25 | 0 | T1
803141 | 2701A Highway 6 | VERNON | British Columbia | V1T5G6 | Canada | w90811vr1 |  | 5M | 10.43.51.129/25 |  | 10.43.51.1/25 | 0 | T1
803142 | 320 ALEXANDER ST NE | SALMON ARM | British Columbia | V1E4S1 | Canada | w90812vr1 | 1 | DSL | 0 | 10.138.111.128/25 | 10.73.6.1/24 | 0 | T1
803143 | 186 VICTORIA ST | Kamloops | British Columbia | V2C5R3 | Canada | w90823vr1 |  | 5M | 10.73.36.1/24 |  | 10.73.30.1/24 | 0 | T1
803144 | 101-100 FRONT STREET | PENTICTON | British Columbia | V2A 1H1 | Canada | w90825vr1 |  | 5M | 0 | 10.137.62.128/25 | 10.73.74.1/24 | 0 | 3M
803145 | 926 BAKER ST | CRANBROOK | British Columbia | V1C 1A5 | Canada | w90826vr1 |  | 5M | 10.34.1.129/26 |  | 10.41.126.1/24 | 0 | T1
803147 | 5811 COONEY RD | RICHMOND | British Columbia | V6X3M1 | Canada | w90829vr1 |  | 5M | 10.34.5.1/26 |  | 10.41.0.1/24 | 0 | T1
803149 | 1708 Dolphin Ave | KELOWNA | British Columbia | V1Y 9S4 | Canada | w90832cr1 |  | 10M | 0 | 10.136.233.128/25 | 10.75.41.1/25 | 10.73.118.1/24 | 10M
803150 | 6588 APPLECROSS RD | NANAIMO | British Columbia | V9V 0A4 | Canada | w90835vr1 |  | 5M | 10.75.64.129/25 |  | 10.75.64.1/25 | 0 | T1
803151 | 550 VICTORIA ST-SUITE 310 | PRINCE GEORGE | British Columbia | V2L 2K1 | Canada | w90836vr1 |  | 5M | 0 | 10.137.180.128/25 | 10.73.58.1/24 | 0 | 3M
803152 | 8411-200TH ST | LANGLEY | British Columbia | V2Y0E7 | Canada | w90839cr1 |  | 5M | 10.43.54.129/25 |  | 10.43.54.1/25 | 0 | T1
803154 | 730 VIEW ST | VICTORIA | British Columbia | V8W 3Y7 | Canada | w90851vr1 | 1 | 5M | 0 | 10.33.64.0/24 | 10.73.102.1/24 | 0 | 10M
803156 | 2491 Bevan Avenue | SIDNEY | British Columbia | V8L 1W2 | Canada | w90853vr1 | 1 | T1 | 0 | 10.136.221.0/25 | 10.75.11.129/26 | 0 | T1
803158 | 2755 BEVERLY ST SUITE 201 2ND FL | DUNCAN | British Columbia | V9L6X2 | Canada | w90855vr7 | 1 | T1 | 0 | 10.138.112.0/25 | 10.75.67.1/25 | 0 | 5M
803157 | 5050 UPLANDS DR | NANAIMO | British Columbia | V9T6N1 | Canada | w90855vr1 |  | 5M | 10.75.67.129/25 |  | 10.73.82.1/24 | 0 | 3M
803159 | 1260 Shoppers Row Suite 210 | Campbell River | British Columbia | V9W2C8 | Canada | w90857vr2 |  | 5M | 10.34.0.65/26 |  | 10.73.90.1/24 | 0 | 3M
803160 | 777A FITZGERALD AVENUE | COURTENAY | British Columbia | V9N2R4 | Canada | w90857vr1 |  | 5M | 0 | 10.138.112.128/25 | 10.41.170.1/24 | 0 | T1
803161 | 650 WEST 41ST AVE-SUITE 638 | VANCOUVER | British Columbia | V5Z 2M9 | Canada | w90862vr1 |  | 5M | 0 | 10.137.181.0/25 | 10.43.53.1/25 | 0 | 3M
803165 | 1789 LONSDALE AVE | NORTH VANCOUVER | British Columbia | V7M2J6 | Canada | w90865vr1 |  | 5M | 0 | 10.138.91.0/25 | 10.73.174.1/24 | 0 | 3M
803105 | 333 7th Ave SW - 14th Flr Calgary AB Canada T2P 2Z1 | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?

## Rate Centre Analysis
Holidays | HolidayQC | HolidayBC
2014-09-01 | 2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13 | 2014-10-13
2014-12-25 | 2014-12-25 | 2014-12-25
2014-12-26 | 2014-12-26 | 2014-12-26
2015-01-01 | 2015-01-01 | 2015-01-01
2015-02-09 | 2015-06-24 | 2015-02-09 | 809024 | 2015-05-01
2015-02-16 | 2015-04-03 | 2015-04-03 | 803076 | 2015-05-04
2015-04-03 | 2015-04-06 | 2015-04-06 | 801489 | 2015-05-05
2015-04-06 | 2015-05-18 | 2015-05-18 | 801441 | 2015-05-05
2015-05-18 | 2014-06-24 | 2015-07-01 | 800913 | 2015-05-05
2015-07-01 | 2015-07-01 | 2015-08-03 | 800454 | 2015-05-05
2015-08-03 | 2015-08-03 | 2015-09-07 | 800686 | 2015-05-05
2015-06-15 |  |  | 801384 | 2015-05-05
2015-09-07 | 2015-09-07 |  | 800227 | 2015-05-05
|  |  | 800855 | 2015-05-07
|  |  | 803052 | 2015-05-06
|  |  | 809012 | 2015-05-06
|  |  | 803043 | 2015-05-06
|  |  | 801455 | 2015-05-06
|  |  | 802055 | 2015-05-06
|  |  | 800285 | 2015-05-06
|  |  | 800335 | 2015-05-06
|  |  | 800109 | 2015-05-06
|  |  | 809069 | 2015-06-08
|  |  | 809084 | 2015-05-08
|  |  | 803060 | 2015-05-11
|  |  | 800928 | 2015-05-07
|  |  | 801535 | 2015-05-07
|  |  | 801983 | 2015-05-07
|  |  | 800859 | 2015-05-07
|  |  | 801607 | 2015-05-08
|  |  | 801378 | 2015-05-08
|  |  | 803089 | 2015-05-13
|  |  | 809059 | 2015-05-12
|  |  | 800714 | 2015-05-12
|  |  | 800786 | 2015-05-12
|  |  | 800683 | 2015-05-12
|  |  | 800082 | 2015-05-12
|  |  | 801362 | 2015-05-12
|  |  | 800360 | 2015-05-13
|  |  | 803030 | 2015-05-19
|  |  | 803067 | 2015-05-19
|  |  | 800612 | 2015-05-12
|  |  | 800582 | 2015-05-14
|  |  | 801165 | 2015-05-14
|  |  | 800937 | 2015-05-14
|  |  | 800023 | 2015-05-14
|  |  | 801488 | 2015-05-15
|  |  | 800057 | 2015-05-15
|  |  | 801959 | 2015-05-15
|  |  | 803081 | 2015-05-21
|  |  | 801589 | 2015-05-20
|  |  | 801025 | 2015-05-20
|  |  | 801173 | 2015-05-20
|  |  | 800119 | 2015-05-20
|  |  | 801906 | 2015-05-20
|  |  | 800918 | 2015-05-20
|  |  | 800279 | 2015-05-21
|  |  | 800104 | 2015-05-21
|  |  | 800202 | 2015-05-21
|  |  | 802318 | 2015-05-21
|  |  | 800607 | 2015-05-21
|  |  | 803103 | 2015-05-26
|  |  | 801198 | 2015-05-22
|  |  | 800263 | 2015-05-22
|  |  | 801051 | 2015-05-22
|  |  | 809062 | 2015-05-22
|  |  | 801465 | 2015-05-25
|  |  | 802088 | 2015-05-25
|  |  | 801161 | 2015-05-25
|  |  | 800395 | 2015-05-25
|  |  | 809070 | 2015-05-28
|  |  | 800179 | 2015-05-27
|  |  | 802095 | 2015-05-27
|  |  | 800096 | 2015-05-27
|  |  | 800592 | 2015-05-27
|  |  | 800018 | 2015-05-27
|  |  | 800447 | 2015-05-27
|  |  | 800820 | 2015-05-27
|  |  | 803057 | 2015-06-01
|  |  | 803039 | 2015-06-02
|  |  | 800813 | 2015-05-28
|  |  | 801005 | 2015-05-28
|  |  | 803090 | 2015-06-02
|  |  | 801699 | 2015-05-28
|  |  | 801239 | 2015-05-29
|  |  | 809103 | 2015-06-01
|  |  | 803070 | 2015-06-03
|  |  | 802366 | 2015-06-03
|  |  | 809092 | 2015-06-03
|  |  | 800876 | 2015-05-29
|  |  | 802815 | 2015-06-02
|  |  | 801215 | 2015-06-02
|  |  | 801594 | 2015-06-03
|  |  | 800898 | 2015-06-03
|  |  | 803056 | 2015-06-08
|  |  | 800887 | 2015-06-02
|  |  | 801992 | 2015-06-04
|  |  | 800011 | 2015-06-04
|  |  | 800147 | 2015-06-04
|  |  | 800105 | 2015-06-04
|  |  | 801006 | 2015-06-05
|  |  | 801702 | 2015-06-05
|  |  | 801615 | 2015-06-05
|  |  | 800006 | 2015-06-05
|  |  | 801167 | 2015-06-05
|  |  | 801078 | 2015-06-05
|  |  | 800042 | 2015-06-05
|  |  | 803069 | 2015-06-10
|  |  | 803078 | 2015-06-10
|  |  | 801820 | 2015-06-09
|  |  | 801487 | 2015-06-09
|  |  | 801087 | 2015-06-09
|  |  | 801326 | 2015-06-09
|  |  | 800044 | 2015-06-10
|  |  | 800857 | 2015-06-10
|  |  | 800296 | 2015-06-10
|  |  | 800657 | 2015-06-10
|  |  | 801984 | 2015-06-10
|  |  | 801963 | 2015-06-10
|  |  | 800090 | 2015-06-11
|  |  | 803072 | 2015-06-17
|  |  | 800247 | 2015-06-16
|  |  | 801416 | 2015-06-16
|  |  | 800888 | 2015-06-16
|  |  | 803029 | 2015-06-19
|  |  | 803097 | 2015-06-22
|  |  | 801561 | 2015-06-18
|  |  | 800391 | 2015-06-18
|  |  | 801642 | 2015-06-19
|  |  | 800416 | 2015-06-19
|  |  | 809072 | 2015-06-24
|  |  | 809073 | 2015-06-24
|  |  | 803083 | 2015-06-29
|  |  | 800047 | 2015-06-25
|  |  | 803049 | 2015-07-02
|  |  | 801863 | 2015-06-26
|  |  | 809088 | 2015-07-02
|  |  | 803101 | 2015-07-02
|  |  | 803104 | 2015-07-07
|  |  | 801866 | 2015-07-03
|  |  | 809075 | 2015-07-09
|  |  | 800982 | 2015-07-09
|  |  | 803092 | 2015-07-14
|  |  | 803091 | 2015-07-14
|  |  | 803085 | 2015-07-14
|  |  | 801377 | 2015-07-13
|  |  | 800295 | 2015-07-13